Hydro Capacity addition Programme for 2021-22

(As on 30.09.2021)

| Sl. No. | Name of the project (Capacity) | Unit Nos. | Cap. (MW) | Capacity Addition as Programmed (Month) | Capacity Addition Actual (Date) | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| A. | State Sector |  |  |  |  |  |
| 1 | Pallivasal KSEB, Kerala 2x30=60 MW | Unit #1 Unit # 2 | 30 30 | March’22 March’22 |  | Likely to slip |
| 2 | Thottiyar KSEB, Kerala 1x30+1x10=40MW | Unit #1 Unit # 2 | 10 30 | March’22 March’22 |  | Likely to slip. |
|  | Sub- total (A): |  | 100 MW |  |  |  |
| B. | Private Sector |  |  |  |  |  |
| 3 | Sorang HSPCL, H.P. 2x50=100 MW | Unit #1 Unit # 2 | 50 50 | September’21 September’21 | 23.09.2021 21.09.2021 | Commissioned Commissioned |
| 4 | Bajoli Holi GMRBHHPPL, H.P. 3x60=180 MW | Unit #1 Unit # 2 Unit # 3 | 60 60 60 | November’21 November’21 November’21 |  |  |
| 5 | Rongnichu MBPCL, Sikkim 2x56.5=113 MW | Unit #1 Unit # 2 | 56.5 56.5 | June’21 June’21 | 25.06.2021 30.06.2021 | Commissioned Commissioned |
|  | Sub- total (B): |  | 393 MW |  |  |  |
|  | Total (A+B) |  | 493 MW |  |  |  |

Note  :- 213 MW out of the target of 493 MW commissioned .