## Sheet1
Sl No. | Project Name | Agency/Owner | Sector (PSU/Pvt) | Capacity (MW) | Year of Stoppage | Total Investment till Date (₹ Cr) | Primary Reasons (Geological/Land/Legal)
1 | Lata Tapovan | NTPC | PSU | 171 | 2014 | 149.93 | Legal (Work stopped since 07.05.2014 in pursuance of Hon'ble Supreme Court Order)
2 | Lower Kalnai | JKSPDC | State | 48 | 2019 | 57.54 | EPC bids were initially invited in July 2011, wherein M/s Coastal Projects Ltd. emerged as the L-1 bidder with a negotiated contract value of Rs. 396.00 crore against an estimated completion cost of Rs. 576.87 crore. The award was approved on 21.08.2013 with a stipulated completion period of 48 months (up to September 2017). However, physical progress remained limited to approximately 9% by August 2017, and the contractor sought extension of time. During the same period, M/s Coastal Projects Ltd. was declared a defaulter by RBI and became subject to insolvency proceedings. Consequently, the bank guarantees amounting to Rs. 79.53 crore were encashed &the contract,terminated. Subsequently, after updating the project cost for the balance works, fresh tenders were invited vide e-NIT dated 24.03.2022. After evaluation and conduct of e-reverse auction, the L-1 bidder was identified, with the quoted price being approximately 19% above the estimated cost. At the quoted cost, the projected tariff exceeded Rs. 6.00 per unit, rendering the project financially unviable. Accordingly, the BoDs of JKSPDC decided to retender the works after undertaking an updation of the DPR, particularly with respect to hydrology and design parameters, with a view to enhancing generation potential in light of the current status of Indus Waters Treaty provisions. In this regard, the tender for updation of the DPR is under process and is being floated shortly
3 | Koyna left bank | WRD | State | 80 | 2017 | 461.82 | Work order terminated due to non performance. Project stalled since July, 2015.
4 | Tangnu romai | TRPGCL | Pvt | 44 | 2014 | 257 | The primary reason for the stoppage of work was the legal issues raised by the local villagers. Subsequently, the company undertaking the project became bankrupt, which further delayed the project execution, We just Acquired the company under IBC route.
5 | Phata Byung | Statkraft | Pvt | 76 | 2017 | 1263 | Works stalled since July, 2017 due to Financial crunch of the erstwhile owner.The project now stands alloted to M/s Statkraft IH through NCLT on 23.03.2023. The revival of Environmental clearance is under process. Project construction can only start after EC issued by MOEF and supplementary Implementation Agreement is signed .
6 | Maheshwar | SMHPC | Pvt | 400 | 2011 | 3101 | Promoter inability to infuse equity for timely project completion. Concurrently, R&R cost has risen from Rs. 171 crore to Rs. 1364 crore impacting project viability & resultant fund constraint for project completion.
7 | Rangit-II | SHPVL | Pvt | 66 | 2017 | 120 | The Project had reveiced all clearanes from Central and State Government. However,the Project got delayed due to non availibility of Additional Land for the project in time, and non-availibility of Debt Fund, leading to one of the operational creditor approached NCLT in 2020, in the mean time the validity of Environmental Clearance was over. Preesntly preperation of EIA EMP is in process.for revalidation of expired Environment Clearance
8 | Panan | Himgiri | Pvt | 300 | 2016-10-01 | 200 | Geological & Natural Calamities (with intervening Legal pause): a sequence of force majeure events with construction restarted between events — (i) 2011 Sikkim earthquake; (ii) 2014 NBWL / Eco-Sensitive Zone pause following Hon'ble Supreme Court directions (NBWL granted October 2019 (Mantam lake formation 2016 ) access to project site disconnected.(iii) January 2020 COVID-19 pandemic, through 2022; (iv) October 2023 South Lhonak GLOF event severely disrupting public access roads and bridges to the project area across the Teesta basin. Site access depends on completion of the two-lane Kayem bridge, Upper Dzongu (under construction by PWD, GoS).
9 | Bhasmey | Gati Infra | Pvt | 51 | 2016 | 353 | Matter is sub-judice. The Court appointed Resolution Professional for Bhasmey HEP stated that works stalled since Sept., 2016. CIRP has been initiated against Gati infra and NCLT has appointed Resolution Professional .The Resolution Professional has received 4 Resolution Plan in the matter of Gati Infrastructure Bhasmey Power Private Limited and are pending for approval from the Committee of Creditors.
|  |  | Total | 1236