Hydro Capacity Addition Programme for 2025-26

| Sl. No. | Name of Project | State/ Implem. Agency | Unit No. | Capacity (MW) |  | Capacity Addition |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target | Actual | As Programmed/ Anticipated |
|  | Central Sector |  |  |  |  |  |
| 1 | Parbati-II /NHPC (4*200=800 MW) | Himachal Pradesh/NHPC | U-4 | 200 | 200 | Commissioned on 13.04.2025 |
| 2 | Tehri PSS/THDC (4*250=1000 MW) | Uttarakhand/THDC | U-1 U-2 U-3 U-4 | 250 250 250 250 | 0 | May'25 Jun’25 Aug’25 Oct’25 |
| 3 | Rangit-IV/NHPC | Sikkim | U-1 U-2 U-3 | 40 40 40 | 0 | Dec'25 Dec'25 Dec'25 |
| 4 | SUBANSIRI LOWER /NHPC 8X250=2000 MW | Arunachal Pradesh | U-1 U-2 U-3 U-4 U-5 | 250 250 250 250 250 | 0 | Dec’25 Jan’26 Jan’26 Feb’26 Feb’26 |
|  |  | Sub-total (Central): |  | 2570 | 200 |  |
|  | State Sector |  |  |  |  |  |
| 3 | Lower Sileru Extension /APGENCO) | Andhra Pradesh | U-1 U-2 | 115 115 | 0 | Mar'26 Mar'26 |
| 4 | Lower Kopili /APGCL | Assam | U-1 U-2 | 55 55 | 0 | Sep'25 Sep'25 |
| 5 | Kundah Pumped Storage (Phase-I, Phase-II & Phase-III) /TANGEDCO | Tamil Nadu | U-1 U-2 U-3 | 125 125 125 | 0 | Feb'26 Feb'26 Mar'26 |
|  |  | Sub-total (State): |  | 715 | 0 |  |
|  | Private Sector |  |  |  |  |  |
| 6 | Pinnapuram 4X240+2X120 =1200 MW | Andhra Pradesh/M/s Greenko Energies Pvt. Ltd. | U-1 U-2 U-3 U-4 U-5 U-6 U-7 U-8 | 240 240 240 240 120 120 240 240 | 0 | May’25 May’25 May’25 Jun’25 Jun’25 Jul’25 Aug’25 Sept’25 |
| 7 | Kutehr/JSW 3x80=240MW | Himachal Pradesh | U-1 U-2 U-3 | 80 80 80 |  | May’25 May’25 May’25 |
|  |  | Sub-total (Private): |  | 1920 | 0 |  |
| Total (CS+SS+PS) |  |  |  | 5205 | 200 |  |