## Sheet2
Annex-1A
List of Hydro Electric Projects (above 25 MW) under active construction
Sl. No. | Name of Scheme | Sector | District | I.C. ( No. X MW.) | Cap. Under Execution(MW) | River/Basin | Likely Commissioning
(Executing Agency)
Andhra Pradesh
1 | Polavaram (APGENCO/ Irrigation Dept., A.P.) | State | East & West Godavari | 12x80 | 960 | Godavari/EFR | 2024-26
| Sub-total: Andhra Pradesh |  |  |  | 960
Arunachal Pradesh
2 | Subansiri Lower (NHPC) | Central | Lower Subansiri | 8x250 | 2000 | Subansiri/ Brahmaputra | 2023-24 (Aug'23)
| Sub-total: Arunachal Pradesh |  |  |  | 2000
Assam
3 | Lower Kopli (APGCL) | State | Dima Hasao & Karbi Anglong | 2x55+2x2.5+1x5 | 120 | Kopili | 2024-25 (Jun'24)
| Sub-total: Assam |  |  |  | 120
Himachal Pradesh
4 | Parbati St. II (NHPC) | Central | Kullu | 4x200 | 800 | Parbati/Beas/Indus | 2022-23 (Mar'23)
5 | Luhri-I (SJVN) | Central | Kullu/Shimla | 2x80+2x25 | 210 | Satluj/Indus | 2025-26 (Jan'26)
6 | Dhaulasidh (SJVN) | Central | Hamirpur/ Kangra | 2x33 | 66 | Beas | 2025-26 (May'25)
7 | Uhl-III (BVPCL) | State | Mandi | 3x33.33 | 100 | Uhl/Beas/ Indus | 2022-23 (Dec'22)
8 | Shongtong Karcham (HPPCL) | State | Kinnaur | 3x150 | 450 | Satluj/ Indus | 2024-25 (Mar'25)
9 | Bajoli Holi (GMR) | Private | Chamba | 3x60 | 180 | Ravi/ Indus | 2021-22 (Sept'21)
10 | Sorang (HSPCL) | Private | Kinnaur | 2x50 | 100 | Sorang/Satluj/Indus | 2021-22 (Jun'21)
11 | Tidong-I (Statkraft IPL) | Private | Kinnaur | 100 | 100 | Tidong/Satluj/Indus | 2022-23 (Jun'22)
12 | Kutehr (JSW Energy Ltd) | Private | Chamba | 3x80 | 240 | Ravi/ Indus | 2025-26 (Nov'25)
| Sub-total: Himachal Pradesh |  |  |  | 2246
Jammu & Kashmir
13 | Pakal Dul (CVPPL) | Central | Kishtwar | 4x250 | 1000 | Marusadar/ Chenab / Indus | 2025-26 (July'25)
14 | Parnai (JKSPDC) | State | Poonch | 3x12.5 | 37.5 | Jhelum/ Indus | 2022-23 (Mar'23)
15 | Kiru (CVPPL) | Central | Kishtwar | 4x156 | 624 | Chenab/ Indus | 2024-25 (Aug.'24)
| Sub-total: Jammu & Kashmir |  |  |  | 1661.5
Kerala
16 | Pallivasal (KSEB) | State | Idukki | 2x30 | 60 | Mudirapuzha/ Periyar/ Baypore Periyar/ WFR | 2021-22 (Dec'21)
17 | Thottiyar (KSEB) | State | Idukki | 1x30+1x10 | 40 | Thottiyar/ Periyar/ / Baypore Periyar/ WFR | 2021-22 (Dec'21)
| Sub-total: Kerala |  |  |  | 100
Punjab
18 | Shahpurkandi (PSPCL/ Irrigation Deptt., Pb.) | State | Gurdaspur | 3x33+3x33+1x8 | 206 | Ravi/ Indus | 2023-24 (Dec'23)
| Sub-total: Punjab |  |  |  | 206
Sikkim
19 | Teesta St. VI NHPC | Central | South Sikkim | 4x125 | 500 | Teesta/Brahmaputra | 2023-24 (Mar'24)
20 | Rongnichu (Madhya Bharat) | Private | East Sikkim | 2x56.5 | 113 | Rongnichu/ Teesta/ Brahmaputra | 2021-22 (June'21)
| Sub-total: Sikkim |  |  |  | 613
Tamil Nadu
21 | Kundah Pumped Storage Phase-I,II&III) | State | Nilgiris | 4x125 | 500 | Kundah/Bhavani/ Cauvery/EFR | 2023-24 (Apr'23)
| Sub-total: Tamil Nadu |  |  |  | 500
Uttarakhand
22 | Tehri PSS (THDC) | Central | Tehri Garhwal | 4x250 | 1000 | Bhilangna/Bhagirathi/ Ganga | 2022-23 (Dec'22)
23 | Vishnugad Pipalkoti (THDC) | Central | Chamoli | 4x111 | 444 | Alaknanada/Ganga | 2023-24 (Dec'23)
24 | Naitwar Mori (SJVNL) | Central | Uttarkashi | 2x30 | 60 | Tons/Yamuna/Ganga | 2022-23 (June'22)
25 | Tapovan Vishnugad (NTPC) | Central | Chamoli | 4x130 | 520 | Dhauliganga / Alaknanada & /Ganga | 2023-24
26 | Vyasi (UJVNL) | State | Dehradun | 2x60 | 120 | Yamuna/Ganga | 2022-23 (Apr'22)
| Sub-total: Uttarakhand |  |  |  | 2144
West Bengal
27 | Rammam-III (NTPC) | Central | Darjeeling | 3x40 | 120 | Rammam/ Rangit/Teesta Brahmaputra | 2022-23 (Nov'22)
| Sub-total: West Bengal |  |  |  | 120
| Total: |  |  |  | 10670.5
CIRS:-Central India River System ; EFR:-Eastern Flowing Rivers ; WFR:-Western Flowing Rivers.