## Annex-1B
List of Hydro Electric Projects(above 25 MW) for which construction is held up (As on 30.09.2021)
Sl. No. | Name of Scheme | Sector | District | I.C. ( No. X MW.) | Cap. Under Execution(MW) | River/Basin | Date of finish/ commissioning* | Present Status/Reasons
(Executing Agency)
Himachal Pradesh
1 | Tangnu Romai (TRPG) | Private | Shimla | 2x22 | 44 | Pabbar/Tons/ Yamuna/ Ganga | 2024-25 | Works are on hold since Aug 2016 due to fund constraints with developer.
| Sub-total: Himachal Pradesh |  |  |  | 44
Jammu & Kashmir
2 | Lower Kalnai (JKSPDC) | State | Kishtwar | 2x24 | 48 | Chenab/ Indus | 2025-26 | Works on all fronts at Dam and Power House site are stalled since the contract has been terminated by JK Govt. order no. 115-PDD of 2019 dated 08.06.2019.
3 | Ratle (RHEPPL / NHPC) | Central | Kishtwar | 4x205 + 1x30 | 850 | Chenab/Indus | 2025-26 | The Project has been stalled since 11.07.2014 due to various issues viz. R&R issues, Local issues, Law & order problem etc. Earlier, it was under execution by private sector developer and some works already have been done. There is no progress since 11th July, 2014. CCEA approval accorded on 11.02.2021. Promoters agreement signed between Government of UT of Jammu & Kashmir, JKPDC and NHPC on 17.03.2021 for establishment of Joint Venture Company. JV formation is in process. Govt. of UT of J&K vide order dated 23 March 2021 conveyed the approval of Administrative Council for incorporation of the JV. The order also conveyed name of the JV as ‘RATLE HYDROELECTRIC POWER CORPORATION LIMITED”. The Promoters agreement between NHPC & JKSPDC for the formation of JV has been signed on 13.04.2021.
| Sub-total: Jammu & Kashmir |  |  |  | 898
Madhya Pradesh
4 | Maheshwar (SMHPCL) | Private | Khargone & Khandwa | 10x40 | 400 | Narmada/CIRS | 2023-24 | Works suspended since Nov-11 due to cash flow problem with developer. M.P. Power Management Company Ltd. has terminated the Power Purchase Agreement with SMHPCL on 18.04.2020.
| Sub-total: Madhya Pradesh |  |  |  | 400
Maharashtra
5 | Koyna Left Bank (WRD,MAH) | State | Satara | 2x40 | 80 | Koyna/ Krishna/EFR | 2025-26 | Project stalled since July, 2015. The current expenditure on the project has already reached to almost original administrative approved cost level. Proposal for revival of the project is submitted to the Govt. of Maharashtra.
| Sub-total: Maharashtra |  |  |  | 80
Sikkim
6 | Bhasmey (Gati Infrastructure) | Private | East Sikkim | 2x25.5 | 51 | Rangpo/ Teesta/ Brahmaputra | 2024-25 | Works are stalled since Sept., 2016 due to funds constraints with developer
7 | Rangit-II (Sikkim Hydro) | Private | West Sikkim | 2x33 | 66 | Greater Rangit/ Teesta/ Brahmaputra | 2024-25 | Works are stalled since December, 2017 due to funds constraints with developer. Project is in NCLT since 30.07.2020.
8 | Panan (Himagiri) | Private | North Sikkim | 4x75 | 300 | Rangyongchu/ Teesta/ Brahmaputra | 2025-26 | Issue of construction of bridge on Mantham Lake for accessebility of site is under discussion with the State Govt of Sikkim.
| Sub-total: Sikkim |  |  |  | 417
Uttarakhand
9 | Lata Tapovan (NTPC) | Central | Chamoli | 3x57 | 171 | Dhauliganga /Alaknanada & Ganga | 2025-26 | Infrastructure works almost completed. As per Hon’ble Supreme Court vide its order dated 07.05.2014 stayed the construction of 24 Hydro projects in Uttrakhand including Lata Tapovan HEPP. According all construction activities stopped since 08.05.14. Main works to re-start after clearance from Hon’ble Supreme Court.
10 | Phata Byung (LANCO) | Private | Rudraprayag | 2x38 | 76 | Mandakini/Alaknanda Ganga | 2024-25 | Works stalled since July, 2017 due to Financial crunch with the contractor / developer.The company is undergoing a corporate insolvency resolution process initiated under IBC for resolution and revival of the project since June 2020. Under this process, the resolution professional appointed by the NCLT has initiated the process for inviting prospective investors for the project.
| Sub-total: Uttarakhand |  |  |  | 247
| Total: |  |  |  | 2086
*Subject to re-start of work in immediate future