| Hydro Capacity Addition Programme for 2022-23 (above 25 MW & excluding Projects under Ministry of New & Energy) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sl. No. | Name of Project | State/ Implem. Agency | Unit No. | Capacity (MW) | Date of Commissioning (As per developer) | Optimistic scenario (as assessed by CEA) | Most likely scenario (as assessed by CEA) | Remarks |
|  | Central Sector |  |  |  |  |  |  |  |
| 1 | Naitwar Mori 2x30=60 MW | Uttarakhand/SJVNL | U-1 U-2 | 30 30 | June'22 June' 22 | Sept'22 Oct'22 | Dec'22 Jan'23 | Q-3 Q-4 |
| 2 | Subansiri Lower 8x250= 2000 MW | Arunachal Pradesh/NHPC | U-1 U-2 | 250 250 | Aug'22 Aug'22 | Oct'22 Nov’22 | Jan'23 Feb'23 | Q-4 Q-4 |
| 3 | Parbati St. II 4x200= 800 MW | Himachal Pradesh/NHPC | U-1 U-2 U-3 U-4 | 200 200 200 200 | Mar'23 Mar'23 Mar'23 Mar'23 | Mar'23 Apr’23 Apr’23 Apr’23 | Aug’23 Sept’23 Sept’23 Sept’23 | 2023-24 |
| 4 | Tehri PSS 4x250= 1000 MW | Uttarakhand/THDC | U-1 U-2 | 250 250 | Dec'22 Mar'23 | Dec'22 Mar'23 | Mar'23 June'23 | Q-4 - |
|  |  | Sub- total (Central): |  | 1860 | 1860 | 1260 | 810 |  |
|  | State Sector |  |  |  |  |  |  |  |
| 5 | Vyasi 2x60=120 MW | Uttarakhand/UJVN | U-1 U-2 | 60 60 | Apr'22 Apr'22 | Apr'22 Apr'22 | Apr'22 May'22 | Q-1 Q-1 |
| 6 | Pallivasal 2x30= 60 MW | Kerala/ KSEB Ltd. | U-1 U-2 | 30 30 | Nov'22 Jan'23 | Jan'23 Jan'23 | Mar'23 Mar'23 | Q-4 Q-4 |
| 7 | Thottiyar 1x30 + 1x10= 40 MW | Kerala/ KSEB Ltd. | U-1 U-2 | 30 10 | Jul'22 Nov'22 | Nov'22 Nov'22 | Feb'23 Mar'23 | Q-4 Q-4 |
|  |  | Sub- total (State): |  | 220 | 220 | 220 | 220 |  |
|  | Private Sector |  |  |  |  |  |  |  |
| 8 | Tidong-I 2x50= 100 MW | Himachal Pradesh/M/s Statkraft India Pvt. Ltd. | U-1 U-2 | 50 50 | Oct'22 Oct'22 | Dec'22 Dec'22 | Mar'23 Apr'23 | Q-4 - |
|  |  | Sub- total (Private): |  | 100 | 100 | 100 | 50 |  |
| Total (CS+SS+PS) |  |  |  | 2180 | 2180 MW | 1580 MW | 1080 MW |  |

Quarter-1= 120 MW

Quarter-2= Nil

Quarter-3= 30 MW

Quarter-4= 930 MW