Hydro Capacity Addition Programme for 2024-25

| Sl. No. | Name of Project | State/ Implem. Agency | Unit No. | Capacity (MW) |  | Capacity Addition |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target | Actual | As Programmed/ Anticipated |
|  | Central Sector |  |  |  |  |  |
| 1 | Parbati-II /NHPC (4*200=800 MW) | Himachal Pradesh/NHPC | U-1 U-2 U-3 U-4 | 200 200 200 200 | 0 | Mar'25 Mar'25 Mar'25 Mar'25 |
| 2 | Tehri PSS/THDC (4*250=1000 MW) | Uttarakhand/THDC | U-1 | 250 | 0 | Feb'25 |
|  |  | Sub-total (Central): |  | 1050 | 0 |  |
|  | State Sector |  |  |  |  |  |
| 4 | Pallivasal (2x30= 60 MW) | Kerala/ KSEB Ltd. | U-1 U-2 | 30 30 | 0 | Dec’24 Dec’24 |
| 5 | Uhl-III (3*33.3=100 MW) | Himachal Pradesh/BVPCL | U-1 U-2 U-3 | 33.3 33.3 33.3 | 0 | Dec’24 Dec’24 Dec’24 |
| 6 | Thottiyar (1x30 + 1x10 = 40 MW) | Kerala/ KSEB Ltd. | U-1 U-2 | 10 30 | 10 30 | Commissioned |
|  |  | Sub-total (State): |  | 200 | 40 |  |
|  | Private Sector |  |  |  |  |  |
| 7 | Pinnapuram 4X240+2X120 =1200 MW | Andhrapradesh/M/s Greenko Energies Pvt. Ltd. | U-1 U-2 | 240 240 | 0 | Feb’25 Mar’25 |
|  |  | Sub-total (Private): |  | 480 | 0 |  |
| Total (CS+SS+PS) |  |  |  | 1730 | 40 |  |