## Annex-1A
Annex-1A
List of Hydro Electric Projects (above 25 MW) under active construction
Sl. No. | Name of Scheme | Sector | District | I.C. ( No. X MW.) | Cap. Under Execution(MW) | River/Basin | Type | Date of finish/ commissioning
(Executing Agency)
Andhra Pradesh
1 | Polavaram (APGENCO/ Irrigation Dept., A.P.) | State | East & West Godavari | 12x80 | 960 | Godavari/EFR | Storage | 2024-26 (Mar'26)
2 | Pinnapuram (Greenko AP01 IREP Private Limited) | Private | Kurnool | 4x240 + 2x120 | 1200 | Pennar Basin | PSS | 2024-25 (Mar'25)
| Sub-total: Andhra Pradesh |  |  |  | 2160
Arunachal Pradesh
3 | Subansiri Lower (NHPC) | Central | Lower Subansiri | 8x250 | 2000 | Subansiri/ Brahmaputra | RoR with diurnal storage | 2022-24 (Mar'24)*
| Sub-total: Arunachal Pradesh |  |  |  | 2000
Assam
4 | Lower Kopli (APGCL) | State | Dima Hasao & Karbi Anglong | 2x55+2x2.5+1x5 | 120 | Kopili/ Brahmaputra | RoR | 2024-25 (Jun'24)
| Sub-total: Assam |  |  |  | 120
Himachal Pradesh
5 | Parbati St. II (NHPC) | Central | Kullu | 4x200 | 800 | Parbati/Beas/Indus | RoR | 2023-24 (Sept'23)
6 | Luhri-I (SJVN) | Central | Kullu/Shimla | 2x80+2x25 | 210 | Satluj/Indus | RoR | 2025-26 (Jan'26)
7 | Dhaulasidh (SJVN) | Central | Hamirpur/ Kangra | 2x33 | 66 | Beas | RoR | 2025-26 (Nov'25)
8 | Uhl-III (BVPCL) | State | Mandi | 3x33.33 | 100 | Uhl/Beas/ Indus | RoR | 2023-24 (Dec'23)
9 | Shongtong Karcham (HPPCL) | State | Kinnaur | 3x150 | 450 | Satluj/ Indus | RoR | 2025-26 (Mar'25)
10 | Tidong-I (Statkraft IPL) | Private | Kinnaur | 2x50 | 100 | Tidong/Satluj/Indus | RoR | 2022-24 $$ (Apr'23)
11 | Kutehr (JSW Energy Ltd) | Private | Chamba | 3x80 | 240 | Ravi/ Indus | RoR | 2025-26 (Nov'25)
| Sub-total: Himachal Pradesh |  |  |  | 1966
Jammu & Kashmir
12 | Pakal Dul (CVPPL) | Central | Kishtwar | 4x250 | 1000 | Marusadar/ Chenab / Indus | Storage | 2025-26 (July'25)
13 | Parnai (JKSPDC) | State | Poonch | 3x12.5 | 37.5 | Jhelum/ Indus | RoR | 2023-24 (Dec'23)
14 | Kiru (CVPPL) | Central | Kishtwar | 4x156 | 624 | Chenab/ Indus | RoR | 2024-25 (Aug.'24)
15 | Ratle (RHEPPL / NHPC) | Central | Kishtwar | 4x205 + 1x30 | 850 | Chenab/Indus | RoR with diurnal pondage | 2025-26 (Feb'26)
16 | Kwar (CVPPPL) | Central | Kishtwar | 4x135 | 540 | Chenab | RoR | 2026-27 (Nov'26)
| Sub-total: Jammu & Kashmir |  |  |  | 3051.5
Kerala
17 | Pallivasal (KSEB) | State | Idukki | 2x30 | 60 | Mudirapuzha/ Periyar/ Baypore Periyar/ WFR | RoR | 2022-23 (Mar'23)
18 | Thottiyar (KSEB) | State | Idukki | 1x30+1x10 | 40 | Thottiyar/ Periyar/ / Baypore Periyar/ WFR | RoR | 2022-23 (Mar'23)
| Sub-total: Kerala |  |  |  | 100
Punjab
19 | Shahpurkandi (PSPCL/ Irrigation Deptt., Pb.) | State | Gurdaspur | 3x33+3x33+1x8 | 206 | Ravi/ Indus | RoR | 2024-25 (Aug'24)
| Sub-total: Punjab |  |  |  | 206
Sikkim
20 | Teesta St. VI NHPC | Central | South Sikkim | 4x125 | 500 | Teesta/Brahmaputra | RoR | 2023-24 (Mar'24)
21 | Rangit-IV (NHPC) | Central | West Sikkim | 3x40 | 120 | Rangit/ Teesta/ Brahmaputra | RoR | 2024-25 (May'24)
| Sub-total: Sikkim |  |  |  | 620
Tamil Nadu
22 | Kundah Pumped Storage Phase-I,II&III) | State | Nilgiris | 4x125 | 500 | Kundah/Bhavani/ Cauvery/EFR | PSS | 2023-24 (Mar'24)
| Sub-total: Tamil Nadu |  |  |  | 500
Uttarakhand
23 | Vishnugad Pipalkoti (THDC) | Central | Chamoli | 4x111 | 444 | Alaknanada/Ganga | RoR | 2024-25 (Mar'25)
24 | Naitwar Mori (SJVNL) | Central | Uttarkashi | 2x30 | 60 | Tons/Yamuna/Ganga | RoR with pondage | 2022-23 (Jan'23)
25 | Tapovan Vishnugad (NTPC) | Central | Chamoli | 4x130 | 520 | Dhauliganga / Alaknanada & /Ganga | RoR | 2024-25 (June'24)
26 | Tehri PSS (THDC) | Central | Tehri Garhwal | 4x250 | 1000 | Bhilangna/Bhagirathi/ Ganga | PSS with Pondage | 2022-24 ** (Jun'23)
| Sub-total: Uttarakhand |  |  |  | 2024
West Bengal
27 | Rammam-III (NTPC) | Central | Darjeeling | 3x40 | 120 | Rammam/ Rangit/Teesta Brahmaputra | RoR | 2024-25 (Dec'24)
| Sub-total: West Bengal |  |  |  | 120
| Total: |  |  |  | 12867.5
* 2 units (500 MW) likely during 2022-23 & 6 units (1500 MW) during 2023-24
** 1 unit (250 MW) likely during 2022-23 & 3 units (750 MW) during 2023-24
$$ 1 unit (50 MW) in 2022-23 and 1 unit (50 MW) in 2023-24.