## HEP
Annex-1A
List of Hydro Electric Projects (above 25 MW) -under implementation
Sl. No. | Name of the Project (Executing Agency) | State / UT | District | I.C. ( No. X MW.) | Cap. Under Execution(MW) | River/Basin | Date of finish/ commissioning
Central Sector
NHPC
1 | Subansiri Lower (NHPC) | Arunachal Pradesh/Assam | Lower Subansiri, Ar. Pradesh / Dhemaji, Assam | 7x250 | 1750 | Subansiri/ Brahmaputra | 2025-27 # (Aug'26)
2 | Dibang Multipurpose Project (NHPC) | Arunachal Pradesh | Lower Dibang Valley | 12x240 | 2880 | Dibang/Brahmaputra | 2031-32 (Feb'32)
3 | Teesta St. VI NHPC | Sikkim | South Sikkim | 4x125 | 500 | Teesta/Brahmaputra | 2027-28 (Dec'27)
4 | Rangit-IV (NHPC) | Sikkim | West Sikkim | 3x40 | 120 | Rangit/ Teesta/ Brahmaputra | 2026-27 (Apr'26)
5 | Ratle (RHEPPL / NHPC) | UT of Jammu & Kashmir | Kishtwar | 4x205 + 1x30 | 850 | Chenab/Indus | 2028-29 (Nov'28)
CVPPL
6 | Pakal Dul (CVPPL) | UT of Jammu & Kashmir | Kishtwar | 4x250 | 1000 | Marusadar/ Chenab / Indus | 2026-27 (Dec'26)
7 | Kiru (CVPPL) | UT of Jammu & Kashmir | Kishtwar | 4x156 | 624 | Chenab/ Indus | 2026-27 (Dec'26)
8 | Kwar (CVPPPL) | UT of Jammu & Kashmir | Kishtwar | 4x135 | 540 | Chenab/Indus | 2027-28 (Mar'28)
SJVN
9 | Luhri-I (SJVN) | Himachal Pradesh | Kullu/Shimla | 2x80+2x25 | 210 | Satluj/Indus | 2029-30 (Feb'30)
10 | Dhaulasidh (SJVN) | Himachal Pradesh | Hamirpur/ Kangra | 2x33 | 66 | Beas/Indus | 2026-27 (Mar'27)
11 | Sunni Dam (SJVN) | Himachal Pradesh | Shimla/Mandi | 4x73+1x73+1x17 | 382 | Satluj/Indus | 2029-30 (Dec'29)
THDC
12 | Vishnugad Pipalkoti (THDC) | Uttarakhand | Chamoli | 4x111 | 444 | Alaknanada/Ganga | 2026-27 (Mar'27)
NTPC
13 | Tapovan Vishnugad (NTPC) | Uttarakhand | Chamoli | 4x130 | 520 | Dhauliganga / Alaknanada & /Ganga | 2028-29 (Mar'29)
14 | Rammam-III (NTPC) | West Bengal | Darjeeling | 3x40 | 120 | Rammam/ Rangit/Teesta Brahmaputra | 2028-29 (Mar'29)
NEEPCO
15 | HEO | Arunachal Pradesh | West Siang | 3x80 | 240 | Yarjep River | 2028-29 (Sept'29)
16 | Tato-I | Arunachal Pradesh | Shi-Yomi | 3x62 | 186 | Siyom River | 2028-29 (Sept'29)
Sub-Total: Central Sector |  |  |  |  | 10432
State Sector
APGENCO
17 | Polavaram (APGENCO/ Irrigation Dept., A.P.) | Andhra Pradesh | East & West Godavari | 12x80 | 960 | Godavari/EFR | 2027-28 (Jan'28)
18 | Lower Sileru Extension (APGENCO) | Andhra Pradesh | Alluri Sitharamaraju | 2x115 | 230 | Sileru/Godavari | 2026-27 (Apr'26)
HPPCL
19 | Shongtong Karcham (HPPCL) | Himachal Pradesh | Kinnaur | 3x150 | 450 | Satluj/ Indus | 2028-29 (Sep'28)
20 | Chanju-III (HPPCL) | Himachal Pradesh | Chamba | 3x16 | 48 | Chanju Nallah | 2027-28 (Dec'27)
KSEB
21 | Mankulam (KSEB) | Kerala | Idukki | 2x20 | 40 | Melachery | 2027-28 (Nov'27)
APGCL
22 | Lower Kopli (APGCL) | Assam | Dima Hasao & Karbi Anglong | 2x55+2x2.5+1x5 | 120 | Kopili/Brahmaputra | 2025-27## (Apr'26)
JKSPDC
23 | Parnai (JKSPDC) | UT of Jammu & Kashmir | Poonch | 3x12.5 | 37.5 | Jhelum/ Indus | 2027-28 (Dec'27)
| PSPCL |  | Poonch
24 | Shahpurkandi (PSPCL/ Irrigation Deptt., Pb.) | Punjab | Pathankot | 3x33+3x33+1x8 | 206 | Ravi/ Indus | 2027-28 (May'27)
UJVNL
25 | Lakhwar Multipurpose Project (UJVNL) | Uttarakhand | Dehradun & Tehri Garhwal | 3x100 | 300 | Yamuna | 2031-32 (Dec'31)
Sub-Total: State Sector |  |  |  |  | 2391.5
Private Sector
Statkraft
26 | Tidong-I (Statkraft IPL) | Himachal Pradesh | Kinnaur | 3x50 | 150 | Tidong/Satluj/Indus | 2026-27 (Jul'26)
Sub-Total: Private Sector |  |  |  |  | 150
| Total: |  |  |  | 12973.5
# Unit-2 (250MW) has been commissioned in Dec'25 and remaining 3 units (750 MW) likely during 2025-26, 4 units (1000 MW) likely during 2026-27.
##2 units (110 MW) likely during 2025-26, 3 units (10 MW) likely during 2026-27.
Note:-Presently 26 no. of hydro electric project (above 25 MW) totaling to 12973.50 MW are under construction.

## PSP
Annex-1B
List of Pumped storage Projects (above 25 MW) -under implementation
Sl. No. | Name of the Project (Executing Agency) | State / UT | District | I.C. ( No. X MW.) | Cap. Under Execution(MW) | River/Basin | Date of finish/ commissioning
Central Sector
THDC
1 | Tehri PSS (THDC) | Uttarakhand | Tehri Garhwal | 1x250 | 250 | Bhilangna/Bhagirathi/ Ganga | 2025-26 (Jan'26)*
Sub-Total: Central Sector |  |  |  |  | 250
State Sector
APGENCO
2 | Upper Sileru PSP (APGENCO) | Andhra Pradesh | Alluri Sitharamaraju | 9x150 | 1350 | Sileru/Godavari | 2028-29 (Feb'29)
KPCL
3 | Sharavathy Pumped Storage Project | Karntaka | Upper dam (Shimoga) & Lower dam (Uttara Kannada) | 8x250 | 2000 | Sharavathy/WFR | 2029-30 (Dec'29)
TANGEDCO
4 | Kundah Pumped Storage Phase-I,II&III) | Tamil Nadu | Nilgiris | 4x125 | 500 | Kundah/Bhavani/ Cauvery/EFR (Off Stream) | 2026-27 (Jun'26)
Sub-Total: State Sector |  |  |  |  | 3850
Private Sector
5 | MP30 Gandhi Sagar Pumped Storage Project (Greenko MP01 IREP Private Limited) | Madhya Pradesh | Neemuch | 7x240 + 2x120 | 1920 | Off stream | 2026-27 (Dec'26)
6 | Chitravathi PSP(M/s Adani Renewable Energy Forty-Two Limited) | Andhra Pradesh | Satya Sai | 2x250 | 500 | Chitravathi River (Off Stream) | 2026-27 (Oct'26)
7 | Bhivpuri PSP(M/s Tata Power Company Limited) | Maharashtra | Raigad | 4x200 + 2x100 | 1000 | Off stream | 2028-29 (Oct'28)
8 | Saundatti PSP (M/s Greenko KA01 IREP Private Limited) | Karnataka | Belagavi | 320x4+160x2 | 1600 | Off stream | 2027-28 (Dec' 2027)
9 | Bhavali PSP (M/s JSW Energy PSP Two Limited) | Maharashtra | Nashik & Thane | 5x250+2x125 | 1500 | Dharna, Ulhas (Off Stream) | 2028-29 (Dec' 2028)
10 | Gandikota PSP ( M/s Adani Renewable Energy Fifty-One Limited) | Andhra Pradesh | Kadapa | 4x250 | 1000 | Penna River (Off Stream) | 2028-29 (Mar' 2029)
Sub-Total: Private Sector |  |  |  |  | 7520
Total: |  |  |  |  | 11620
Note:-Presently 10 no. of Pumped Storage projects (above 25 MW) totaling to 11620 MW are under implementation.
*Out of total four units three units of Tehri PSP(750 MW) have been commissioned during June-December,2025