## Annex-1B
List of Hydro Electric Projects (above 25 MW) under implementation
Sl. No. | Name of Scheme | State | District | I.C. ( No. X MW.) | Cap. Under Execution(MW) | River/Basin | Date of finish/ commissioning
(Executing Agency)
Central Sector
1 | Subansiri Lower (NHPC) | Arunachal Pradesh | Lower Subansiri | 8x250 | 2000 | Subansiri/ Brahmaputra | 2022-24 ** (Aug'23)
2 | Parbati St. II (NHPC) | Himachal Pradesh | Kullu | 4x200 | 800 | Parbati/Beas/Indus | 2022-23 (Mar'23)
3 | Luhri-I (SJVN) | Himachal Pradesh | Kullu/Shimla | 2x80+2x25 | 210 | Satluj/Indus | 2025-26 (Jan'26)
4 | Dhaulasidh (SJVN) | Himachal Pradesh | Hamirpur/ Kangra | 2x33 | 66 | Beas | 2025-26 (May'25)
5 | Pakal Dul (CVPPL) | Jammu & Kashmir | Kishtwar | 4x250 | 1000 | Marusadar/ Chenab / Indus | 2025-26 (July'25)
6 | Kiru (CVPPL) | Jammu & Kashmir | Kishtwar | 4x156 | 624 | Chenab/ Indus | 2024-25 (Aug.'24)
7 | Teesta St. VI NHPC | Sikkim | South Sikkim | 4x125 | 500 | Teesta/Brahmaputra | 2023-24 (Mar'24)
8 | Vishnugad Pipalkoti (THDC) | Uttarakhand | Chamoli | 4x111 | 444 | Alaknanada/Ganga | 2024-25 (Jun'24)
9 | Naitwar Mori (SJVNL) | Uttarakhand | Uttarkashi | 2x30 | 60 | Tons/Yamuna/Ganga | 2022-23 (Dec'22)
10 | Tapovan Vishnugad (NTPC) | Uttarakhand | Chamoli | 4x130 | 520 | Dhauliganga / Alaknanada & /Ganga | 2024-25 (Jun'24)
11 | Tehri PSS (THDC) | Uttarakhand | Tehri Garhwal | 4x250 | 1000 | Bhilangna/Bhagirathi/ Ganga | 2022-24*** (Jun'23)
12 | Rammam-III (NTPC) | West Bengal | Darjeeling | 3x40 | 120 | Rammam/ Rangit/Teesta Brahmaputra | 2024-25 (Dec'24)
13 | Rangit-IV (NHPC) | Sikkim | West Sikkim | 3x40 | 120 | Rangit/ Teesta/ Brahmaputra | 2024-25 (May'24)
14 | Ratle (RHEPPL / NHPC) | Jammu & Kashmir | Kishtwar | 4x205 + 1x30 | 850 | Chenab/Indus | 2025-26 (Feb.'26)
15 | Lata Tapovan (NTPC) | Uttarakhand | Chamoli | 3x57 | 171 | Dhauliganga /Alaknanada & Ganga | 2025-26*
Sub-Total: Central Sector |  |  |  |  | 8485
State Sector
16 | Polavaram (APGENCO/ Irrigation Dept., A.P.) | Andhra Pradesh | East & West Godavari | 12x80 | 960 | Godavari/EFR | 2024-26
17 | Lower Kopli (APGCL) | Assam | Dima Hasao & Karbi Anglong | 2x55+2x2.5+1x5 | 120 | Kopili | 2024-25 (Jun'24)
18 | Uhl-III (BVPCL) | Himachal Pradesh | Mandi | 3x33.33 | 100 | Uhl/Beas/ Indus | 2023-24 (Dec'23)
19 | Shongtong Karcham (HPPCL) | Himachal Pradesh | Kinnaur | 3x150 | 450 | Satluj/ Indus | 2024-25 (Mar'25)
20 | Parnai (JKSPDC) | Jammu & Kashmir | Poonch | 3x12.5 | 37.5 | Jhelum/ Indus | 2023-24 (Dec'23)
21 | Pallivasal (KSEB) | Kerala | Idukki | 2x30 | 60 | Mudirapuzha/ Periyar/ Baypore Periyar/ WFR | 2022-23 ## (Sept'22)
22 | Thottiyar (KSEB) | Kerala | Idukki | 1x30+1x10 | 40 | Thottiyar/ Periyar/ / Baypore Periyar/ WFR | 2022-23 ## (Dec'22)
23 | Shahpurkandi (PSPCL/ Irrigation Deptt., Pb.) | Punjab | Gurdaspur | 3x33+3x33+1x8 | 206 | Ravi/ Indus | 2024-25 (Aug'24)
24 | Kundah Pumped Storage Phase-I,II&III) | Tamil Nadu | Nilgiris | 4x125 | 500 | Kundah/Bhavani/ Cauvery/EFR | 2023-24 (Apr'23)
25 | Vyasi (UJVNL) | Uttarakhand | Dehradun | 2x60 | 120 | Yamuna/Ganga | 2021-22 # (Mar'22)
26 | Lower Kalnai (JKSPDC) | Jammu & Kashmir | Kishtwar | 2x24 | 48 | Chenab/ Indus | 2025-26 *
27 | Koyna Left Bank (WRD,MAH) | Maharashtra | Satara | 2x40 | 80 | Koyna/ Krishna/EFR | 2025-26*
Sub-Total: State Sector |  |  |  |  | 2721.5
Private Sector
28 | Bajoli Holi (GMR) | Himachal Pradesh | Chamba | 3x60 | 180 | Ravi/ Indus | 2021-22 (Feb'22)
29 | Tidong-I (Statkraft IPL) | Himachal Pradesh | Kinnaur | 100 | 100 | Tidong/Satluj/Indus | 2022-23 (Oct'22)
30 | Kutehr (JSW Energy Ltd) | Himachal Pradesh | Chamba | 3x80 | 240 | Ravi/ Indus | 2025-26 (Nov'25)
31 | Tangnu Romai (TRPG) | Himachal Pradesh | Shimla | 2x22 | 44 | Pabbar/Tons/ Yamuna/ Ganga | 2024-25 *
32 | Maheshwar (SMHPCL) | Madhya Pradesh | Khargone & Khandwa | 10x40 | 400 | Narmada/CIRS | 2023-24 *
33 | Bhasmey (Gati Infrastructure) | Sikkim | East Sikkim | 2x25.5 | 51 | Rangpo/ Teesta/ Brahmaputra | 2024-25*
34 | Rangit-II (Sikkim Hydro) | Sikkim | West Sikkim | 2x33 | 66 | Greater Rangit/ Teesta/ Brahmaputra | 2024-25 *
35 | Panan (Himagiri) | Sikkim | North Sikkim | 4x75 | 300 | Rangyongchu/ Teesta/ Brahmaputra | 2025-26 *
36 | Phata Byung (LANCO) | Uttarakhand | Rudraprayag | 2x38 | 76 | Mandakini/Alaknanda Ganga | 2024-25*
Sub-Total: Private Sector |  |  |  |  | 1457
| Total: |  |  |  | 12663.5
* The Project is presently stalled.Commissioning is subject to immediate restart of works
** 2 units (500 MW) likely during 2022-23 & 6 units (1500 MW) during 2023-24
*** 2 units (500 MW) likely during 2022-23 & 2 units (500 MW) during 2023-24
#Vyasi (120MW) was not under original Hydro Capacity addition Programme for 2021-22.
## Pallivasal and Thottiyar were under original Hydro Capacity addition Programme for 2021-22 but now slipping to 2022-23.