Hydro Capacity Addition Programme for 2025-26

| Sl. No. | Name of Project | State/ Implem. Agency | Unit No. | Capacity (MW) |  | Capacity Addition |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target | Actual | As Programmed/ Anticipated |
|  | Central Sector |  |  |  |  |  |
| 1 | Parbati-II /NHPC (4*200=800 MW) | Himachal Pradesh/NHPC | U-4 | 200 | 200 | Commissioned on 13.04.2025 |
| 2 | Rangit-IV/NHPC | Sikkim/NHPC | U-1 to 3 | 120 | 0 | Dec'2025 |
| 3 | SUBANSIRI LOWER /NHPC | Arunachal Pradesh/NHPC | U-1 to 5 | 1250 | 0 | Feb'2026 |
| 4 | Tehri PSS/THDC | Uttarakhand/THDC | U-1 to U-4 | 1000 | 500 | Nov’2025 (U-1 & 2 commissioned on 05.06.2025 & 05.07.2025 respectively) |
|  |  | Sub- total (Central): |  | 2570 | 700 |  |
|  | State Sector |  |  |  |  |  |
| 1 | Lower Sileru Extension /APGENCO) | Andhra Pradesh/APGENCO | U-1 to 2 | 230 | 0 | Mar'2026 |
| 2 | Lower Kopili /APGCL | Assam/APGCL | U-1 to 2 | 110 | 0 | Dec'2025 |
| 3 | Kundah Pumped Storage (Phase-I, Phase-II & Phase-III) /TANGEDCO | Tamil Nadu/ TANGEDCO | U-1 to 3 | 375 | 0 | Mar'2026 |
|  |  | Sub- Total (State): |  | 715 | 0 |  |
|  | Private Sector |  |  |  |  |  |
| 1 | Kutehr/JSW | Himachal Pradesh/JSW | U-1 to 3 | 240 | 240 | Commissioned in Aug'2025 |
| 2 | Pinnapuram 6X240+2X120 =1680 MW | Andhra Pradesh/Greenko | U-1 to 8 | 1680 | 1440 | Sept'2025 (U-1 to U-4 and U-6 to U-7 commissioned till Aug’2025) |
|  |  | Sub- Total (Private): |  | 1920 | 1680 |  |
| Total (CS+SS+PS) |  |  |  | 5205 | 2380 |  |