## Annex-1B
List of Hydro Electric Projects(above 25 MW) for which construction is held up (As on 30.06.2022)
Sl. No. | Name of Scheme | Sector | District | I.C. ( No. X MW.) | Cap. Under Execution(MW) | River/Basin | Date of finish/ commissioning* | Present Status/Reasons
(Executing Agency)
Himachal Pradesh
1 | Tangnu Romai (TRPG) | Private | Shimla | 2x22 | 44 | Pabbar/Tons/ Yamuna/ Ganga | 2025-26 | Works are on hold since Aug 2016 due to fund constraints with developer.
| Sub-total: Himachal Pradesh |  |  |  | 44
Jammu & Kashmir
2 | Lower Kalnai (JKSPDC) | State | Kishtwar | 2x24 | 48 | Chenab/ Indus | 2026-27 | Works on all fronts at Dam and Power House site are stalled since the contract has been terminated by JK Govt. order no. 115-PDD of 2019 dated 08.06.2019.The Balance Work stands tendered out by JKSPDC in EPC mode vide E-NIT No 01 on 24-03-2022.
| Sub-total: Jammu & Kashmir |  |  |  | 48
Madhya Pradesh
3 | Maheshwar (SMHPCL) | Private | Khargone & Khandwa | 10x40 | 400 | Narmada/CIRS | 2024-25 | Works suspended since Nov-11 due to cash flow problem with developer. M.P. Power Management Company Ltd. has terminated the Power Purchase Agreement with SMHPCL on 18.04.2020.
| Sub-total: Madhya Pradesh |  |  |  | 400
Maharashtra
4 | Koyna Left Bank (WRD,MAH) | State | Satara | 2x40 | 80 | Koyna/ Krishna/EFR | 2026-27 | Project stalled since July, 2015. The current expenditure on the project has already reached to almost original administrative approved cost level. The preparation of draft of Expression of Interest is in process for completing the balance Civil and Electro- Mechanical works of the project by Govt. of Maharashtra.
| Sub-total: Maharashtra |  |  |  | 80
Sikkim
5 | Bhasmey (Gati Infrastructure) | Private | East Sikkim | 2x25.5 | 51 | Rangpo/ Teesta/ Brahmaputra | 2025-26 | Works are stalled since Sept., 2016 due to funds constraints with developer
6 | Rangit-II (Sikkim Hydro) | Private | West Sikkim | 2x33 | 66 | Greater Rangit/ Teesta/ Brahmaputra | 2025-26 | Works are stalled since December, 2017 due to funds constraints with developer. Project is in NCLT since 30.07.2020.
7 | Panan (Himagiri) | Private | North Sikkim | 4x75 | 300 | Rangyongchu/ Teesta/ Brahmaputra | 2026-27 | Issue of construction of bridge on Mantham Lake for accessebility of site is under discussion with the State Govt of Sikkim.
| Sub-total: Sikkim |  |  |  | 417
Uttarakhand
8 | Lata Tapovan (NTPC) | Central | Chamoli | 3x57 | 171 | Dhauliganga /Alaknanada & Ganga | 2026-27 | Infrastructure works almost completed. As per Hon’ble Supreme Court vide its order dated 07.05.2014 stayed the construction of 24 Hydro projects in Uttrakhand including Lata Tapovan HEPP. According all construction activities stopped since 08.05.14. Main works to re-start after clearance from Hon’ble Supreme Court.
9 | Phata Byung (LANCO) | Private | Rudraprayag | 2x38 | 76 | Mandakini/Alaknanda Ganga | 2025-26 | Works stalled since July, 2017 due to Financial crunch with the contractor / developer.The company is undergoing a corporate insolvency resolution process initiated under IBC for resolution and revival of the project since June 2020. Under this process, the resolution professional appointed by the NCLT has initiated the process for inviting prospective investors for the project.
| Sub-total: Uttarakhand |  |  |  | 247
| Total: |  |  |  | 1236