Hydro Capacity addition Programme for 2021-22

(As on 31.10.2021)

| Sl. No. | Name of the project (Capacity) | Unit Nos. | Cap. (MW) | Capacity Addition as Programmed (Month) | Capacity Addition Actual (Date) | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| A. | State Sector |  |  |  |  |  |
| 1 | Pallivasal KSEB, Kerala 2x30=60 MW | Unit #1 Unit # 2 | 30 30 | December’21 December’21 |  | Likely to slip |
| 2 | Thottiyar KSEB, Kerala 1x30+1x10=40MW | Unit #1 Unit # 2 | 10 30 | December’21 December’21 |  | Likely to slip. |
|  | Sub- total (A): |  | 100 MW |  |  |  |
| B. | Private Sector |  |  |  |  |  |
| 3 | Sorang HSPCL, H.P. 2x50=100 MW | Unit #1 Unit # 2 | 50 50 | June’21 June’21 | 23.09.2021 21.09.2021 | Commissioned Commissioned |
| 4 | Bajoli Holi GMRBHHPPL, H.P. 3x60=180 MW | Unit #1 Unit # 2 Unit # 3 | 60 60 60 | June’21 June’21 June’21 |  |  |
| 5 | Rongnichu MBPCL, Sikkim 2x56.5=113 MW | Unit #1 Unit # 2 | 56.5 56.5 | May’21 May’21 | 25.06.2021 30.06.2021 | Commissioned Commissioned |
|  | Sub- total (B): |  | 393 MW |  |  |  |
|  | Total (A+B) |  | 493 MW |  |  |  |

Note:-

213 MW out of the target of 493 MW commissioned.

Vyasi (120MW) was not under original Hydro Capacity addition Programme for 2021-22.The project is likely to be commissioned by Mar’22.

Hydro Capacity addition Programme for 2021-22

| Sl. No. | Particular (With Address) | Unit Nos. | Cap. (MW) | Capacity addition as programmed |
| --- | --- | --- | --- | --- |
| A. | State Sector |  |  |  |
| 1. | Vyasi* UJVNL Dehradun, Uttarakhand 2x60=120 MW | Unit#1 Unit#2 | 60 60 | Mar,22 Mar,22 |
|  | Sub- total (A): |  | 120 |  |
| B. | Private Sector |  |  |  |
| 2 | Rongnichu 2x56.5= 113 MW Madhya Bharat Power Corporationh. East Sikkim, Sikkim | Unit #1 Unit # 2 | 56.5 56.5 | June,21(Comm.) June,21(Comm.) |
| 3. | Sorang Himachal Sorang Power Kinnaur, H.P. 2x50= 100 MW | Unit #1 Unit # 2 | 50 50 | Sept,21(Comm.) Sept,21(Comm.) |
| 4. | Bajoli Holi GMR Bajoli Holi Hydro Power Pvt. Ltd. Chamba, H.P. 3x60= 180 MW | Unit #1 Unit # 2 Unit # 3 | 60 60 60 | Nov,21 Nov,21 Nov,21 |
|  | Sub- total (B): |  | 393 |  |
|  | Total (A+B) |  | 513 |  |

Note:-

*Vyasi (120MW) was not under original Hydro Capacity addition Programme for 2021-22.

2. Pallivasal and Thottiyar were under original Hydro Capacity addition Programme for 2021-22 have now slipped to 2022-23.