## Sheet1
Annex-1A
List of Hydro Electric Projects (above 25 MW) -under implementation
Sl. No. | Name of the Project (Executing Agency) | State / UT | District | I.C. ( No. X MW.) | Cap. Under Execution(MW) | River/Basin | Date of finish/ commissioning | % Physical Progress
Central Sector
NHPC
1 | Subansiri Lower (NHPC) | Arunachal Pradesh/Assam | Lower Subansiri, Ar. Pradesh / Dhemaji, Assam | 8x250 | 2000 | Subansiri/ Brahmaputra | 2025-27 # (May'26) | 94.69
2 | Parbati St. II (NHPC) | Himachal Pradesh | Kullu | 4x200 | 800 | Parbati/Beas/Indus | 2024-25 (Mar'25) | 98.7
3 | Dibang Multipurpose Project (NHPC) | Arunachal Pradesh | Lower Dibang Valley | 12x240 | 2880 | Dibang/Brahmaputra | 2031-32 (Feb'32) | 13.9
4 | Teesta St. VI NHPC | Sikkim | South Sikkim | 4x125 | 500 | Teesta/Brahmaputra | 2027-28 (Dec'27) | 69.4
5 | Rangit-IV (NHPC) | Sikkim | West Sikkim | 3x40 | 120 | Rangit/ Teesta/ Brahmaputra | 2025-26 (Dec'25) | 83.64
6 | Ratle (RHEPPL / NHPC) | UT of Jammu & Kashmir | Kishtwar | 4x205 + 1x30 | 850 | Chenab/Indus | 2028-29 (Nov'28) | 16.5
CVPPL
7 | Pakal Dul (CVPPL) | UT of Jammu & Kashmir | Kishtwar | 4x250 | 1000 | Marusadar/ Chenab / Indus | 2026-27 (Sept'26) | 64.45
8 | Kiru (CVPPL) | UT of Jammu & Kashmir | Kishtwar | 4x156 | 624 | Chenab/ Indus | 2026-27 (Sept'26) | 51.86
9 | Kwar (CVPPPL) | UT of Jammu & Kashmir | Kishtwar | 4x135 | 540 | Chenab/Indus | 2027-28 (Dec'27) | 27.61
SJVN
10 | Luhri-I (SJVN) | Himachal Pradesh | Kullu/Shimla | 2x80+2x25 | 210 | Satluj/Indus | 2028-29 (Dec'28) | 51
11 | Dhaulasidh (SJVN) | Himachal Pradesh | Hamirpur/ Kangra | 2x33 | 66 | Beas/Indus | 2026-27 (Mar'27) | 63.9
12 | Sunni Dam (SJVN) | Himachal Pradesh | Shimla/Mandi | 4x73+1x73+1x17 | 382 | Satluj/Indus | 2028-29 (Dec'28) | 27.61
THDC
13 | Vishnugad Pipalkoti (THDC) | Uttarakhand | Chamoli | 4x111 | 444 | Alaknanada/Ganga | 2026-27 (Dec'26) | 69
NTPC
14 | Tapovan Vishnugad (NTPC) | Uttarakhand | Chamoli | 4x130 | 520 | Dhauliganga / Alaknanada & /Ganga | 2028-29 (Mar'29) | 72.2
15 | Rammam-III (NTPC) | West Bengal | Darjeeling | 3x40 | 120 | Rammam/ Rangit/Teesta Brahmaputra | 2028-29 (Mar'29) | 44.94
Sub-Total: Central Sector |  |  |  |  | 11056
State Sector
APGENCO
16 | Polavaram (APGENCO/ Irrigation Dept., A.P.) | Andhra Pradesh | East & West Godavari | 12x80 | 960 | Godavari/EFR | 2027-28 (Sep'27) | 31.16
17 | Lower Sileru Extension (APGENCO) | Andhra Pradesh | Alluri Sitharamaraju | 2x115 | 230 | Sileru/Godavari | 2025-26 (Oct'25) | 31
HPPCL
18 | Shongtong Karcham (HPPCL) | Himachal Pradesh | Kinnaur | 3x150 | 450 | Satluj/ Indus | 2028-29 (Sep'28) | 54.23
19 | Chanju-III (HPPCL) | Himachal Pradesh | Chamba | 3x16 | 48 | Chanju Nallah | 2027-28 (Jul'27) | 17.07
KSEB
20 | Pallivasal (KSEB) | Kerala | Idukki | 2x30 | 60 | Mudirapuzha/ Periyar/ Baypore Periyar/ WFR | 2024-25 (Mar'25) | 99.75
21 | Mankulam (KSEB) | Kerala | Idukki | 2x20 | 40 | Melachery | 2026-27 (Dec'26) | 13.05
APGCL
22 | Lower Kopli (APGCL) | Assam | Dima Hasao & Karbi Anglong | 2x55+2x2.5+1x5 | 120 | Kopili/Brahmaputra | 2025-26 (Sep'25) | 86.11
BVPCL
23 | Uhl-III (BVPCL) | Himachal Pradesh | Mandi | 3x33.33 | 100 | Uhl/Beas/ Indus | 2024-25 (Mar'25) | 100
JKSPDC
24 | Parnai (JKSPDC) | UT of Jammu & Kashmir | Poonch | 3x12.5 | 37.5 | Jhelum/ Indus | 2027-28 (Jul'27) | 63
PSPCL
25 | Shahpurkandi (PSPCL/ Irrigation Deptt., Pb.) | Punjab | Pathankot | 3x33+3x33+1x8 | 206 | Ravi/ Indus | 2026-27 (Apr'26) | 80.9
UJVNL
26 | Lakhwar Multipurpose Project (UJVNL) | Uttarakhand | Dehradun & Tehri Garhwal | 3x100 | 300 | Yamuna | 2028-29 (Oct'28) | 10.65
Sub-Total: State Sector |  |  |  |  | 2551.5
Private Sector
Statkraft
27 | Tidong-I (Statkraft IPL) | Himachal Pradesh | Kinnaur | 3x50 | 150 | Tidong/Satluj/Indus | 2026-27 (Jun'26) | 99.55
JSW
28 | Kutehr (JSW Energy Ltd) | Himachal Pradesh | Chamba | 3x80 | 240 | Ravi/ Indus | 2025-26 (Jul'25) | 90.86
Sub-Total: Private Sector |  |  |  |  | 390
| Total: |  |  |  | 13997.5
# 5 units (1250 MW) likely during 2025-26, 3 units (750 MW) likely during 2026-27.
Note:-Presently 28 no. of hydro electric project (above 25 MW) totaling to 13997.5 MW are under construction.

## Sheet2
Annex-IB
List of Pumped storage Projects (above 25 MW) -under implementation
Sl. No. | Name of the Project (Executing Agency) | State / UT | District | I.C. ( No. X MW.) | Cap. Under Execution(MW) | River/Basin | Date of finish/ commissioning | % Physical Progress
Central Sector
THDC
1 | Tehri PSS (THDC) | Uttarakhand | Tehri Garhwal | 4x250 | 1000 | Bhilangna/Bhagirathi/ Ganga | 2025-26 (Oct'25) | 97.9
Sub-Total: Central Sector |  |  |  |  | 1000
State Sector
APGENCO
2 | Upper Sileru PSP (APGENCO) | Andhra Pradesh | Alluri Sitharamaraju | 9x150 | 1350 | Sileru/Godavari | 2028-29 (Feb'29) | Project is in the initial stage of construction
KPCL
3 | Sharavathy Pumped Storage Project | Karntaka | Upper dam (Shimoga) & Lower dam (Uttara Kannada) | 8x250 | 2000 | Sharavathy/WFR | 2029-30 (Dec'29) | Project is in the initial stage of construction
TANGEDCO
4 | Kundah Pumped Storage Phase-I,II&III) | Tamil Nadu | Nilgiris | 4x125 | 500 | Kundah/Bhavani/ Cauvery/EFR | 2025-26 (Dec'25) | 80.5
Sub-Total: State Sector |  |  |  |  | 3850
Private Sector
Greenko
5 | Pinnapuram (Greenko AP01 IREP Private Limited) | Andhra Pradesh | Kurnool | 4x240+2x120 | 1200 | Off stream | 2025-26 (July'25) | 94.8
6 | MP30 Gandhi Sagar Pumped Storage Project (Greenko MP01 IREP Private Limited) | Madhya Pradesh | Neemuch | 7x240 + 2x120 | 1920 | Off stream | 2028-29 (Jun'28) | Project is in the initial stage of construction
Sub-Total: Private Sector |  |  |  |  | 3120
| Total: |  |  |  | 7970