Hydro Capacity Addition Programme for 2023-24

(Above 25 MW & excluding Projects under Ministry of New & Energy)

| Sl. No. | Name of Project | State/ Implem. Agency | Unit No. | Capacity (MW) | Date of Commissioning (As per developer) | Most likely scenario |
| --- | --- | --- | --- | --- | --- | --- |
|  | Central Sector |  |  |  |  |  |
| 1 | Naitwar Mori | Uttarakhand /SJVNL | U-1 | 30 | May'23 | Nov'23 |
|  | 2x30=60 MW |  | U-2 | 30 | May' 23 | Nov'23 |
| 2 | Subansiri Lower 8x250= 2000 MW | Arunachal Pradesh/NHPC | U-1 U-2 U-3 U-4 | 250 250 250 250 | June'23 July'23 Aug'23 Dec'23 | Mar’23 Mar’23 2024-25 2024-25 |
| 3 | Tehri PSS 4x250= 1000 MW | Uttarakhand/THDC | U-1 U-2 U-3 U-4 | 250 250 250 250 | Aug'23 Sept'23 Nov.'23 Dec.'23 | 2024-25 2024-25 2024-25 2024-25 |
|  |  | Sub- total (Central): |  | 2860 | 2860 | 560 |
|  | State Sector |  |  |  |  |  |
| 5 | Pallivasal | Kerala/ KSEB Ltd. | U-1 | 30 | June'23 | Mar'24 |
|  | 2x30= 60 MW |  | U-2 | 30 | June'23 | Mar'24 |
| 6 | Thottiyar | Kerala/ KSEB Ltd. | U-1 | 30 | Jul'23 | Mar'24 |
|  | 1x30 + 1x10= 40 MW |  | U-2 | 10 | Nov'23 | Mar'24 |
|  |  | Sub- total (State): |  | 100 | 100 | 100 |
|  | Private Sector |  |  |  |  |  |
| 7 | Tidong-I 3x50= 150 MW | Himachal Pradesh/ M/s Statkraft India Pvt. Ltd. | U-1 U-2 U-3 | 50 50 50 | June'24 June'24 June'24 | Not likely during 2023-24 |
| 8 | Pinnapuram 4X240+2X120=1200 MW | M/s Greenko Energies Pvt. Ltd. | U-1 U-2 U-3 U-4 U-5 U-6 | 240 240 240 240 120 120 | Jan’24 Jan’24 Feb’24 Feb’24 Mar’24 Mar’24 | 2024-25 2024-25 2024-25 2024-25 2024-25 2024-25 |
|  |  | Sub- total (Private): |  | 1350 | 1350 | Nil |
| Total (CS+SS+PS) |  |  |  | 4310 | 4310 | 660 |