Hydro Capacity Addition Programme for 2023-24

| Sl. No. | Name of Project | State/ Implem. Agency | Unit No. | Capacity (MW) |  | Capacity Addition |  | Reason for slippage |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target | Actual | As Programmed | Actual(A)/ Anticipated |  |
|  | Central Sector |  |  |  |  |  |  |  |
| 1 | Naitwar Mori | Uttarakhand /SJVNL | U-1 | 30 | 30 | June’23 | 24.11.2023 |  |
|  | 2x30=60 MW |  | U-2 | 30 | 30 | July'23 | 04.12.2023 |  |
| 2 | Subansiri Lower 8x250= 2000 MW | Arunachal Pradesh/NHPC | U-1 U-2 U-3 U-4 | 250 250 250 250 |  | Aug’23 Sept’23 Jan’24 Mar’24 | Slipping to 2025-26 Slipping to 2025-26 Slipping to 2025-26 Slipping to 2025-26 | - Diversion tunnel-1 collapsed. - Slope stability of left bank. - Erection of balance 6 nos. of radial gates, DT plugging |
| 3 | Tehri PSS 4x250= 1000 MW | Uttarakhand/THDC | U-1 U-2 U-3 U-4 | 250 250 250 250 |  | Oct'23 Nov'23 Jan’24 Feb’24 | Slipping to 2024-25 Slipping to 2024-25 Slipping to 2024-25 Slipping to 2024-25 | - River joining works are critical - Permission from Up irrigation Dept from 1-30th Jun,2024 - Plug breaking of HRT |
|  |  | Sub- total (Central): |  | 2060 |  | 2060 | 60 |  |
|  | State Sector |  |  |  |  |  |  |  |
| 4 | Pallivasal | Kerala/ KSEB Ltd. | U-1 | 30 |  | Dec'23 | Mar'24 |  |
|  | 2x30= 60 MW |  | U-2 | 30 |  | Dec'23 | Mar'24 |  |
| 5 | Thottiyar | Kerala/ KSEB Ltd. | U-1 | 30 |  | Dec'23 | Mar'24 |  |
|  | 1x30 + 1x10= 40 MW |  | U-2 | 10 |  | Mar'24 | Mar'24 |  |
|  |  | Sub- total (State): |  | 100 |  | 100 | 100 |  |
|  | Private Sector |  |  |  |  |  |  |  |
| 6 | Pinnapuram 4X240+2X120=1200 MW | M/s Greenko Energies Pvt. Ltd. | U-1 U-2 U-3 | 240 240 240 |  | Jan’24 Feb’24 Mar’24 | Slipping to 2024-25 Slipping to 2024-25 Slipping to 2024-25 | Slow progress of works |
|  |  | Sub- total (Private): |  | 720 |  | 720 | - |  |
| Total (CS+SS+PS) |  |  |  | 2880 | 60 | 2880 | 160 |  |