## Annex-1B
(As on 31.07.2023)
List of Hydro Electric Projects (above 25 MW) under implementation -Sector-wise
Sl. No. | Name of the Project (Executing Agency) | State / UT | District | I.C. ( No. X MW.) | Cap. Under Execution(MW) | River/Basin | Date of finish/ commissioning | % Physical Progress
Central Sector
1 | Subansiri Lower (NHPC) | Arunachal Pradesh/Assam | Lower Subansiri, Ar. Pradesh / Dhemaji, Assam | 8x250 | 2000 | Subansiri/ Brahmaputra | 2023-25 (Dec'24) # | 89.67
2 | Parbati St. II (NHPC) | Himachal Pradesh | Kullu | 4x200 | 800 | Parbati/Beas/Indus | 2024-25 (Jun'24) | 95.4
3 | Luhri-I (SJVN) | Himachal Pradesh | Kullu/Shimla | 2x80+2x25 | 210 | Satluj/Indus | 2025-26 (Jan'26) | 51
4 | Dhaulasidh (SJVN) | Himachal Pradesh | Hamirpur/ Kangra | 2x33 | 66 | Beas/Indus | 2025-26 (Nov'25) | 59
5 | Pakal Dul (CVPPL) | UT of Jammu & Kashmir | Kishtwar | 4x250 | 1000 | Marusadar/ Chenab / Indus | 2026-27 (Sept'26) | 35.58
6 | Kiru (CVPPL) | UT of Jammu & Kashmir | Kishtwar | 4x156 | 624 | Chenab/ Indus | 2025-26 (Mar'26) | 20
7 | Teesta St. VI NHPC | Sikkim | South Sikkim | 4x125 | 500 | Teesta/Brahmaputra | 2026-27 (Aug'26) | 51.85
8 | Vishnugad Pipalkoti (THDC) | Uttarakhand | Chamoli | 4x111 | 444 | Alaknanada/Ganga | 2026-27 (Jun'26) | 65
9 | Naitwar Mori (SJVNL) | Uttarakhand | Uttarkashi | 2x30 | 60 | Tons/Yamuna/Ganga | 2023-24 (Oct'23) | 96
10 | Tapovan Vishnugad (NTPC) | Uttarakhand | Chamoli | 4x130 | 520 | Dhauliganga / Alaknanada & /Ganga | 2025-26 (Dec'25) | 75
11 | Tehri PSS (THDC) | Uttarakhand | Tehri Garhwal | 4x250 | 1000 | Bhilangna/Bhagirathi/ Ganga | 2023-25## (Jun'24) | 94.7
12 | Rammam-III (NTPC) | West Bengal | Darjeeling | 3x40 | 120 | Rammam/ Rangit/Teesta Brahmaputra | 2026-27 (Sept'26) | 44
13 | Rangit-IV (NHPC) | Sikkim | West Sikkim | 3x40 | 120 | Rangit/ Teesta/ Brahmaputra | 2024-25 (Aug'24) | 66.01
14 | Ratle (RHEPPL / NHPC) | UT of Jammu & Kashmir | Kishtwar | 4x205 + 1x30 | 850 | Chenab/Indus | 2026-27 (May'26) | 8.64
15 | Kwar (CVPPPL) | UT of Jammu & Kashmir | Kishtwar | 4x135 | 540 | Chenab/Indus | 2026-27 (Nov'26) | 5.89
16 | Sunni Dam (SJVN) | Himachal Pradesh | Shimla/Mandi | 4x73+1x73+1x17 | 382 | Satluj/Indus | 2027-28 (Mar'28) | 19
17 | Dibang Multipurpose Project (NHPC) | Arunachal Pradesh | Lower Dibang Valley | 12x240 | 2880 | Dibang/Brahmaputra | 2031-32 (Feb'32) | Initial stage of construction
18* | Lata Tapovan (NTPC) | Uttarakhand | Chamoli | 3x57 | 171 | Dhauliganga /Alaknanada & Ganga | * | 4
Sub-Total: Central Sector |  |  |  |  | 12287
State Sector
19 | Polavaram (APGENCO/ Irrigation Dept., A.P.) | Andhra Pradesh | East & West Godavari | 12x80 | 960 | Godavari/EFR | 2024-26 (Mar'26)### | 14
20 | Lower Kopli (APGCL) | Assam | Dima Hasao & Karbi Anglong | 2x55+2x2.5+1x5 | 120 | Kopili/Brahmaputra | 2024-25 (Mar'25) | 50
21 | Uhl-III (BVPCL) | Himachal Pradesh | Mandi | 3x33.33 | 100 | Uhl/Beas/ Indus | 2024-25 (Dec'24) | 95
22 | Shongtong Karcham (HPPCL) | Himachal Pradesh | Kinnaur | 3x150 | 450 | Satluj/ Indus | 2026-27 (Nov'26) | 47
23 | Parnai (JKSPDC) | UT of Jammu & Kashmir | Poonch | 3x12.5 | 37.5 | Jhelum/ Indus | 2024-25 (Mar'25) | 54
24 | Pallivasal (KSEB) | Kerala | Idukki | 2x30 | 60 | Mudirapuzha/ Periyar/ Baypore Periyar/ WFR | 2023-24 (Mar'24) | 92.65
25 | Thottiyar (KSEB) | Kerala | Idukki | 1x30+1x10 | 40 | Thottiyar/ Periyar/ / Baypore Periyar/ WFR | 2023-24 (Mar'24) | 95
26 | Shahpurkandi (PSPCL/ Irrigation Deptt., Pb.) | Punjab | Pathankot | 3x33+3x33+1x8 | 206 | Ravi/ Indus | 2025-26 (Oct'25) | 63
27 | Kundah Pumped Storage Phase-I,II&III) | Tamil Nadu | Nilgiris | 4x125 | 500 | Kundah/Bhavani/ Cauvery/EFR | 2024-25 (Oct'24) | 64
28 | Chanju-III (HPPCL) | Himachal Pradesh | Chamba | 3x16 | 48 | Chanju Nallah | 2027-28 (Jun'27) | Initial stage of construction
29 | Mankulam (KSEB) | Kerala | Idukki | 2x20 | 40 | Melachery | 2026-27 (May'26) | 5
30 | Lakhwar Multipurpose Project (UJVNL) | Uttarakhand | Dehradun & Tehri Garhwal | 3x100 | 300 | Yamuna | 2028-29 (Oct'28) | 8
31 | Lower Sileru Extension (APGENCO) | Andhra Pradesh | Alluri Sitharamaraju | 2x115 | 230 | Sileru/Godavari | 2025-26 (Mar'26) | Initial stage of construction
32* | Lower Kalnai (JKSPDC) | UT of Jammu & Kashmir | Kishtwar | 2x24 | 48 | Chenab/ Indus | * | 10
33* | Koyna Left Bank (WRD,MAH) | Maharashtra | Satara | 2x40 | 80 | Koyna/ Krishna/EFR | * | 5
Sub-Total: State Sector |  |  |  |  | 3219.5
Private Sector
34 | Tidong-I (Statkraft IPL) | Himachal Pradesh | Kinnaur | 3x50 | 150 | Tidong/Satluj/Indus | 2024-25 (Jun'24) | 91
35 | Kutehr (JSW Energy Ltd) | Himachal Pradesh | Chamba | 3x80 | 240 | Ravi/ Indus | 2025-26 (Nov'25) | 68
36 | Pinnapuram (Greenko AP01 IREP Private Limited) | Andhra Pradesh | Kurnool | 4x240+2x120 | 1200 | Pennar Basin | 2023-25#### (Jun'24) | 60
37* | Tangnu Romai (TRPG) | Himachal Pradesh | Shimla | 2x22 | 44 | Pabbar/Tons/ Yamuna/ Ganga | * | 20
38* | Maheshwar (SMHPCL) | Madhya Pradesh | Khargone & Khandwa | 10x40 | 400 | Narmada/CIRS | * | 85
39* | Bhasmey (Gati Infrastructure) | Sikkim | East Sikkim | 2x25.5 | 51 | Rangpo/ Teesta/ Brahmaputra | * | 30
40* | Rangit-II (Sikkim Hydro) | Sikkim | West Sikkim | 2x33 | 66 | Greater Rangit/ Teesta/ Brahmaputra | * | 20
41* | Panan (Himagiri) | Sikkim | North Sikkim | 4x75 | 300 | Rangyongchu/ Teesta/ Brahmaputra | * | Nil
42* | Phata Byung (LANCO) | Uttarakhand | Rudraprayag | 2x38 | 76 | Mandakini/Alaknanda Ganga | * | 74
Sub-Total: Private Sector |  |  |  |  | 2527
| Total: |  |  |  | 18033.5
# 2 units (500 MW) likely during 2023-24 and remaining 6 units (1500 MW) during 2024-25
## 2 units (500 MW) likely during 2023-24 and remaining 2 units (500 MW) during 2024-25
### 4 units (320 MW) likely during 2024-25 & 8 units (640 MW) during 2025-26
#### 2 units (480 MW) likely during 2023-24 and remaining 4 units (720 MW) during 2024-25
* The Project is presently stalled.Commissioning is subject to restart of works
Note:-Presently 42 no. of hydro electric project (above 25 MW) totaling to 18033.5 MW are under implementation . Out of these,33 no. HEPs totaling to 16797.5 MW are under active construction and 9 no. HEPs totaling to 1236 MW are presently stalled.