## Annex-IB
Annex-I
List of Hydro Electric Projects (above 25 MW) held-up
Sl. No. | Name of Scheme | Sector | District | I.C. ( No. X MW.) | Cap. Under Execution(MW) | River/Basin | Type | % Physical progress | Present Status& steps taken to restart works
(Executing Agency)
Himachal Pradesh
1 | Tangnu Romai (TRPG) | Private | Shimla | 2x22 | 44 | Pabbar/Tons/ Yamuna/ Ganga | RoR | 20% | Works on hold since Aug 2016 due to fund constraints with the developer .Project is likely to be commissioned 4 years after restart of works.
| Sub-total: Himachal Pradesh |  |  |  | 44
UT of Jammu & Kashmir
2 | Lower Kalnai (JKSPDC) | State | Kishtwar | 2x24 | 48 | Chenab/ Indus | RoR | 10% | Works on all fronts at Dam and Power House site are stalled since the contract has been terminated by JK Govt. order no. 115-PDD of 2019 dated 08.06.2019. The Balance Work stands tendered out by JKSPDC in EPC mode vide E-NIT on 24.03.2022.Project is likely to be commissioned 4 years after restart of works.
| Sub-total: UT of Jammu & Kashmir |  |  |  | 48
Madhya Pradesh
3 | Maheshwar (SMHPCL) | Private | Khargone & Khandwa | 10x40 | 400 | Narmada/CIRS | RoR | 85% | Works suspended since Nov-11 due to cash flow problem with developer. M.P. Power Management Company Ltd. has terminated the Power Purchase Agreement with SMHPCL on 18.04.2020. The application of PFC has been admitted in NCLT on 27.09.2022 under IBC.Project is likely to be commissioned 2 years after restart of works.
| Sub-total: Madhya Pradesh |  |  |  | 400
Maharashtra
4 | Koyna Left Bank (WRD,MAH) | State | Satara | 2x40 | 80 | Koyna/ Krishna/EFR | PSS | 5% | Project stalled since July, 2015. The current expenditure on the project has already reached to almost original administrative approved cost level. The proposal for execution with various options (By WRD/ Through BOT/ By MSPGCL in collaboration with WRD) is under process.Project is likely to be commissioned 4 years after restart of works
| Sub-total: Maharashtra |  |  |  | 80
Sikkim
5 | Bhasmey (Gati Infrastructure) | Private | East Sikkim | 2x25.5 | 51 | Rangpo/ Teesta/ Brahmaputra | RoR | 30% | Works stalled since Sept., 2016 due to funds constraints.Project is likely to be commissioned 4 years after restart of works.
6 | Rangit-II (Sikkim Hydro) | Private | West Sikkim | 2x33 | 66 | Greater Rangit/ Teesta/ Brahmaputra | RoR | 20% | Works stalled since Dec., 2017 due to funds constraints. Project is in NCLT since 30.07.2020.Project is likely to be commissioned 3 years after restart of works
7 | Panan (Himagiri) | Private | North Sikkim | 4x75 | 300 | Rangyongchu/ Teesta/ Brahmaputra | RoR | Nil | The permanent bridge over Mantam Lake for accessibility to Dam site is being constructed by SPWD and likely to be completed by Mid of the year 2023.Project is likely to be commissioned 5 years after restart of works.
| Sub-total: Sikkim |  |  |  | 417
Uttarakhand
8 | Lata Tapovan (NTPC) | Central | Chamoli | 3x57 | 171 | Dhauliganga /Alaknanada & Ganga | RoR | 3.8% | Infrastructure works almost completed. Hon’ble SC stayed construction of 24 HE projects in Uttarakhand including Lata Tapovan. Project is likely to be commissioned 4 years after restart of works.
9 | Phata Byung (LANCO) | Private | Rudraprayag | 2x38 | 76 | Mandakini/Alaknanda Ganga | RoR | 74% | Works stalled since July, 2017 due to Financial crunch. Company undergoing corporate insolvency resolution process initiated under IBC for resolution and revival of the project since June 2020. Resolution Plan is under approval by the National Company Law Tribunal.Project is likely to be commissioned 2 years after restart of works.
| Sub-total: Uttarakhand |  |  |  | 247
| Total: |  |  |  | 1236