## Annex-II
Annex-II
List of Hydro Electric Projects (above 25 MW) held-up
Sl. No. | Name of Scheme | Sector | State /District | I.C. ( No. X MW.) | Cap. Under Execution(MW) | River/Basin | Type | % Physical progress | Present Status | Measures to be taken to restart works
(Executing Agency)
A | Projects held up due to sub-judice matters
1 | Lata Tapovan (NTPC) | Central | Uttarakhand/Chamoli | 3x57 | 171 | Dhauliganga /Alaknanada & Ganga | RoR | 3.8% | Matter is sub-judice. Infrastructure works almost completed. Hon’ble SC stayed construction of 24 HE projects in Uttarakhand including Lata Tapovan. Project is likely to be commissioned 4 years after restart of works. Work stalled since May, 2014. | Project is stalled due to Sub-Judice matter
2 | Maheshwar (SMHPCL) | Private | Madhya Pradesh /Khargone & Khandwa | 10x40 | 400 | Narmada/CIRS | RoR | 85% | Matter is sub-judice. Works suspended since Nov-11 due to cash flow problem with developer. M.P. Power Management Company Ltd. has terminated the Power Purchase Agreement with SMHPCL on 18.04.2020. The application of PFC has been admitted in NCLT on 27.09.2022 under IBC. CIRP has been put on hold by NCLT vide order dated 17.03.2023 in an application filed by Entegra Ltd. PFC has filed an Appeal before the NCLAT against the NCLT Order dated 17.03.2023 for recommencement of CIRP.Project is likely to be commissioned 2 years after restart of works. | Project in NCLT.The resolution process may be expedited
3 | Bhasmey (Gati Infrastructure) Pvt. Ltd. | Private | Sikkim /East Sikkim | 2x25.5 | 51 | Rangpo/ Teesta/ Brahmaputra | RoR | 30% | Matter is sub-judice. The Court appointed Resolution Professional for Bhasmey HEP stated that works stalled since Sept., 2016. CIRP has been initiated against Gati infra and NCLT has appointed Resolution Professional .The Resolution Professional has received 4 Resolution Plan in the matter of Gati Infrastructure Bhasmey Power Private Limited and are pending for approval from the Committee of Creditors. Project is likely to be commissioned 4 years after restart of works. | CPSUs and other financially sound companies having expertise in hydro electric project construction may come forward and take these projects either through NCLT route or negotiation with the developers (outside NCLT).
|  |  | Sub total |  | 622
B | Projects held up due to funds constraints
1 | Tangnu Romai Power Generation Power Ltd. | Private | Himachal Pradesh /Shimla | 2x22 | 44 | Pabbar/Tons/ Yamuna/ Ganga | RoR | 20% | Works on hold since Aug 2016. Funds constraints with the developer. Project is likely to be commissioned 4 years after restart of works. | CPSUs and other financially sound companies having expertise in hydro electric project construction may come forward and take these projects either through NCLT route or negotiation with the developers (outside NCLT).
2 | Rangit-II (Sikkim Hydro) Power Ventures Ltd. | Private | Sikkim /West Sikkim | 2x33 | 66 | Greater Rangit/ Teesta/ Brahmaputra | RoR | 20% | Works stalled since Dec., 2017. Funds constraints with the developer. Project is likely to be commissioned 3 years after restart of works | CPSUs and other financially sound companies having expertise in hydro electric project construction may come forward and take these projects either through NCLT route or negotiation with the developers (outside NCLT).
|  |  | Sub total |  | 110
C | Project held up due to accessibility to project site
1 | Panan (Himagiri) Hydro Energy Private Ltd. | Private | Sikkim /North Sikkim | 4x75 | 300 | Rangyongchu/ Teesta/ Brahmaputra | RoR | Nil | Accessibility to Project site. The permanent bridge over Mantam Lake for accessibility to Dam site is being constructed by Roads and Bridges Department Govt. of Sikkim which is likely to be completed by 2026. The Financial Institutes are awaiting for completion of bridge, thereafter the process of financing the project can start. .Project is likely to be commissioned 5 years after restart of works. | The bridge over Mantham Lake for accessibility to Dam site may be expedited by the State Govt
|  |  | Sub total |  | 300
D | Projects held up due to other issue
1 | Lower Kalnai (JKSPDC) | State | U.T of Jammu & Kashmir /Kishtwar | 2x24 | 48 | Chenab/ Indus | RoR | 10% | Works on all fronts at Dam and Power House site are stalled since the contract has been terminated by JK Govt. order no. 115-PDD of 2019 dated 08.06.2019. The Balance Work stands tendered out by JKSPDC in EPC mode vide E-NIT on 24.03.2022. Technical evaluation of the bids is completed and financial bids are slated to be opened .Project is likely to be commissioned 4 years after restart of works. | In Lower Kalnai HEP, bidding process for balance works needs to be expedited by the State Govt.
2 | Koyna Left Bank (WRD,MAH) | State | Maharashtra /Satara | 2x40 | 80 | Koyna/ Krishna/EFR | PSS | 5% | Project stalled since July, 2015. The current expenditure on the project has already reached to almost original administrative approved cost level. The proposal for execution with various options (By WRD/ Through BOT/ By MSPGCL in collaboration with WRD) is under process.Project is likely to be commissioned 4 years after restart of works | The proposal for execution with various options (By WRD/ Through BOT/ By MSPGCL in collaboration with WRD) is under process which may be expedited
3 | Phata Byung (LANCO) | Private | Uttrakhand /Rudraprayag | 2x38 | 76 | Mandakini/Alaknanda Ganga | RoR | 74% | Works stalled since July, 2017 due to Financial crunch.The project stands alloted to M/s Statkraft IH through NCLT on 23.03.2023. The revival of Environmental clearance is under process. Project is likely to be commissioned 2 years after restart of works. | The project stands alloted to M/s Statkraft IH through NCLT on 23.03.2023.Likely to re-start shortly.
|  |  | Sub total |  | 204
| Total: |  |  |  | 1236