Status of Under Execution Hydro Electric Projects (above 25 MW) in the Country

| Sl. No. | Name of Project Executing Agency Date of CEA clearance / Approval Capacity (MW) Broad Features Cost (original/latest) In Rs. Crores. | State Comm. Sch. (original/ Now Ant. | Broad Present Status / Critical Area | Remarks/ Critical issues |
| --- | --- | --- | --- | --- |
| A | Central Sector |  |  |  |
| 1 | Parbati-II NHPC 11.09.2002 # 4x200 = 800 MW Broad Features : Dam – 85m High, 109. m long at top, concrete gravity type HRT- 6m x 31.23km P.House- Surface 23.5mx 39.7mx 123m. Turbine- Pelton Swyd.- 13.8/400 kV Cost: Original:3919.59 Latest: 9897.59 (04/20 PL) Contractors Civil : Gammon / Valecha HM : Om Metals E&M : BHEL | H.P. 2009-10 2024-25 (Sep’24) | CIVIL WORKS Dam & Intake Structure (83.7m high and 3.7m D-shaped intake structure) - Completed. Head Race Tunnel (6m diameter, 31.545Km long) – HRT excavation: Completed (Except 40.72 m rock plug at D/s of Adit-IV) • Overt lining: 28910 m (91.60%) lining out of 31561 m completed. Total 144m Lining progress achieved during Dec-2023. Power House (23.5m x 39.7m x 123m size): Completed. Nallah Works -Completed ELECTROMECHANICAL WORKS: All units synchronized with grid HYDROMECHANICAL WORKS: All the major HM works completed. | -Slow progress of HRT excavation due to geological constraints. -Heavy rainfall since Jul,2023 which has cut off the approach to working fronts in HRT. |
| 2 | ## TapovanVishnugad NTPC 11.08.2004/Nov, 2006 4x130 = 520 MW Broad Features : Barrage–5 bays of 12m HRT- 5.4m x 11.97km P.House- underground Turbine- V.Pelton Cost: Original: 2978.48 Latest: 7700 (4th qtr 22) Agencies: - Barrage Package: M/s RPPL - HRT Package: M/s HCC - Powerhouse and Penstock Package: Ms Patel Engineering Ltd. - HM Package: Om Metals - E&M Package: BHEL - Switchyard Package: M/s GE T&D India Ltd. - GT Package: ABB Ltd. | # Uttarakhand 2012-13 2028-29 (Dec’28) | Barrage: Excavation Completed and Concreting almost completed. HRT& Adits: Muck removal works have been completed through all the faces of HRT till Nov,2022. Lastly, Face#2 of HRT cleared in Nov,2022 Desilting Chamber: Concreting under progress. Gate erection completed. TRT, Pressure shaft, Surge shaft completed. E&M works: More than 80% Supply is completed. 2 units are boxed-up and the erection of 3rd unit is 80% complete. The erection agency of M/s BHEL has been demobilized. Hydro-Mechanical works: a. Damage assessment is completed, repair methodology and required supplies has been chalked out. b. Rate finalization for restoration works &BOI’s are under process c. Supplies for Radial Gate & other components and start of balance works is being taken-up with agency in parallel to rate finalization. Muck removal (Flash flood occured on 07 Feb 2021) from all faces almost completed except at SFT. Automatic Flood Warning System has been commenced. HRT Intake Adit Portal Approach Road restored | - Work on the project stopped since 05.01.2023 by the district administration due to subsidence in Joshimath area. Hon’ble High Court allowed for some essential works vide order dated 23.05.2023 |
| 3 | Tehri PSS, THDC, 18.7.06 Nov-11 (Revised CCEA) 4x250=1000 MW Broad Features : Surge Shaft: U/s – 2 nos. D/s – 2 nos Power House: U/G TRT: 2, Dia 9m and Lenghth 1070m & 1160m Turbine: VF reversible pump turbine Cost: Original: 1657.60 Latest:6439.60 ( Oct-22PL) Contractors ## Turnkey : Alstom, France/ HCC | # Uttara khand 2010-11 2024-25 (Oct’24) | - Works already executed with Tehri Stage-I before award of EPC contract:Main Dam, 2 Headrace Tunnels, Transformer Hall, Main Cable Gallery of PSP. Works being executed under EPC Contract: Electro-mechanical Works: Unit-1: Pre-commissioning activities underway after successful boxing-up. Unit synchronization targeted by 15.03.2024. Unit-2: Boxing up successfully completed on 26.12.2023. Unit synchronization targeted by 31.03.2024. Unit-3: Following the lowering of the Stator and Runner, turbine shaft free completed on 31.10.23. Rotor is targeted to lower by Jan’2024. Unit synchronization targeted by 31.05.2024. Unit-4: Runner has been lowered in generator pit on 22.12.2023. Stator & Rotor assembly is also in progress in service bay. Unit synchronization targeted by 30.06.2024. Civil & Hydro-mechanical Works Upstream Surge Shaft- 1 & 2 (145 m each): Lining of USSS-1 required for commissioning of first two units is near completion and lining of USSS-2 is progressing well and likely to be completed by May’24. Down Stream Surge Shaft – 1 & 2 (70.5 m each): Shaft lining and grouting completed. Erection of fixed wheel gate is scheduled to be completed by mid of Jan’24. Tail Race Tunnels- 1 & 2 (2406 m): TRT-01 Concrete lining competed and TRT-02 lining will be completed by Jan’24. Outlet works including gate lowering: Concreting work is in advance stage. TRT Gate lowering is targeted by end of Jan’24. Dismantling the flood protection wall and accomplish river joining works: All the works in respect of 1st and 2nd Units are targeted for completion by Jan’24 except river joining works. However, as per the discussion with UPID officials and subsequent communication received; the shutdown of Tehri HPP and Koteshwar HEP to complete the river joining works may only be available from 15th May’24/ 01st Jun’24 to 30th Jun’24. In such case, commissioning of 1st Unit can be achieved by 31st Jul’24 and rest three units in a gap of one month each by Oct’24. |  |
| 4 | Lata Tapovan, NTPC Aug-2012 3x57= 171 MW Broad Features : Barrage–14 bays of 11m each HRT- 7.51 Km, 4.7m dia P.House- underground Turbine- V.Francis Cost: Original: 1527.00 Latest: 1801.07 Contractors Civil & HM : L&T ## E&M : BHEL | # Uttara khand 2017-18 2028-29 (Subject to re-start of works) | Infrastructure works are almost completed. Main works to re-start after clearances from Hon‘ble Supreme Court. EPC contract for Civil & HM works awarded to M/s L&T on 17-08-2012. E&M package awarded to M/s BHEL on 07.12.12. MoWR vide letter dated 24.01.2019 to MoEF has communicated that only 7 out of 51 Hydro Projects which are under various stages of construction in Uttarakhand has been recommended for implementation. LataTapovan project is not included in the 7 recommended projects. - Barrage (29 m high)-Not started yet. - Desilting chamber (135 m L x 33m W x 17.5 m H)--Not started yet. - HRT (4.7 m diameter, 7.51 km long)-Not started yet. - Surge Shaft (7 m diameter 144.8 m height)-Not started yet. - Pressure Shaft (3no. 2.0 m diameter 297 m long)-Not started yet. - Power House (85mx 17mx 40.5m)-Not started yet. On 08.07.2020, Director /Conservator forest NDNP, submitted report to Chief Conservator forest Dehradun for LTHEPP mentioning that as per revised notification, project is out of ESZ boundaries. Project is likely to be commissioned 4 years after restart of works. | Construction work stopped vide Hon’ble Supreme Court order dated 7.5.14. Since then, various hearings had been held but the matter is yet to be concluded. Last hearing was held on 22.08.2022, wherein Hon’ble Supreme Court issued the order for listing the matter on 11.10.2022. Matter is likely to be listed on 17.01.2024. Meanwhile, M/s L&T have raised claims of nearly Rs 336 Cr for disruption to Civil & HM Package awarded to them. The dispute pertaining to the claim was under arbitration. Award for the same has been passed by Ld. Arbitral Tribunal on 20.05.2022. The award has been challenged by both parties in the Hon’ble High Court of Delhi. Next hearing listed on 12.03.2024. The contract of EM package, which was awarded to BHEL has been fore-closed on 28.07.2021. Matter is sub-judice. Infrastructure works almost completed. Hon’ble SC stayed construction of 24 HE projects in Uttarakhand including Lata Tapovan. Project is likely to be commissioned 4 years after restart of works. Work stalled since May, 2014. |
| 5 | Vishnugad Pipakoti THDC 21.08. 2008 4x111= 444 MW Broad Features : Dam – 65m High, 89.3m long, concrete gravity HRT- 13.4 Km, 8.8m dia Horse shoe shape P. House-Underground 127mx 20.3mx 50m Turbine- Francis SWYD- 13.8/420 kV Cost:Original: 2491.58 Latest:3860.35 (02/2019 PL) Contractors Civil &HM : HCC ## E&M : BHEL | # Uttara khand 2013-14 # 2026-27 # (Jun’26) | Civil & HM Works: River Diversion has been completed. Construction of U/S Coffer Dam has been completed. Dam excavation: Around 78% completed. Concreting is targeted to start by mid of Jan’24. Frequent resistance from local villagers is being faced for dumping. De-silting Chambers: 95.60% excavation and 54.70% lining work completed in all 3 DCs. Balance work is scheduled to be completed by Feb’25. HRT by DBM (Total 1.5 kms): 100% excavation completed. Kerb concreting and overt lining completed in the length of 572 m and 427 m respectively. HRT by TBM (12 kms): 400 m HRT has been constructed. Machine Hall: In Service Bay, after completion of crane beam by mid of Jan-24, EoT erection is targeted to be completed by end of Feb-24. In Unit area, benching is in progress and Unit-1 pit excavation is targeted by Mar’24. Transformer Hall: Excavation has been completed and support measures are in progress. TRT: Around 57% heading excavation has been completed. TRT outlet area: Slope stabilization work has been completed. Electro - Mechanical Works: 48% supply of equipment/ material has been completed. | -Financial crunch with the civil contractor -Intermittent stoppage of works after the Joshimath subsidence issue Jan’23 |
| 6 | ## Subansiri Lower NHPC 09.09.2003 8x250= 2000 MW (1000 MW in 12th Plan) Broad Features : Dam –116m High, concrete gravity HRT- 8 x 9.5m x 1145m Power House- Surface Turbine- Francis SWYD- 16/400 kV Cost: Original: 6285.33 Latest:19992.43 (04/17 PL) Contractors Civil : BGS-SGS-Soma JV HM : Texmaco E&M : Alstom | Arunachal Pradesh Assam 2009-11 2025-26 # (Oct’25) | ➢ Dam (116m high and 284m long):- Cumulative concreting of 99.84 percent achieved. ➢ Power House (285m x 61m x 64m size):- cumulative qty. achieved 95.77 percent. ➢ E&M Works- unit-1 boxed up and unit-2 boxing is in advanced stage (expected by Dec’23) ➢ HM Works: Testing and commissioning of all 08 nos. Intake Service Gates have been completed. Fabrication of ferrule and erection work of Penstock Liner is in progress (96.45 percent completed). | Radial Gates erection and Diversion Tunnel plugging are critical activities. |
| 7 | Teesta-VI NHPC 08.3.2019 4x125= 500 MW Broad Features: Barrage: 26.5m high HRT- 2nos,27.52km long Pressure shaft: 4nos. 5.4m dia. 151m to 198m length, TRT: 4nos 247m each length, 7.5x7.0m D-shapped. PH- Under ground Turbine- Francis Cost: Original: 3283.08 Latest : 5748.04 (07/2018 PL) Contractors Civil : JAL & Gammon ## E&M : Alstom | Sikkim 2012-13 2026-27 (Aug’26) | - Civil works: Barrage (31.5 high and 105 m long) Excavation: 7.81 lac cum (98%) out of 8.07 lac cum completed. Concreting: 2.64 lac cum (77%) out of 3.44 lac cum completed. HRT (9.8m diameter) Heading excavation of (16.99) km (61.72%) executed out of total 27.52 km, benching excavation of (5.55) km (20.16%), Overt Lining of (4.18) km (15.18%), Invert lining of (1.65) km (6%) has been completed. Desilting Basin Surface Excavation of approx. 2.53 lac cum (65%) executed out of 3.88 lac cum, concreting of 0.95 lac cum (56%) executed out of 1.71 lac cum. Surge Shaft/Surge Gallery: Excavation 98 % & concreting 61% completed. Pressure Shaft (2 nos. steel lined 5.4 internal dia.): Excavation 97 % & Backfill concrete 59% completed. Power House (142m x 18.5m x 52.44m size): Excavation 97 %, concreting 81 % (total qty revised) completed. Downstream Surge Chamber: Excavation of Adit has been completed; however concrete lining is still to be taken up. Tail Race Tunnel: Excavation 86%, concrete lining 100 % completed. (B) HM works are in progress (59.92%). (C) E & M works are in progress (61.94%). | Poor geology in HRT. |
| 8 | Rammam-III NTPC Hydro Ltd. 10.09.14 3x40 = 120 MW Broad Features : Run of the River Scheme Cost :Original: 1381.84 Latest : 1592.34 Contractors - Barrage and Part HRT Package: M/s Simplex Infrastructures Ltd & M/s Apex-Encon Project Pvt Ltd (JV))- - Power-House and Part HRT Package: M/s SEW Infra Ltd. – EM Package: M/S BHEL- | West Bengal 2019-20 2026-27 (Sep’26) | - Barrage (27m height and 122.5 m length): - River diversion completed. Excavation of 151061 cum (95%) (out of 1,59,000 cum) and concreting of 38949 cum(32%) (out of 1, 22,750 cum) have been completed. - De-silting chamber (U/G, 2 nos. each of 140 m length x 7.5 m width x 12.55 m depth):- Excavation & lining of both De-silting chamber completed, - SFT excavation: - Out of 360m of SFT, 78m ( 22%) has been completed. - HRT (3.5 m diameter, 8.2 km long): - As of now, 2700 m (32.85%) HRT have been excavated. - Adit-2 excavation: 645m/800m (82%) have been done. Adit-1 completed. - Intake tunnel, Branch tunnel and Adit-1 to GOC –DC: - excavation completed. - Surge Shaft (14.50 m diameter 53.75 m height): - Surge Shaft excavation & Orifice slab casting is completed. Lining is in progress. - Pressure Shaft/Penstock ( 1591m long): –Pressure shaft excavation completed. - Powerhouse (73.50m x 22.40 m x 41.60 m): - Out of 1,56,099 cum of excavation, 1,53,417 cum (98%) has been excavated. Concreting 39.5% completed. - EM Works: -Tower, Beam, AC kiosk, Bus stringing, Equipment structure and main equipment installation completed. Earth mat laying work is under progress completion. - Switchyard: -Civil works completed & handed over to EM agency and under progress. TRC (657m): - Excavation & Concreting completed. | - Signing of PPA/ATS: - Clearance for signing of PPA by West Bengal Govt. awaited. - Power Evacuation Line: Power Evacuation line/ ATS also not getting finalized due to pending decision for PPA. - Heavy flood hit the Barrage area on 18.06.2023 and upstream of Barrage and equipment including access road were washed away/damaged Poor financial condition of existing vendors- Financial Assistance/ Support is being provided by NTPC |
| 9 | Pakal Dul CVPPL 03.10.2006 4x250 = 1000 MW Broad Features : Dam – 167m High, Width-305m), CFRD, HRT- 2 nos. 7.2m dia 1000m long S.Shaft-16m dia 200m Height P.House- Underground (157mx20.20mx49m) TRT- 5.5m dia, 125m long. Cost: Original:8112.12 Latest: 8112.12 Contractors Civil : Afcons – JAL – JV L&T,JAL HM: PES E&M : Voith Hydro Ltd | J&K 2020-21 2026-27 (Sept’26) | Civil Works: - Dam Package (CFRD 167m high and 305m width)- LoA issued to M/s Jaiprakash Associates on 21.6.2018 at a cost of Rs.2853 crores. Construction activities at the site are in progress. Access adit to HRT-1 & 2 have been completed of a total length of 1797.5 m and 1841.5m respectively. Diversion Tunnel (1 no, diameter 11 m, length 851 m).): Works of Diversion Tunnel completed. River Diversion achieved on 01.11.2021 and the same was e-inaugurated by Hon'ble Minister of Power & NRE in presence of senior officers from GoI, GoJK, NHPC and CVPPPL. Construction of upstream and downstream coffer dam is in progress. - HRT-TBM Package (HRT 2Nos., 7.2m dia, 9.6 km long each (7.3 Km through TBM))- All 97 nos. consignments of TBM-1 and 95 nos. consignment of TBM-2 have also been reached at site. Excavation of Adit-1 including false portal of Cumulative length of 104m completed on 31.05.2023. Excavation of Adit-2 of 126m has completed on 19.10.2023.. Tunnel Boring Machine-1 for construction of Head Race Tunnel-1 has been launched successfully on 25.07.2023 and Excavation started from 29.07.23 & Cumulative progress of Adit-1 by TBM-01 is 384.69 m out of 494m . TBM-02 (Askini) assembly started on dated 01.04.2023& 55% completed and it is anticipated to be launched in March’2024. - Power House Civil Works ( PH Cavern 166m (L) x 20.2 m(W) x 50.5 m(H))- Construction activities are in progress. Construction of Power House Cavern, MIV cavern Transformer Hall cavern, Valve House, Adit to Pressure Shafts, Surge shaft, TRT and part-HRTs are in progress. - E&M Works - Detailed Engineering of E&M equipment’s including submission/checking of drawings, layout plan and equipment manufacturing/supply/inspection is in progress. Installation of MIV Crane Embedments in MIV Service bay has been completed. Installation of GT rails and embedments in service bay, Connecting Tunnel and Transformer Cavern upto GT-4 (Grid-9) has been completed. Erection of MIV EOT Crane, Erection of Draft Tube of Unit-1 & Unit -2, Erection of draft tube of Unit#3, Earthmat erection in U#4 have been completed. Erection of Spiral Casing of Unit#1 and Unit#2 is in progress with the lowering of Stayring in Unit#1 & 2 in respective pits. | - HRT & Dam works are critical. |
| 10 | Kiru CVPPL 13.06.2016 4x156=624 MW Broad Features : Dam – 135m High, Width-193m), Concrete gravity, Penstock 4nos., 5.5m dia. P.House- Underground (182mx23.6mx51.2m) TRT- 4 nos., 7.0m dia, 165 to 190m long. Cost: Original:4287.59 Latest: 4287.59 Contractors Civil : Patel Engg. HM: PES Engineers E&M : Andritz Hydro | J&K 2023-24 2025-26 (Mar’26) | Civil works - Construction of Coffer Dam, PH Cavern, TH Cavern, Adit to Pressure Shaft top & bottom is in progress. Activity for filling of material for construction of u/s and D/s Coffer Dam has been completed on 08.05.2022. Dam abutment stripping and dam excavation below river bed is in progress. Dam concreting has been started on 05.05.2022 and is in progress. Diversion Tunnel (1 no, diameter 9 m, length 666 m): River Diversion achieved on 31.12.2021. HM Works: Detailed Design Engineering/ manufacturing & supply of HM components is in progress. Power House Civil Works (182m (L)x 23.6m(W) x 51.2m(H))– Power House Pilot Excavation (182m) completed on 31.03.22. Benching in progress. | - The project is in initial stage of construction. |
| 11 | Ratle Ratle Hydro Electric Project Pvt. Ltd. / NHPC 19.12.2012 4x205+1x30= 850 MW Broad Features : Dam Height-133m Length-194.8m Spillway-Radia Gate-(5) Size-10.75x1420 m Diversion Tunnel:2 Nos., Circular (Right back) Pressure Tunnel:11m dia each. Pressure Shaft : 6.6 m each steel lined. P.House-Underground Turbine- Francis Average Gross Head-100.39m Addl. Unit(30MW) Housed in Main P.H. Cavity) Rated Head-98.9m Cost : Original: Rs 5281.94 Crore Latest Rs. 5281.94 Crore Contractors Civil & HM : GVK E&M : Alstom | J&K 2017-18 2026-27 (May’26) | • Improvement / Construction of Roads: - Completed. • Excavation of Diversion Tunnels / MAT: In progress. Excavation in Power House (78%), Power House Cavern (80%), Dam abutment excavation (62%) Tail Race Tunnel (TRT) Excavation (18%) Achieved. |  |

| 12 | Rangit-IV Jal Power corp. Ltd. 06.07.2007 3x40= 120 MW Broad Features: Dam: Concrte 44m high .HRT : D- 6.4m L- 6.5km Power House : Surface Turbine: Francis Cost: Original:726.17 Latest : 938.29 (10/19 PL) Contractors Civil : Ritwik (27.08.2021) HM : PES (28.06.2021) E&M : Andritz (08.07.2021) | Sikkim 2011-12 2025-26 (May’25) | CIVIL WORKS: Dam (44 m high and 135.35 m long) - Excavation 95.27% completed. Concreting 83.26% completed. Removal/ clearance of material deposited due to flooding in working area. 1.09 lac cum (54.69%) out of 2.0 lac cum completed. HRT (6.4 m diameter) - Heading excavation of approx. 5.69 km (87.73%) executed out of total 6.48 km, benching excavation of approx. 5.18 km (79.85%), Overt lining of 1115.50 m (17.19%) has been completed. Desilting Chamber (3 nos. each of 120 m length x 13m width x 15 m depth) - 3187 m (94.86%) excavation out of 3360 m is completed. 2558 m (76.14%) concreting out of 3360 m is completed. . Surge Shaft (1 nos., 18 M dia., 56 M height): Excavation 100% completed, concreting 82.2% completed. Pressure Shaft (1 no. 5.5m dia., 236m length) : Excavation 100.00 % completed Surface Power House (75.3m (L) x 20.20m (W) x 41.35 m (H): Excavation 96.88% completed & Concreting 0.313 lac cum (89.68%) out of 0.35 lac (revised qty.) cum completed. ELECROMECHANICAL WORKS: In progress (47.51%). Hydro Mechanical works For Execution of balance works, HM package LOT-II awarded on 28.06.2021. 34.40 % of HM Packages achieved | -Slow progress of works on account of Covid-19 associated lockdowns and restrictions. -Poor geology in HRT. -Methane in HRT |
| --- | --- | --- | --- | --- |
| 13 | Luhri Stage-1 SJVN Ltd. 01.05.2018 2x80+2x25=210 MW Broad Features: Dam: 86 m high HRT: 9m dia 38 km length Power House:Underground Turbine: Francis Cost: Original -1810.56(05/2020) Contractor : Civil: Luhri Hydro Power Consortium dt. 24.11.2020 E&M works: Voith Hydro dt. 16.7.2021 Transmission line from Switchyard to Polling station: M/s Kalpatru Power dt. 6.7.2022 | Himachal Pradesh 2025-26 2025-26 (Jan’26) | Investment approval accorded on 20.11.2020. Civil & Hydro-mechanical Works awarded on 24.11.2020. Electro-mechanical package awarded on 16.07.2021. Dam works: Dam excavation: In progress and cumulative 6,27,673 cum (75%) out of 8,37,912 cum Completed. Dam concreating: Started on 10.04.2023 and 3,421 cum out of 4,33,790 cum completed. Work hampered in monsoon due to overtopping of coffer dam and accumulation of silt. Power house: Excavation: In progress and cumulative 4,40669 cum (88%) out of 4,99,615 cum completed. Service way: Concreting of Columns and Beams completed on 10.11.2023. Roof work is in progress. Tail Race Channel: - In progress and cumulative 4,73,809 cum (74%) out of 6,40,220 cum completed. E&M Works: Design/drawings of DT liner, Spiral Case, pit liner, generator foundation, runner assembly and generator stator frame & core assembly have been approved. Draft tube liners for unit-1 (Main) and unit-3 & 4 (Auxiliary) were received at the site. Inspection of DT liner for Unit-2 completed on 02.11.2023. Manufacturing of the spiral case & EOT crane is in progress. |  |
| 14 | Dhaulasidh Hydro Electric Project SJVN Ltd (2x33 MW = 66 MW) Cost: Original: Rs. 687.97 Cr Civil & HM works: M/s Rithwik Projects Pvt. Ltd. dt. 6.5.2021 EM works: M/s Voith Hydro dt. 19.1.2022 | Himachal Pradesh 2025-26 2025-26 # (Nov ’25) | Investment approval accorded on 1.10.2020. River Diversion achieved on 15.02.2022. Coffer dam: D/s Coffer dam: Completed on 11.04.2022. U/s Coffer dam: Completed on 05.07.2022. Dam works: Left Bank Stripping: Completed on 14.06.2022.Right Bank Stripping: Completed on 28.03.2023.River Bed Excavation: Completed on 20.03.2023.Dam Concreting: In progress and 32,659 cum out of 3,11,450 cum completed. Tail Race Channel: Excavation completed on 28.03.2023. Power House works: Excavation up to unit pit: Completed on 20.12.2022.Concreting: In progress and 1581 cum out of 32,225 cum completed. EM Works: 1. EM Package: Design & engineering of EM components is in progress. Draft tube liners for both main units were received at the site. Fabrication of spiral cases and Stator frames for the Generator are in progress. 2. EOT crane: Crane fabricated and inspection completed on 26.10.2023. | Works hampered in monsoon due to flash flood. |
| 15 | Kwar Hydro Electric Project, CVPPPL (4x135 MW = 540 MW) Cost: Original: Rs. 4526.12 Cr Civil works: M/s Patel Engg. Limited dtd. 11.05.2022 | UT of J&K 2026-27 (Nov’26) | Mobilization in progress. DT outlet portal development & DT inlet portal development have been completed & further work of tunnel excavation work from DT outlet side and DT inlet side, Excavation of MAT portal & Dam excavation (stripping of dam abutments) are under progress. DT Overt Concrete Lining- 686 m progress out of cumulative 701m has been made till date. DT Invert Concrete Lining- 207m progress out of 701m has been made till date Dam Stripping excavation- 101070 cum progress out of cumulative 220000 cum has been made till date. Adit to TRT- 249 m progress out of cumulative 550m has been achieved till date MAT Excavation- 504m progress out of cumulative 609 m has been made till date. CVT Excavation- cumulative 273 m completed on 31.08.2023. Surge Gallery- 326m progress out of cumulative 766m has been made till date. GIS Cavern Excavation (Pilot at crown)- 65 m progress out of cumulative 65 m has been made till date. | The works have recently been awarded. |
| 16 | Sunni Dam SJVN 4x73+1x73+1x17=382 MW Cost: Original: Rs. 2614.51 crs (05/21) Civil & HM works: M/s Rithwik Projects Pvt. Ltd. dt. 14.1.2023 EM works: Yet to be awarded | Himachal Pradesh 2027-28 2027-28 (Mar’28) | Investment approval accorded on 4.1.2023 Major Civil Work and HM works awarded on 14.01.2023. - Heading of Diversion Tunnel: 476m (93%) out of 510m completed. Benching under progress. - Stripping for dam left abutments started and 20020 cum out of 1,21,130 cum completed. - Suspension bridge (110m span) completed. Road from Dam Top to DT Inlet Portal under progress. Approach roads to project components under progress. Construction power: Construction power for initial requirement provided to Contractor. For peak requirement, work of construction of 22 kV line from HPSEB substation at Gumma to dam site through HPSEBL is in progress. |  |
| 17 | Dibang HEP, NHPC (12x240=2880MW) Cost: Rs. 31876.39 Cr Infrastructure Works: M/s L&T dated 27.02.2023 | Arunachal Pradesh 2031-32 (Feb’32) | The works have recently been awarded. |  |

| B | ## State Sector |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 18 | ## Parnai JKSPDC 21.10.2013 3x12.5= 37.5 MW Broad Features: Barrage: 107m Long, 11.7m High HRT: D Shape, 9236m long, 3.2m dia Surge Shaft: 3.2m Dia Power House- Surface- 60x12x28 Cost: Original: 640.86 Latest 640.86 Contractors Civil : Patel & Alstom E&M : Andritz | UT of J&K 2017-18 2025-26 (Dec,25) |  |  | The implementation of the project has been undertaken by awarding the EPC contract in favour of M/s. Patel Engg. Ltd. in 2013. - Barrage (107m long, 11.7m high and 7m wide concrete structure):- Barrage works nearing completion. Laying of deck completed in spillway portion. The deck slab in under sluice portion shall be started after diversion of water on spillway side. Progress is slow by the Contractor. - HRT (D-shaped, 3.2m diameter, 9.156km long):- 6494 RM out of 9236 m excavation completed. 774 m out of 9236 m lining completed. - Surge Shaft ( 3.2m dia):- - Pressure shaft (1 no., 2m dia, 1733m long):- Excavation 20791.50 cum out of total 34560 cum completed. 2002.25 cum out of 7497 cum concreting has been completed. - Power House (Surface 60x12x28m):-Excavation 62081.72 cum out of total 65000 cum completed. | - Slow progress of works - Contractual Issues. |
| 19 | ## Lower Kalnai JKSPDC 16.08.2013 2x24= 48 MW Broad Features: Dam: 110m Span, 49m High HRT: D Shape, 3960m long, 4m dia Surge Shaft: 14m Dia Power House- 55x23.45x32.4 Cost: Original: 576.87 Latest 576.87 Contractors Civil : Coastal E&M : GE | UT of J&K 2017-18 (Commissioning Subject to re-start of works) |  |  | EPC contract awarded to M/s. CPL in Sept., 2013. Diversion tunnel has been completed and river diversion made on 30.11.2016. Work on coffer dams has been started Dam:- Excavation work completed for right abutment of the dam bridge. Excavation of left abutment completed upto 50%. HRT:-Adit excavation is in progress. . 'Works on all fronts at Dam and Power House site are stalled since 24.01.2018 due to payment dispute with subcontractors and due to non-settlement of extension of time of the contract by the JKSPDC .The contract with M/s. Coastal Projects Ltd. has been terminated and The Balance Work stands tendered out by JKSPDC in EPC mode vide E-NIT No 01 on 24-03-2022. | - Works on all fronts at Dam and Power House site are stalled since the contract has been terminated by JK Govt. order no. 115-PDD of 2019 dated 08.06.2019. The Balance Work stands tendered out by JKSPDC in EPC mode vide E-NIT on 24.03.2022. Technical evaluation of the bids is completed and financial bids are slated to be opened .Project is likely to be commissioned 4 years after restart of works. |
| 20 | ## Shahpurkandi Irrigation Deptt. &PSPCL 04.05.2011 3x33+3x33+1x8=206 MW Cost: Original: 1835.50 Latest 2368.55 (Power Component) Contractors Civil & HM for Main Dam with two Head Regulators : Soma – BUREYA JV Power Houses : M/s OMIL JV E&M : BHEL | Punjab 2015-16 2025-26 (Oct’25) |  | Main Dam: Overall 95% work of Main Dam portion has been completed. Hydel Channel: Almost 95% works has been completed. Power House: Excavation completed. Concreting started and 28% completed. E&M: Initial stage of procurement of equipment. Draft tube liner works for two units completed. |  | Delay in E&M works is critical for schedule commissioning. |
| 21 | ## Uhl-III Beas Valley Power Corporation Ltd. (HPSEB) 19.09.02 / (TEC -2x50 MW) 3x33.3 =100 MW (Revised vide HPSEB letter dt. 19.01.07. Broad Features: HRT-4.15m x 8.47 km S.Shaft- 13m x 68.8m Penstock- 3.4m x 1851.946 m (main) P.House- Surface Turbine- V. Francis Cost: Original: 431.56 Latest:1281.52 Contractors Civil : Continental / Abir HM : PES E&M : BHEL | # H.P. 2006-07 2024-25 (Dec’24) |  | All works completed in July, 2018. During Hydro Static pressure Test (HST) of Penstock, some leakage was observed. Repair of penstock & HST completed by March, 2020. On 17.05.2020 after Trial run of Unit-1, during synchronisation to grid transmission load rejection was done but the penstock ruptured along penstock ferrule # 345 which is about 110m upstream of surface power house. The restoration of the Penstock works awarded to M/S P&R Infraprojects Pvt Ltd on November 06, 2021. The work of dismantling of ruptured penstock almost completed and design of penstock rehabilitation work has been approved by GM (D). plates is under transportation stage. Fabrication of Steel Ferrules and erection is under process. |  |  |
| 22 | ## Shongtong Karcham H.P. Power Corpn. Ltd. Clearance: 16.08.2012 3x150= 450 MW Broad Features: Intake Tunnel: 4 Nos. Horse shoe 6.4m dia 192 to 280m length HRT- Circular, 10.5m dia, 8096m long. Power House- Under ground Turbine- VF. Switchyard: 400 Kv. Cost: Original: 2807.83 Latest:2807.83 Contractors Civil & HM : Patel E&M : Andritz | # H.P. 2016-17 2026-27 (Nov’26) |  |  | - Barrage (95.40m long at top):-Downstream Coffer Dam completed. Upstream Coffer Dam 84% completed. - Barrage Work:- 53% of excavation completed - Power Intake:- 29.79% Excavation completed. - Desilting chamber (4 nos. each of 260 m length x 17m width x 22.80 m depth):-Excavation of Desilting chambers 74% completed. - Silt Flushing Tunnel (SFT):-Excavation of SFT 41% completed. - HRT (10.5m diameter, 7.7125 km long):-Heading excavation 97% completed. Benching excavation 69% completed. - Surge Shaft (30.6m diameter 98.5m height):-Excavation-81.67%completed - Pressure Shaft (3nos. 5.0m diameter, Length I&III = 230m, II = 220m):-Excavation of PAC 100% completed. - Power House (131.15m (L) x 23m (W) x 44.29m (H)):-100% excavation of Powerhouse Cavern, 100% excavation of Transformer hall completed. 2nd EOT Crane in machine hall installed. Installation of draft tube in Unit-I completed. - TRT( including adit, Main TRT, Unit TRTs & manifold): Excavation 73.19% completed. - E&M Works:-Supply 63.9% completed. Erection yet to start. Overall E&M works 57.51% completed - Draft Tube:-50.83% excavation completed | Dam is critical due to change in design and approval of same. |
| 23 | Koyna Left Bank PSS WRD, Mah. 20.02.2004 2x40 = 80 MW Broad Features: Water from the existing ShivajiSagar Lake (Koyna reservoir) is to be utilized for generation. Intake Tunnel: Dia – 7.20 M Length – 235.5 M (including Lake tap) HRT: Dia – 7.20 M Length – 80 M Penstock – 2 nos ,Dia – 2.9M Length – 10 M each P.House – Underground Turbine – Reversible Cost: Original: 245.02 Latest:1403.77 Contractors Civil &HM : BT Patil – Malaxmi JV / Patel E&M : LitostrojSlovania&Koncar, Croatia | Maharashtra 2014-15 2027-28 (Subject to re-start of works) |  | Civil Works: Excavation of intake structure 4781 cum out of 14105 cum and lining 2485 cum out of 3381 cum completed. Excavation of Switchyard completed. Excavation of Approach tunnel & Ventilation tunnel is in progress. Tail surge shaft :Excavation in soft strata completed. Excavation for inclined / vertical / lateral shafts in hard rock 6448 / 9223 cum completed. TRT : 364 / 24003 cum excavation completed. Machine Hall : Underground Excavation is under progress. 31500 cum excavation out of 55050 cum completed. E&M works: The contract for details engineering manufacturing supply, supervision erection, testing and commissioning of pump turbine, generator motor and associated equipment is signed with M/s IVRCL Ltd., Pune on 16.12.2010. Further TG set has been ordered as under: Turbine/Pump: M/s Litosroj Power, Slovenia (European Union) Generator/Motor: M/s Koncar Power, Plant & Electric Traction Engineering, Croatia (European Union). EOT Crane :- Works awarded to M/s Pedvak Cranes Private Limited Hyderabad on 12.04.2013. Tail surge shaft: Excavation for inclined/vertical/lateral shafts in hard rock 6448 cum out of 9223 completed. Excavation in soft strata completed. |  | Project stalled since July, 2015. The current expenditure on the project has already reached to almost original administrative approved cost level. The proposal for execution with various options (By WRD/ Through BOT/ By MSPGCL in collaboration with WRD) is under process.Project is likely to be commissioned 4 years after restart of works. |
| 24 | ## Polavaram ## APGENCO / Irrigation Deptt., A.P. ## 21.07.2010/ 25.02.2009 ## 12x80= 960 MW Broad Features: ## ECRF Dam- L-2454 m, H-57.9m, ## Spillway- L-1128m, ## Spill gate -48 Nos. ## Approach channel-175m. ## Intake tunnel: Ø 9m, L-130m (12 Nos) ## Power House- Surface type, ## Turbine- Vertical Kaplan ## Tail Race Channel- 1130m. Cost: Original: 4956.39 Latest:5338.95 (Power Component) Contractors Civil :Navyug contract terminated and awarded to M/s Megha Engineering and Infrastructure Ltd. (MEIL) (EPC contractor) E&M : BHEL | Andhra Pradesh 2017-18 2024-26 (Mar’26) | Pressure Tunnels (1 to 12) : Erection: Completed – 208 Nos., Balance- 80 Nos. Concreting: Completed – 204 Nos., Balance -84 Nos. U/s Transition : Completed – 1048Cum , Balance -4552 Cum D/s Transition: Completed – 7258 Cum, Balance -8142 Cum Power House area – Concreting work: Completed:18691 Cum, Balance: 64109Cum. Overall Physical progress: 22.97% Overall financial progress: 20% . |  |  |  |
| 25 | ## Lower Sileru extension ## APGENCO ## 2x115 = 230 MW ## 24.08.2020 Contractors ## M/s SSEL-PES Consortium Cost: Original: 571 (2020-21) Latest: 571 (2020-21) | Andhra Pradesh 2025-26 (Mar’26) | Project is in initial stage of construction |  |  |  |
| 26 | Pallivasal KSEB 2x30= 60 MW 31.01.2007 Broad Features: HRT: 3.50m X 3396m Surge Shaft: 7.0m X 49m Pressure Shaft: 2.50m X 1019.20m Penstock: 2.nos., 1161.20m each. Power House: Surface Turbine: Pelton S. Yard: 220kV – Single bus Cost: Original: 222.00 Latest: 550.00 Contractors Single Package (Except Intake & balance Tunneling works) ESSAR – DEC – CPPL JV -M/s Bumi-Zillion JV (for Intake works & balance Tunneling works) -M/s Anchor structure-PSE-SSIPCJV, M/s. Shri Sarvasana Industries Pvt. Ltd. | # Kerala 2010-11 2023-24 (Mar’24) |  | Contract for Civil &HM works has been terminated w.e.f. 13.09.18. Balance work has been re-tendered on the risk & cost of Contract, Subsequently balance works have been awarded to M/s. Sri Sarvasna Industries Pvt. Ltd. and M/s. DSE Anchor Structure. Civil Works: 99.35% completed. HM Works: 98.80% completed. E&M Works: 73% completed. Intake structure: Intake structure completed including gate erection. Leading channel of Water conductor system replaced by cut & cover/soil accordingly intake is shifted. HRT: Excavation 3347m/3347m completed. Invert conc: 3347m/3347m completed. Surge Tank/Forebay : Excavation completed. Conc.843/843 cum. Pressure Shaft: Excavation - Completed. fabrication of steel Liner completed and erection of 1096/1906 m completed. Surface penstock: Excavation 122500/122600 cum. Concreting- 12850/12850 cum. Fabrication of ferrule completed, Erection completed. Power House: Excavation and Concreting completed. Finishing works of Power House in progress. Tail race Channel (2 Nos.): Excavation & lining completed. The overall progress achieved: - 96.66%. The overall financial progress achieved:- 95.04%. |  |  |
| 27 | Thottiyar KSEB 1x30 + 1x10= 40 MW 05.06.2008 Broad Features: Weir: 222m Long 11 blocks 7.5m height Tunnel: Circular 2.6m dia 199m long. Power House: Surface Turbine : Vertical Pelton Cost: Original: 136.79 Latest: 280 Contractors Civil & HM : PRIL- Sri Sarvana Industries | # Kerala # 2012-13 2023-24 (Mar’24) |  | Original contract for Civil & HM works foreclosed without risk & cost of Contractor M/s. Coastal Project Ltd. -Civil & HM works re-awarded to M/s PRIL-Sri Sarvana Industries Pvt. Ltd. on 05.01.2018. KSEB decided to execute E&M works departmentally & tendering was awarded to M/s Fitwell. Civil Works: Weir: Excavation – 44.13% completed, Concreting – 77.90% completed. Approach Channel & Intake: 100% works completed. Tunnel – 100% works completed. Penstock, Anchors, Rocker support: Excavation – 87.24% completed, concreting -76.6% completed, Fabrication and erection of penstock 100% completed. Power house , switch yard and allied works: Excavation – 95.47%, Concreting – 67.54% completed. Bridge – 100% works completed. E&M works- Erection of supplied Electro/Hydro mechanical equipments for the power house was retendered on 14.02.2020. Physical Progress 96.70% Financial Progress 84.25% |  |  |
| 28 | Mankulam KSEB 2 X 20 = 40 MW 03.03.2022 Broad features: Dam: Concrete, straight gravity HRT:3.6mX2473m Surge shaft: Dia- 8m , top level of surge – 719.11m Pressure shaft: 1 no. Dia- 3m, Area – 7.07m2, Length – 398m Penstock: 2 Nos. 30m x2.3m Turbine: Pelton Max. gross head: 323.43m Cost: 600Cr. (2016) Contractors CIVIL & HM: M/s. PES Engineers Private Limited - M/s KSR Infracon Private Limited, Joint Venture (PES-KSR JV | # Kerala 2026-27 (May’26) |  | Civil Works : 6.75%completed. HM Works: Not yet started. E&M Works: Not yet tendered. Intake structure: Leading channel of Water conductor system excavated. HRT: Excavation -850 m completed. , Surge Tank/Forebay: Erection of Gantry crane progressing. Pressure Shaft: Excavation -511.6m. Power House: Excavation progressing Bridge and road: Bridge completed and opened for traffic. Dam: Block 7&8 Rock excavation is progressing. Overall Physical progress:9.11% Overall Financial progress: 6.48% |  |  |
| 29 | Kundah Pumped storage (Phase-I, Phase-II & Phase-III) TANGEDCO 4x125= 500 MW Broad Features: HRT: Ø 8.5mX1247.33m. Surge Shaft: Ø (28m/16m/10m) x68m depth. Pressure Shaft: 2 Nos. Ø 5.50m X 463.38 m (each) Penstock: 4.nos. Ø 3.9m x45.4m each. Power House: Under Ground. Tail race surge chamber: 10m(W);52m(L):48m(H) Tail Race Tunnel: Ø 8.5mx895m Turbine: Francis reversible turbine. Cost: Original: 1216.59 Revised: 3401 EPC cost: Rs. 2424.09 crore (capital cost under revision by TANGEDCO) Contractors Civil &HM : Patel / Kundah PSP E&M: MEIL | # Tamil Nadu # 2022-23 2024-25 (Jul’25) |  | Civil & H&M Works: - Phase-I, Package I & II (Civil and HM works), LOI issued for package - I to M/s Patel engineering, and for package - II M/s Kundah PSP Consortium on 15.02.2018. The site was handed over on 05.03.2018. MAT & CCVT: Mining works completed. Lining in CCVT to be done. ADITS in Power House & TRT, HRT Complexes: Mining works completed. Power House: Mining completed fully mining in 4 Nos. Bus ducts completed. Draft tube pit and drainage pit excavation completed, service bay raft concreting laying completed. Service bay column concrete 12 nos completed. Service Bay and Machine hall concrete under progress. TRT Surge Tank: Mining works completed. Transformer Cavern:Mining completed fully. Excavation for Draft tube, Gate shafts are completed. Transformer cavern sump excavation iscompleted. Transformer Hall Raft Concrete, waste oil sump under progressLining to be done. TRT: Mining completed and overt Concrete lining under progress. Lower intake:Work stopd since reservoir water lepevel raised above the Coffer dam top due to incessant monsoon rain. TRT Gate shaft: Mining completed. Lining work to be taken up. Draft Tube Tunnel: Mining in DT Tunnel-1, 2, 3, 4completed (5m & 4.5 m). Draft Tube Gate shaft (4 nos ):Mining completed. |  | . |
| 30 | ## Lower Kopli APGCL 2x55+2x2.5+1x5= 120 MW Broad Features: Dam: Conc. Gravity HRT- Circular, 7m dia, 3.64Km long. Power House- Surface Turbine- VF. Switchyard: 220 Kv. Cost: Original:1115.91 Latest:1795 Contractors Civil : L&T | # Assam 2023-24 2024-25 (Mar’25) |  | At present detailed survey work, geotechnical investigation work etc. are being carried out by M/s L&T. Civil work preliminary survey and geo technical investigations going on at site . Overall Physical progress – 61% Overall financial progress – 54.74% HM work – not yet started E&M works – contract awarded to M/S Andritz Hydro Pvt. Ltd on 09.09.21 |  |  |
| 31 | ## Chanju-III H.P. Power Corpn. Ltd. Clearance: 14.07.2015 3x16= 48 MW Broad Features: HRT- D shape, 5090m long. Power House- Under ground Turbine- Vertical shaft Pelton Cost: Original: 418.57 Latest: 418.57 Contractors Civil & HM : MFB- ACNC (JV). ## E&M : | # H.P. 2027-28 2027-28 (Jul’27) |  | - Mobilization by Civil Contractor in respect of Package-I & II:- Adit-1 of HRT –Excavation completed(136 m). Temporary Jhula (Ropeway) is under installation to start the excavation of HRT from Adit-1. Main Access Tunnel(205m): - MAT Portal excavation has been completed. Under ground excavation of MAT has been carried out up to 30m through local contractor. Now work is to be carried out by main contractor. E&M WORKS: Technical bids were opened on 22.07.2023 & evaluation of technical bids are under process. Tail Race Tunnel cum Adit to the bottom of pressure shaft: Portal excavation/development work of TRT is in progress since 24.09.2023. Backfilling work behind the rib for portal development is in progress. Diversion of additional Forest Land (2.62 ha): The case was uploaded on web portal of MoEF&CC on 13.02.2023.The joint inspection held on 18.03.2023. Thereafter case was uploaded on MoEF&CC web portal on 09.10.2023. Concerned DFO raised some observations & reply of the same was submitted on 24.10.2023. |  |  |
| 32 | ## Lakhwar Multipurpose Project (UJVNL) Clearance: 23.12.2021 3x100= 300 MW Cost: Original: 5747.17. Latest: 5747.17 | # Uttara khand 2028-29 2028-29 # (Oct’28) |  | Letter of Acceptance (LOA) has been issued to M/s L&T Limited for the work of “Balance civil works for Construction of 204m high concrete gravity dam, Intake, (3X100 MW) capacity underground Power House and appurtenant works on river Yamuna of Lakhwar Multipurpose Project in District- Dehradun/Tehri Garhwal (Uttarakhand)” on 01.02.2023. |  |  |
| C | Private Sector |  |  |  |  |  |
| 33 | Tangnu Romai-I M/s Tangnu Romai Power generation 2x22= 44 MW 30.11.2007 (TEC by HPSEB) Broad Features: Barrage at EL + 2555 m HRT-3.1m dia& 7.220 km length Surge Shaft- 5m dia, Top Level 2570 m & Bottom Level 2520 m Penstock- 2 m dia& 609.3 m length P.House- Surface Turbine – Vertical Francis Cost: Original:255.00 Latest:641.89 Contractors Civil & HM : Sai Urja E&M : Andritz | H.P. 2014-15 (Subject to re-start of works) |  | Civil works awarded on 14.06.2010 to M/s Sai Urja Hydel Project (P) Ltd. Barrage and Diversion Cannel: 26211 cum out of 93800 cum excavation completed. Desilting Chambers & SFTPC: Excavation completed. SFT excavation 420 / 450.66 m completed. HRT: 2826m out of 6300m excavation completed. Power House, Switchyard & Misc.: 60275 m3 out of 72000 m3 excavation completed. In February-2015, due to land slide the steel bridge on Pabbar River, connecting Project components has been completely damaged. The restoration works are completed. |  | - Works on hold since Aug 2016. Funds constraints with the developer. Project is likely to be commissioned 4 years after restart of works. |
| 34 | Tidong-I M/s Statkraft India Pvt. Ltd. 3x50 = 150 MW 28.07.2006 Broad Features: HRT–D-3.5m L- 8461 m P.H. Surface Turbine –Vertical Pelton Cost: Original 543.15 Latest 1850 Contractors Civil &HM : SCL Infratech / Himalaya E&M : Alstom | H.P. 2021-22( New Developer) 2024-25 (June’24) |  | River Diversion Works: Excavation completed and 32144/37159 cum concreting completed. Head Works: Head works for the project are nearing completion. HRT (8409m): HRT Excavation completed. 8356/8409 m lining completed. Surge Shaft: Surge shaft Excavation completed & Lining (10 m) out of 89m completed. Pressure Shaft: Pressure Shaft excavation completed (1.4 km). 471.77m out of 1388m lining has been completed. Powerhouse (Surface) & Tail-race Channel (4 m wide open channel, 50 m long): Power House external building construction completed. Overall, 98% Power House civil works has been completed. E&M Works: 100 MW, 100% works completed. 50 MW, 55% completed. T Line – 57% completed. Overall physical progress achieved is 91%. M/s Statkraft India Pvt Ltd has acquired the 100% equity of the project on 04.09.2018 |  | - Pressure shaft &Transmission Line critical. |
| 35 | Kutehr M/s JSW Energy (Kutehr) Ltd. 3x80 = 240 MW 31.08.2010 Broad Features: Cost: Original: 1798.13 Latest : 2879 Contractors Civil &HM : M/s Angelique – PCC consortium, M/s MF BumiGeotech Pvt. Ltd. & M/s. PES Engineers Pvt. Ltd. E&M : M/s Andritz Hydro Pvt Ltd. | H.P. 2024-25 2025-26 (Nov’25) |  | Civil works, HM works and E&M works awarded on 20.10.2019, 19.09.2019 and 13.02.2020 respectively. River diversion achieved on 25.01.2020. Barrage (27m high): Concreting of Upstream keys &Apron floor(85m) completed. Concrete of Left Half of barrage: 73076.85 cum completed out of 75000 cum. HRT: Six out of Six Construction Adits to HRT completed,14566.35m out of14566.35 m of Head Race Tce 03 daylighted on 27.10.2023 completed. . Physical Progress 73.30.5% Financial 70.15% |  |  |
| 36 | ## Phata Byung M/s Lanco 06.10.2008 2x38 MW = 76 MW Broad Features: Dam – 26m high HRT- 3.2 m dia& 9.38 km length Turbine – Frances Cost: Original: 520.00 Latest : 1132 Contractors Civil : Lanco HM : Cimmco E&M : Alstom | Uttara khand 2012-13 (Subject to re-start of works) |  | Dam concreting: 17800/18000 cum concreting completed. P.H.: Excavation completed & Concreting in progress. HRT: Excavation almost completed. 1400 m Lining has been completed. Excavation and lining of Intake-I & Intake-II completed. Pressure shaft: Excavation completed & lining is under progress. TRT: Excacation 178/235m completed. E&M Works: Pit liner erection of units completed. EOT Crane installed and Commissioned. Ferrule Fabrication work is in progress. Work progress is stalled since July’17 on account of main EPC contractor and holding Company M/s LancoInfratech Limited (LITL) being referred to NCLT under the Corporate Insolvency Resolution Process (CIRP) and subsequently, the initiation of liquidation proceeding as per NCLT Liquidation order in August 2018. However, the preservation works of Project are being carried out regularly at site by the Company, LancoMandakini Hydro Energy Private Limited (LMHEPL). Presently, the company is undergoing a corporate insolvency resolution process initiated under IBC for resolution and revival of the project since June 2020. Under this process, the resolution professional appointed by the NCLT has initiated the process for inviting prospective investors for the project. |  | - Works severely affected due to flash floods in June, 2013. - Works stalled since July, 2017 due to Financial crunch with the contractor / developer. The company is undergoing a corporate insolvency resolution process initiated under IBC for resolution and revival of the project since June 2020. Under this process, the resolution professional appointed by the NCLT initiated the process for inviting prospective investors for the project. On 25.02.2022, the CoC approved the Final Statkraft IH Holding AS Resolution Plan by a majority of 100%. The Resolution Professional has filed for approval of the resolution Plan Application before the Hon’ble NCLT. The Allahabad bench of the National Company Law Tribunal approved the resolution. According to the resolution plan, Statkraft will pay a total of ₹180 crore including ₹149.61 crore to secured financial creditors within 90 days of approval of the resolution plan and ₹27.8 crore towards meeting the payment for costs of the corporate insolvency resolution proceedings. Works stalled since July, 2017 due to Financial crunch.The project stands alloted to M/s Statkraft IH through NCLT on 23.03.2023. The revival of Environmental clearance is under process. Project is likely to be commissioned 2 years after restart of works. |
| 37 | Maheshwar, SMHPCL 30 12 96/ 29.9.2006 (FC) 10x40= 400 MW Broad Features: Dam-35m High, concrete gravity P.Shaft-10x7.82m x 52m P.House - Surface Turbine- Kaplan Cost: Original: 1569.27 Latest: 8121.00 Contractors Civil & HM : Sew E&M : BHEL | M. P. 2001-02 (Subject to re-start of works) |  | Civil & HM Works: All major civil works completed. All 27 nos radial gates commissioned. Unit Erection: Unit-10: Initial spinning achieved on 14.10.2011. Unit-9 & 8: Ready for spinning. Unit-7: Guide apparatus trial assembly in progress. Unit-6: Erection of turbine embedded parts & foundation parts completed. Unit-5 to 1: Erection of units is in initial stages. Works suspended since Nov-11 due to cash flow problem with developer. M.P. Power Management Company Ltd. has terminated the Power Purchase Agreement, R&R Agreement & Escrow Agreement with SMHPCL on 18.04.2020 &20.04.2020respectively . |  | Matter is sub-judice. Works suspended since Nov-11 due to cash flow problem with developer. M.P. Power Management Company Ltd. has terminated the Power Purchase Agreement with SMHPCL on 18.04.2020. The application of PFC has been admitted in NCLT on 27.09.2022 under IBC. CIRP has been put on hold by NCLT vide order dated 17.03.2023 in an application filed by Entegra Ltd. PFC has filed an Appeal before the NCLAT against the NCLT Order dated 17.03.2023 for recommencement of CIRP.Project is likely to be commissioned 2 years after restart of works. |
| 38 | Bhasmey Gati Infrastructure 2x25.5= 51 MW Broad Features : Dam-33.2m High, Symmetrical gravity HRT-5.3m dia&5.132 km length , Circular. Surge Shaft- 89.8m Hight& 14m dia. P.House-Outdoor Turbine-VF TRT-2 Nos, L- 50m Swityard-132/11 KV Cost :Original : 408.50 Latest :746.01 Contractors Civil : Simplex E&M : Voith | Sikkim 2012-13 (Subject to re-start of works) |  | Project is in initial stage of construction. River diversion achieved. Barrage: 61555cum/194600cumexcavation completed. HRT: 1670m/4460m excavation completed. PH: 136105 cum/185937cum excavation completed. Surge Shaft : 8567cum / 22000cum Surface excavation completed. Overall Physical progress: 38% . |  | - Matter is sub-judice. The Court appointed Resolution Professional for Bhasmey HEP stated that works stalled since Sept., 2016. CIRP has been initiated against Gati infra and NCLT has appointed Resolution Professional .The Resolution Professional has received 4 Resolution Plan in the matter of Gati Infrastructure Bhasmey Power Private Limited and are pending for approval from the Committee of Creditors. Project is likely to be commissioned 4 years after restart of works. |
| 39 | Rangit-II Sikkim Hydro Power Limited 10.02.2010 2x33= 66 MW Broad Features : Dam-47m High, Concrete Gravity HRT-3.9m dia&4.745 km length , Surge Shaft- 65.5m High & 10m dia. Underground Pressure Shaft : 1.7 m dia& 2.5 km length. P.House-Outdoor Turbine- Pelton Vertical Swityard- GIS, 132/11KV Cost :Original : 496.44 Latest : 496.44 Contractors Civil &HM : Coastal E&M : Gammon | Sikkim 2015-16 (Subject to re-start of works) |  | EPC contract awarded to M/s Coastal in February, 2012. Diversion Tunnel: River diversion through diversion tunnel has been achieved. Dam :Excavation 53100cum out of 85000cum completed. HRT: Excavation 623m out of 4745m completed. Surge Shaft: Excavation completed. Concreting 37/1667 cum done. Pressure shaft: Excavation of pressure shaft I - 25m out of 128m and pressure shaft II - 154m out of 377m completed Power House: Excavation of surface power house is being taken up. Overall Physical progress: 40% . |  | Works stalled since Dec., 2017. Funds constraints with the developer. Project is likely to be commissioned 3 years after restart of works |
| 40 | Panan Himagiri Hydro Energy Pvt. Ltd. 07.03.2011 4x75= 300 MW Broad Features : Dam-115m from deepest foundation level Desilting Chambers : Underground, 2 Size (14Lx22Wx2.5H) HRT- modified horse shoe, 6 m dia& 9549m length , Surge Shaft- 102 m High & 15m dia. Pressure Shaft : 2/4, 3.4/2.4m dia, 707.4 m- Long P.House-Surface Turbine-Vertical Francis Cost :Original: 1833.05 Latest :2675.00 Contractors Civil : Essar | Sikkim 2018-19 (Subject to re- start of works) |  | Civil works awarded on 22.02.2014. Infrastructural works and geological investigations are in progress. Starting of civil construction works was held up for want of the National Board of Wild Life (NBWL) clearance. On dismissal of the case in NGT on 21.08.17, the developer has made an application to PCCF cum-Secretary, Forests, Environment & Wild Life Management Department for grant of NOC, in National Board for Wildlife (NBWL) angle. Now, the NoC in regard to NBWL has been received vide state Govt letter dated 4.10.2019. In view of the new hydro policy announced by Ministry of Power, GOI, which will help in convincing the investors to release the funds to start the project works. An artificial lake (Mantham Lake) created in August 2016 due to heavy landslide resulting no accessibility for several years to the Upper Dzongu/ Dam site, which are beyond the control of the company/ force majeure. It is being understood that now Road and Bridge Department of Govt of Sikkim started erecting 60 Tonne Bridge, but work may progress in full stretch only after this rainy season i.e. of year 2022 and the construction work is likely to be completed by 4th quarter of 2022 then the project work will re-start. The project is likely to be commissioned in 2025-26, subject to restart of works. Overall Physical progress: NIL |  | - Accessibility to Project site. The permanent bridge over Mantam Lake for accessibility to Dam site is being constructed by Sikkim PWD which is likely to be completed by Nov' 2024. The Financial Institutes are awaiting for completion of bridge, thereafter the process of financing the project can start. .Project is likely to be commissioned 5 years after restart of works. |
| 41 | Pinnapuram PSP Greenko Energy 20.4.2022 4x240+2x120=1200 MW Broad Features : Upper reservoir: FRL 463m Dam height-40m from ground level Lower reservoir: FRL 337m Dam height-38m from ground level Pressure Shaft : 5, 7.5m dia, 83.5 m- long P.House-Surface Turbine-Vertical Francis reversible pump turbine Cost :Original: 6465.22 Latest :6465.22 Contractors E&M : M/s Andritz Civil : M/s Megha | Andhra Pradesh 2024-25 2024-25 2024-25 (Dec'24) |  | Upper Reservoir and Upper Intake: Excavation- 100% progress achieved. Concreting and erection : Upper reservoir-88% completed. Upper intake -64% completed. . Pressure Shaft: Excavation (5,08,644 cum), Fabrication (17,667 cum) and Erection( 17,667 cum)-98% & 75% and 67% completed respectively. Power House: Excavation (11,67,862 cum) completed. & Concreting (69%) completed. Lower Reservoir, Lower Intake and Tail Race Channel: All Excavation & lower reservoir embankments completed. Out of (40,834 cum) Tail Race Channel lining works 57% completed. Downstream intake and RCC works – 64% completed. E&M works: Power House – installation of DT segments ,DT cone, Foundation ring, Spiral segment, stay ring of unit 1 to 4 completed. Stator & Rotor service vay from unit 1&2 in progress. - Generator Components: 90% delivered to site - Turbine components: 40% delivered to site, majority of balance material being assembled directly at Andritz workshop, 1 unit is ready for dispatch - All Draft Tubes delivered to site - Stay ring for all Units delivered to site. - Turbine Shafts: 5 Units delivered to site. - Spiral case segments: All Units delivered to site. - Runners: 6 Units delivered to site. |  | -Developer is planning additional two units of 240MW each. |

Grand Total : 41 nos. – 17973.5 MW