## Annex-IB
Annex-II
List of Hydro Electric Projects (above 25 MW) held-up
Sl. No. | Name of Scheme | Sector | State /District | I.C. ( No. X MW.) | Cap. Under Execution(MW) | River/Basin | Type | % Physical progress | Present Status
(Executing Agency)
A | Projects held up due to sub-judice matters
1 | Lata Tapovan (NTPC) | Central | Uttarakhand/Chamoli | 3x57 | 171 | Dhauliganga /Alaknanada & Ganga | RoR | 3.8% | Matter is sub-judice. Infrastructure works almost completed. Hon’ble SC stayed construction of 24 HE projects in Uttarakhand including Lata Tapovan. Project is likely to be commissioned 4 years after restart of works. Work stalled since May, 2014.
2 | Maheshwar (SMHPCL) | Private | Madhya Pradesh /Khargone & Khandwa | 10x40 | 400 | Narmada/CIRS | RoR | 85% | Matter is sub-judice. Works suspended since Nov-11 due to cash flow problem with developer. M.P. Power Management Company Ltd. has terminated the Power Purchase Agreement with SMHPCL on 18.04.2020. The application of PFC has been admitted in NCLT on 27.09.2022 under IBC. CIRP has been put on hold by NCLT vide order dated 17.03.2023 in an application filed by Entegra Ltd. PFC has filed an Appeal before the NCLAT against the NCLT Order dated 17.03.2023 for recommencement of CIRP.Project is likely to be commissioned 2 years after restart of works.
3 | Bhasmey (Gati Infrastructure) Pvt. Ltd. | Private | Sikkim /East Sikkim | 2x25.5 | 51 | Rangpo/ Teesta/ Brahmaputra | RoR | 30% | Matter is sub-judice. The Court appointed Resolution Professional for Bhasmey HEP stated that works stalled since Sept., 2016. CIRP has been initiated against Gati infra and NCLT has appointed Resolution Professional .The Resolution Professional has received 4 Resolution Plan in the matter of Gati Infrastructure Bhasmey Power Private Limited and are pending for approval from the Committee of Creditors. Project is likely to be commissioned 4 years after restart of works.
|  |  | Sub total |  | 622
B | Projects held up due to funds constraints
1 | Tangnu Romai Power Generation Power Ltd. | Private | Himachal Pradesh /Shimla | 2x22 | 44 | Pabbar/Tons/ Yamuna/ Ganga | RoR | 20% | TRPGL is a project of Hydro Electric Power Plant.Works on hold since Aug' 2016.Corporate Insolvency Resolution Process (CIRP) has been initiated in respect of the Corporate Debtor (TRPGPL) under the Insolvency and Bankruptcy Code 2016 (IBC) vide an order of the Hon’ble National Company Law Tribunal, Chandigarh Bench dated 06th May, 2024. Project is likely to be commissioned 4 years after restart of works.
2 | Rangit-II (Sikkim Hydro) Power Ventures Ltd. | Private | Sikkim /West Sikkim | 2x33 | 66 | Greater Rangit/ Teesta/ Brahmaputra | RoR | 20% | Works stalled since Dec., 2017. Funds constraints with the developer.Therer was delay in providing land by State Government to the Company for Construction, the Environment Clearance got Expired. The Same is being under renewal from MoEF. Project is likely to be commissioned 3 years after restart of works.
|  |  | Sub total |  | 110
C | Project held up due to accessibility to project site
1 | Panan (Himagiri) Hydro Energy Private Ltd. | Private | Sikkim /North Sikkim | 4x75 | 300 | Rangyongchu/ Teesta/ Brahmaputra | RoR | Nil | The 300 MW Panan Hydroelectric Project in Dzongu, North Sikkim, has faced multiple delays due to various challenges. Initially, the project secured all necessary approvals and began construction in 2011, but an earthquake in 2011 delayed progress until 2012. Floods in 2016 washed away infrastructure, further hindering construction. Additionally, the formation of Mantam Lake posed further concerns. The project faced delays in obtaining NBWL clearance, which was finally achieved in 2019. The COVID-19 pandemic caused a lockdown from 2020 to 2021, delaying progress again. In October 2023, flash floods disrupted infrastructure, and the Teesta bridge collapse in February 2025 halted the project entirely. These events have severely impacted the construction timeline, with limited access to the project site. Despite overcoming several challenges, the project remains stalled due to ongoing infrastructure issues..Project is likely to be commissioned 5 years after restart of works.
|  |  | Sub total |  | 300
D | Projects held up due to other issue
1 | Lower Kalnai (JKSPDC) | State | U.T of Jammu & Kashmir /Kishtwar | 2x24 | 48 | Chenab/ Indus | RoR | 10% | The Lower Kalnai Hydel Project (48 MW) in Jammu and Kashmir faced delays due to contractor insolvency. In July 2011, tenders were invited for the EPC contract of the 48 MW Lower Kalnai Project. Coastal Projects Ltd emerged as the lowest qualified bidder with a negotiated EPC bid price of Rs. 396.00 crore. The estimated completion cost, based on the L1 offer, was Rs. 576.87 crore. The Notification of Award was issued on September 12, 2013, with a completion deadline of September 2017. On account of poor progress & insolvency of the contractor, JKSPDC decided to encash bank guarantees totalling Rs. 79.532 crore and terminate the contract. The EPC Contract with M/s Coastal Projects Private Limited was terminated in August 2019. The revised project cost was tendered in March 2022, with M/s MEIL emerging as the lowest bidder at Rs 701.66 crore, 24.30% higher than the original estimate. After negotiations, the final cost was reduced to Rs 671 crore. However, the project’s financial viability remains uncertain due to the need for exemptions, including SGST reimbursement and waivers on free power and water usage charges. Project is likely to be commissioned 4 years after restart of works.
2 | Koyna Left Bank (WRD,MAH) | State | Maharashtra /Satara | 2x40 | 80 | Koyna/ Krishna/EFR | PSS | 5% | Project stalled since July, 2015.The process for the revised administrative approval of the said project is in progress at the GoMWRD level . Government OF Maharashtra Water Resources Department has issued Policy for Development of Pumped Storage Hydropower Project dated 20.12.2023.As per the provision of this policy for developmentof Pumped Storage Hydropower Projects (PSP) and co-located Solar hybrid projects through Public Private Partnership is under progress. Government of Maharashtra,Water Resources Department has already spent total Rs.462.17 Crores till December -2024 on the Koyna Left bank Hydro project under Category-I of this policy.A Memorandum of Understanding has been signed for the further development of Koyna left bank Hydropower PSS (2x40MW) through a Joint Venture between Mahagenco and the Water Resources Department. Preparation of draft Lease Agreement for Koyna LBC PSS with Mahagenco is under finalization for further execution of the project..Project is likely to be commissioned 4 years after restart of works.
3 | Phata Byung (LANCO) | Private | Uttrakhand /Rudraprayag | 2x38 | 76 | Mandakini/Alaknanda Ganga | RoR | 74% | Works stalled since July, 2017 due to Financial crunch.The project stands alloted to M/s Statkraft IH through NCLT on 23.03.2023. the present progress is, ESIA studies are going on Based on TOR issued by MOEF and the project can restart the construction only after EC issued by EAC, MOEF. Project is likely to be commissioned 2 years after restart of works.
|  |  | Sub total |  | 204
| Total: |  |  |  | 1236