

                                               Hydro Capacity Addition Programme for 2023-24

	
Sl.
No.
	
Name of Project
	
State/ Implem. Agency
	
Unit No.
	
Capacity (MW)
	Date of Commissioning during start of year(As per
developer)
	Most likely scenario
(as assessed by CEA)at the start of year 2023-24
	Latest commissioning schedule

	
	Central Sector
	
	
	
	
	
	

	 
1
	Naitwar Mori
	Uttarakhand /SJVNL
	U-1
	30
	May'23
	June’23
	Commissioned on 24.11.2023

	
	2x30=60 MW
	
	U-2
	30
	May' 23
	July'23
	[bookmark: _GoBack]04.12.2023

	
2
	
Subansiri Lower 8x250= 2000 MW
	
Arunachal Pradesh/NHPC
	   U-1
U-2
U-3
U-4
	250
250
250
250

	June'23
July'23                   Aug'23                       Dec’23  
	         Aug’23
          Sept’23
         Jan’24
         Mar’24
	Mar’24
Mar’24
Slipping to 2024-25
Slipping to 2024-25

	       3
	Parbati St. II
4X200=800 MW
	Himachal Pradesh/NHPC
	U-1
   U-2
U-3
U-4
	200
200
200
200
	Mar'24
Mar'24
 Mar'24
 Mar'24
	Not likely during 2023-24

	Not likely during 2023-24

	
	
	
	
	
	
	
	 

	4
	Tehri PSS
	Uttarakhand/THDC
	U-1
	250
	Aug'23
	Oct'23
	Slipping to 2024-25

	
	4x250= 1000 MW
	
	U-2
U-3
U-4
	250
250
250
	Sept'23
Nov.'23
Dec.'23
	Nov'23
Jan’24
Feb’24
	Slipping to 2024-25
Slipping to 2024-25
Slipping to 2024-25

	
	
	Sub- total (Central):
	
	2860
	2860
	2060
	560

	
	State Sector
	
	
	
	
	
	

	5
	Pallivasal
	Kerala/ KSEB Ltd.
	U-1
	30
	June'23
	Dec'23
	Mar'24

	
	2x30= 60 MW
	
	U-2
	30
	June'23
	Dec'23
	Mar'24

	
6
	Thottiyar
	
Kerala/ KSEB Ltd.
	U-1
	30
	       Jul'23
	Dec'23
	Mar'24

	
	1x30 + 1x10= 40 MW
	
	U-2
	10
	       Nov'23
	Mar'24
	Mar'24

	
	
	Sub- total (State):
	
	100
	100
	100
	100

	
	Private Sector
	
	
	
	
	
	

	
7
	Tidong-I
3x50= 150 MW
	Himachal Pradesh/
M/s Statkraft
India Pvt. Ltd.
	  U-1
  U-2
  U-3

	50
50
50
	June'24                       June'24
June'24
	Not likely during 2023-24
	
Not likely during 2023-24

	    
    8
	Pinnapuram  4X240+2X120=1200 MW
	  M/s Greenko   Energies Pvt. Ltd.
	U-1
U-2
U-3
U-4
U-5
U-6
	240
240
240
240
120
120
	Jan’24
Jan’24
Feb’24
Feb’24
Mar’24
Mar’24
	Jan’24
Feb’24
               Mar’24
Not likely during 2023-24
Not likely during 2023-24
Not likely during 2023-24
	 Slipping to 2024-25
Slipping to 2024-25
Slipping to 2024-25
Not likely during 2023-24
Not likely during 2023-24
Not likely during 2023-24

	
	
	Sub- total (Private):
	
	    
    1350
	             1350
	           720
	         -

	Total (CS+SS+PS)
	4310
	4310
	2880
	660



                     Total capacity likely to be achieved by 31.03.2024 – 660 MW
