
    
Hydro Capacity Addition Programme for 2025-26

	Sl.
No.
	Name of Project
	State/ Implem. Agency
	Unit No.
	Capacity (MW)
	Capacity Addition


	
	
	
	
	Target
	Actual
	As Programmed/ Anticipated

	
	Central Sector
	
	
	
	
	

	1
	Parbati-II /NHPC
(4*200=800 MW)
	Himachal Pradesh/NHPC
	U-4
	200
	200
	Commissioned on 13.04.2025

	2
	SUBANSIRI LOWER /NHPC
	Arunachal Pradesh/NHPC
	U-1 to 4
	1000
	500
	Mar'2026
[bookmark: _GoBack](U-2 & U-3 commissioned during Dec’25 to Jan’26)

	3
	Tehri PSS/THDC

	Uttarakhand/THDC

	U-1 to U-4
	1000
	750
	Jan’2026
(U-1 ,2& 3 commissioned on 05.06.2025, 05.07.2025 & 10.12.2025 respectively)

	
	
	Sub- total (Central):
	
	2200
	1450
	

	
	State Sector
	
	
	
	
	

	1
	Lower Kopili /APGCL
	Assam/APGCL
	U-1 to 2
	110
	0
	Mar'2026

	
	
	Sub- Total (State):
	
	110
	0
	


	
	Private Sector
	
	
	
	
	

	
1
	  Kutehr/JSW
	Himachal Pradesh/JSW
	U-1 to 3
	240
	240
	Commissioned in Aug'2025

	2
	Pinnapuram  6X240+2X120
=1680 MW
	Andhra Pradesh/Greenko
	U-1 to 8
	1680
	1680
	Commissioned in Oct'2025

	
	
	Sub- Total (Private):
	
	1920
	1920
	

	Total (CS+SS+PS)
	
	4230
	3370
	



