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                                           Hydro Capacity Addition Programme for 2023-24

	Sl.
No.
	Name of Project
	State/ Implem. Agency
	Unit No.
	Capacity (MW)
	Capacity Addition

	Reason for slippage

	
	
	
	
	Target 
	Actual 
	As Programmed
	Actual(A)/ Anticipated
	

	
	Central Sector
	
	
	
	
	
	
	

	
1
	Naitwar Mori
	Uttarakhand /SJVNL
	U-1
	30
	30
	June’23
	 24.11.2023
	

	
	2x30=60 MW
	
	U-2
	30
	30
	July'23
	    04.12.2023
	

	
2
	
Subansiri Lower 8x250= 2000 MW
	
Arunachal Pradesh/NHPC
	  U-1
U-2
U-3
U-4
	250
250
250
250

	
	Aug’23
Sept’23
Jan’24         Mar’24
	Slipping to 2025-26
Slipping to 2025-26
Slipping to 2025-26
Slipping to 2025-26

	· Diversion tunnel-1 collapsed.
· Slope stability of left bank. 
· Erection of balance 6 nos. of      radial gates, DT plugging

	3
	Tehri PSS
4x250= 1000 MW
	Uttarakhand/THDC
	U-1    U-2
U-3
U-4
	250
250
250
250
	
	Oct'23
Nov'23
Jan’24
Feb’24
	Slipping to 2024-25
Slipping to 2024-25
Slipping to 2024-25
Slipping to 2024-25

	· River joining works are critical
· Permission from Up irrigation Dept from 1-30th Jun,2024
·  Plug breaking of HRT

	
	
	Sub- total (Central):
	
	2060
	
	2060
	60
	

	
	State Sector
	
	
	
	
	
	
	

	4
	Pallivasal
	Kerala/ KSEB Ltd.
	U-1
	30
	
	Dec'23
	Mar'24
	

	
	2x30= 60 MW
	
	U-2
	30
	
	Dec'23
	Mar'24
	

	
5
	Thottiyar
	
Kerala/ KSEB Ltd.
	U-1
	30
	
	Dec'23
	Mar'24
	

	
	1x30 + 1x10= 40 MW
	
	U-2
	10
	
	Mar'24
	Mar'24
	

	
	
	Sub- total (State):
	
	100
	
	100
	100
	

	
	Private Sector
	
	
	
	
	
	
	

	
6
	Pinnapuram  4X240+2X120=1200 MW
	M/s Greenko   Energies Pvt. Ltd.
	U-1
U-2
U-3

	240
240
240

	
	Jan’24
Feb’24
Mar’24

	Slipping to 2024-25
Slipping to 2024-25
Slipping to 2024-25

	Slow progress of works 

	
	
	Sub- total (Private):
	
	    
   720
	
	720
	-
	

	Total (CS+SS+PS)
	2880
	60
	2880
	160
	



