## Annex-1A
Annex 1A
List of Hydro Electric Projects (above 25 MW) under implementation
Sl. No. | Name of Scheme | Sector | District | I.C. ( No. X MW.) | Cap. Under Execution(MW) | River/Basin | Anticipated date of commissioning
(Executing Agency)
Andhra Pradesh
1 | Polavaram (APGENCO/ Irrigation Dept., A.P.) | State | East & West Godavari | 12x80 | 960 | Godavari/EFR | 2027-28 (Sep'27)
2 | Lower Sileru Extension (APGENCO) | State | Alluri Sitharamaraju | 2x115 | 230 | Sileru/Godavari | 2025-26 (Mar'26)
| Sub-total: Andhra Pradesh |  |  |  | 1190
Arunachal Pradesh
3 | Subansiri Lower (NHPC) | Central | Lower Subansiri | 8x250 | 2000 | Subansiri/ Brahmaputra | 2025-27 # (May'26)
4 | Dibang Multipurpose Project (NHPC) | Central | Lower Dibang Valley | 12x240 | 2880 | Dibang /Brahmaputra | 2031-32 (Feb'32)
5 | HEO | Central | West Siang | 3x80 | 240 | Yarjep River | 2029-30 (Sept'29)
6 | Tato-I | Central | Shi-Yomi | 3x62 | 186 | Siyom River | 2029-30 (Sept'29)
| Sub-total: Arunachal Pradesh |  |  |  | 5306
Assam
7 | Lower Kopli (APGCL) | State | Dima Hasao & Karbi Anglong | 2x55+2x2.5+1x5 | 120 | Kopili/ Brahmaputra | 2025-27## (Apr'26)
| Sub-total: Assam |  |  |  | 120
Himachal Pradesh
8 | Luhri-I (SJVN) | Central | Kullu/Shimla | 2x80+2x25 | 210 | Satluj/Indus | 2028-29 (Dec'28)
9 | Dhaulasidh (SJVN) | Central | Hamirpur/ Kangra | 2x33 | 66 | Beas/Indus | 2026-27 (Mar'27)
10 | Sunni Dam (SJVN) | Central | Shimla/Mandi | 4x73+1x73+1x17 | 382 | Satluj | 2028-29 (Dec'28)
11 | Shongtong Karcham (HPPCL) | State | Kinnaur | 3x150 | 450 | Satluj/ Indus | 2028-2 (Sep'28)
12 | Chanju-III (HPPCL) | State | Chamba | 3x16 | 48 | Chanju Nallah | 2027-28 (Dec'27)
13 | Tidong-I (Statkraft IPL) | Private | Kinnaur | 3x50 | 150 | Tidong/Satluj/Indus | 2026-27 (Jun'26)
14 | Kutehr (JSW Energy Ltd) | Private | Chamba | 3x80 | 240 | Ravi/ Indus | 2025-26 (Aug'25)
| Sub-total: Himachal Pradesh |  |  |  | 1546
Jammu & Kashmir
15 | Pakal Dul (CVPPL) | Central | Kishtwar | 4x250 | 1000 | Marusadar/ Chenab / Indus | 2026-27 (Dec'26)
16 | Kiru (CVPPL) | Central | Kishtwar | 4x156 | 624 | Chenab/ Indus | 2026-27 (Dec'26)
17 | Ratle (RHEPPL / NHPC) | Central | Kishtwar | 4x205 + 1x30 | 850 | Chenab/Indus | 2029-30 (Aug'29)
18 | Kwar (CVPPPL) | Central | Kishtwar | 4x135 | 540 | Chenab/ Indus | 2027-28 (Mar'28)
19 | Parnai (JKSPDC) | State | Poonch | 3x12.5 | 37.5 | Jhelum/ Indus | 2027-28 (Dec'27)
| Sub-total: Jammu & Kashmir |  |  |  | 3051.5
Kerala
20 | Mankulam (KSEB) | State | Idukki | 2x20 | 40 | Melachery | 2026-27 (Dec'26)
| Sub-total: Kerala |  |  |  | 40
Punjab
21 | Shahpurkandi (PSPCL/ Irrigation Deptt., Pb.) | State | Pathankot | 3x33+3x33+1x8 | 206 | Ravi/ Indus | 2026-27 (Oct'26)
| Sub-total: Punjab |  |  |  | 206
Sikkim
22 | Teesta St. VI NHPC | Central | South Sikkim | 4x125 | 500 | Teesta/Brahmaputra | 2026-27 (Dec'27)
23 | Rangit-IV (NHPC) | Central | West Sikkim | 3x40 | 120 | Rangit/ Teesta/ Brahmaputra | 2025-26 (Dec'25)
| Sub-total: Sikkim |  |  |  | 620
Uttarakhand
24 | Vishnugad Pipalkoti (THDC) | Central | Chamoli | 4x111 | 444 | Alaknanada/Ganga | 2026-27 (Mar'27)
25 | Tapovan Vishnugad (NTPC) | Central | Chamoli | 4x130 | 520 | Dhauliganga / Alaknanada & /Ganga | 2028-29 (Mar'29)
26 | Lakhwar Multipurpose Project (UJVNL) | State | Dehradun & Tehri Garhwal | 3x100 | 300 | Yamuna | 2031-32 (Dec'31)
| Sub-total: Uttarakhand |  |  |  | 1264
West Bengal
27 | Rammam-III (NTPC) | Central | Darjeeling | 3x40 | 120 | Rammam/ Rangit/Teesta Brahmaputra | 2028-29 (Mar'29)
| Sub-total: West Bengal |  |  |  | 120
| Total: |  |  |  | 13463.5
# 5 units (1250 MW) likely during 2025-26 and 3 units (750 MW) likely during 2026-27.
##2 units (110 MW) likely during 2025-26, 3 units (10 MW) likely during 2026-27.
Note:-Presently 27 no. of hydro electric project (above 25 MW) totaling to 13463.5 MW are under implementation.

## Sheet1
Annex 1B
List of Pumped Storagec Projects (above 25 MW) under implementation
Sl. No. | Name of the Project (Executing Agency) | Sector | District | I.C. ( No. X MW.) | Cap. Under Execution(MW) | River/Basin | Date of commissioning
Andhra Pradesh
1 | Pinnapuram (Greenko AP01 IREP Private Limited) | Private | Kurnool | 1x240+2x120 | 480 | Off Stream | 2025-26$ (Aug'25)
2 | Chitravathi PSP(M/s Adani Renewable Energy Forty-Two Limited) | Private | Satya Sai | 2x250 | 500 | Chitravathi River | 2026-27 (Oct'26)
3 | Upper Sileru PSP (APGENCO) | State | Alluri Sitharamaraju | 9x150 | 1350 | Sileru/Godavari | 2028-29 (Feb'29)
| Sub-total: Andhra Pradesh |  |  |  | 2330
Karnataka
4 | Sharavathy Pumped Storage Project | State | Upper dam (Shimoga) & Lower dam (Uttara Kannada) | 8x250 | 2000 | Sharavathy/WFR | 2029-30 (Dec'29)
| Sub-total: Karnataka |  |  |  | 2000
Madhya Pradesh
5 | MP30 Gandhi Sagar Pumped Storage Project (Greenko MP01 IREP Private Limited) | Private | Neemuch | 7x240 + 2x120 | 1920 | Off Stream | 2028-29 (Jun'28)
| Sub-total: Madhya Pradesh |  |  |  | 1920
Tamil Nadu
6 | Kundah Pumped Storage Phase-I,II&III) | State | Nilgiris | 4x125 | 500 | Kundah/Bhavani/ Cauvery/EFR | 2025-27# (Apr'26)
| Sub-total: Tamil Nadu |  |  |  | 500
Uttarakhand
7 | Tehri PSS (THDC) | Central | Tehri Garhwal | 2x250 | 500 | Bhilangna/Bhagirathi/ Ganga | 2025-26* (Oct'25)
| Sub-total: Uttarakhand |  |  |  | 500
Maharashtra
8 | Bhivpuri PSP(M/s Tata Power Company Limited) | Private | Raigad | 4x200 + 2x100 | 1000 | Indrayani River | 2028-29 (Oct'28)
| Sub-total: Maharashtra |  |  |  | 1000
| Total: |  |  |  | 8250
Note:-Presently 8 no. of Pumped Storage projects (above 25 MW) totaling to 8250 MW are under implementation.
$Out of total eight units five units of Pinnapuram PSP(1200MW) has been commissioned during June,2025.
*Out of total four units two unit of Tehri PSP(250MW) has been commissioned during June and July 2025
#3 units (375 MW) likely during 2025-26, 1 unit (125 MW) likely during 2026-27