**Hydro Capacity addition Programme for 2021-22**

| **Sl.**  **No.** | **Name of the project (Capacity)** | **Unit Nos.** | **Cap.**  **(MW)** | **Capacity Addition**  **as Programmed (Month)** | **Capacity Addition**  **Actual (Date)** | **Remarks** |
| --- | --- | --- | --- | --- | --- | --- |
| **A.** | **State Sector** |  |  |  |  |  |
| 1 | **Pallivasal**  KSEB, Kerala  2x30=60 MW | Unit #1  Unit # 2 | 30  30 | December’21  December’21 |  |  |
| 2 | **Thottiyar**  KSEB, Kerala  1x30+1x10=40MW | Unit #1  Unit # 2 | 10  30 | December’21  December’21 |  |  |
|  | **Sub- total (A):** |  | **100 MW** |  |  |  |
| **B.** | **Private Sector** |  |  |  |  |  |
| 3 | **Sorang**  HSPCL, H.P.  2x50=100 MW | Unit #1  Unit # 2 | 50  50 | August’21  August’21 |  |  |
| 4 | **Bajoli Holi**  GMRBHHPPL, H.P.  3x60=180 MW | Unit #1  Unit # 2  Unit # 3 | 60  60  60 | September’21  September’21  September’21 |  |  |
| 5 | **Rongnichu**  MBPCL, Sikkim  2x56.5=113 MW | Unit #1  Unit # 2 | 56.5  56.5 | June’21  June’21 | 25.06.2021  30.06.2021 | **Commissioned**  **Commissioned** |
|  | **Sub- total (B):** |  | **393 MW** |  |  |  |
|  | **Total (A+B)** |  | **493 MW** |  |  |  |