**Hydro Capacity addition Programme for 2021-22**

 (As on 31.10.2021)

| **Sl.****No.** | **Name of the project (Capacity)** | **Unit Nos.** | **Cap.****(MW)** | **Capacity Addition** **as Programmed (Month)** | **Capacity Addition** **Actual (Date)** | **Remarks** |
| --- | --- | --- | --- | --- | --- | --- |
| **A.** | **State Sector** |  |  |  |  |  |
| 1 | **Pallivasal**KSEB, Kerala2x30=60 MW | Unit #1Unit # 2 | 3030 | December’21December’21 |  | Likely to slip  |
| 2 | **Thottiyar**KSEB, Kerala1x30+1x10=40MW | Unit #1Unit # 2 | 1030 | December’21December’21 |  | Likely to slip. |
|  | **Sub- total (A):** |  | **100 MW** |  |  |  |
| **B.** | **Private Sector** |  |  |  |  |  |
| 3 | **Sorang**HSPCL, H.P.2x50=100 MW | Unit #1Unit # 2 | 5050 | June’21June’21 | 23.09.202121.09.2021 | **Commissioned****Commissioned** |
| 4 | **Bajoli Holi**GMRBHHPPL, H.P.3x60=180 MW | Unit #1Unit # 2Unit # 3 | 606060 | June’21June’21June’21 |  |  |
| 5 | **Rongnichu**MBPCL, Sikkim2x56.5=113 MW | Unit #1Unit # 2 | 56.556.5 | May’21May’21 | 25.06.202130.06.2021 | **Commissioned****Commissioned** |
|  | **Sub- total (B):** |  | **393 MW** |  |  |  |
|  | **Total (A+B)** |  | **493 MW** |  |  |  |

**Note:-**

**213 MW out of the target of 493 MW commissioned**.

**Vyasi (120MW) was not under original Hydro Capacity addition Programme for 2021-22.The project is likely to be commissioned by Mar’22.**

**Hydro Capacity addition Programme for 2021-22**

| **Sl.****No.** | **Particular****(With Address)** | **Unit Nos.** | **Cap.****(MW)** | **Capacity addition** **as programmed** |
| --- | --- | --- | --- | --- |
| **A.** | **State Sector** |  |  |  |
| 1. | **Vyasi\***UJVNL Dehradun, Uttarakhand2x60=120 MW | Unit#1Unit#2 | 6060 | Mar,22Mar,22 |
|  | **Sub- total (A):** |  | **120**  |  |
| **B.** | **Private Sector** |  |  |  |
| 2 | **Rongnichu**2x56.5= 113 MWMadhya Bharat Power Corporationh. East Sikkim, Sikkim | Unit #1Unit # 2 | 56.556.5 | June,21(Comm.)June,21(Comm.) |
| 3. | **Sorang**Himachal Sorang Power Kinnaur, H.P.2x50= 100 MW | Unit #1Unit # 2 | 5050 | Sept,21(Comm.)Sept,21(Comm.) |
| 4. | **Bajoli Holi**GMR Bajoli Holi HydroPower Pvt. Ltd. Chamba, H.P.3x60= 180 MW | Unit #1Unit # 2Unit # 3 | 606060 | Nov,21Nov,21Nov,21 |
|  |  |  |  |  |
|  | **Sub- total (B):** |  | **393** |  |
|  | **Total (A+B)** |  | **513** |  |

**Note:-**

**\***Vyasi (120MW) was not under original Hydro Capacity addition Programme for 2021-22.

2. Pallivasal and Thottiyar were under original Hydro Capacity addition Programme for 2021-22 have now slipped to 2022-23.