**Hydro Capacity addition Programme for 2021-22**

| **Sl.****No.** | **Name of the project (Capacity)** | **Unit Nos.** | **Cap.****(MW)** | **Capacity Addition** **as Programmed (Month)** | **Capacity Addition** **Actual (Date)** | **Remarks** |
| --- | --- | --- | --- | --- | --- | --- |
| **A.** | **State Sector** |  |  |  |  |  |
| 1 | **Pallivasal**KSEB, Kerala2x30=60 MW | Unit #1Unit # 2 | 3030 | December’21December’21 |  | **Slipping to 2022-23** |
| 2 | **Thottiyar**KSEB, Kerala1x30+1x10=40MW | Unit #1Unit # 2 | 1030 | December’21December’21 |  |  **Slipping to 2022-23**. |
|  | **Sub- total (A):** |  | **100 MW** |  |  |  |
| **B.** | **Private Sector** |  |  |  |  |  |
| 3 | **Sorang**HSPCL, H.P.2x50=100 MW | Unit #1Unit # 2 | 5050 | June’21June’21 | 23.09.202121.09.2021 | **Commissioned****Commissioned** |
| 4 | **Bajoli Holi**GMRBHHPPL, H.P.3x60=180 MW | Unit #1Unit # 2Unit # 3 | 606060 | June’21June’21June’21 |  | **Feb’22 (likely)****Feb’22 (likely)****Feb’22 (likely)** |
| 5 | **Rongnichu**MBPCL, Sikkim2x56.5=113 MW | Unit #1Unit # 2 | 56.556.5 | May’21May’21 | 25.06.202130.06.2021 | **Commissioned****Commissioned** |
|  | **Sub- total (B):** |  | **393 MW** |  |  |  |
|  | **Total (A+B)** |  | **493 MW** |  |  |  |

**Note:-**

**213 MW out of the target of 493 MW commissioned**.

**Vyasi (120MW) was not under original Hydro Capacity addition Programme for 2021-22.The project is likely to be commissioned by Mar’22.**