**Annex-I**

**Hydro Capacity Addition Programme for 2023-24**

**(Above 25 MW & excluding Projects under Ministry of New & Energy)**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Sl.****No.** | **Name of Project** | **State/ Implem. Agency** | **Unit No.** | **Capacity (MW)** | **Date of Commissioning (As per****developer)** | **Most likely scenario** |
|  | **Central Sector** |  |  |  |  |  |
| 1 | Naitwar Mori | Uttarakhand /SJVNL | U-1 | 30 | May'23 | Aug’23 |
| 2x30=60 MW | U-2 | 30 | May' 23 | Sept'23 |
| 2 | Subansiri Lower 8x250= 2000 MW | Arunachal Pradesh/NHPC |  U-1U-2U-3U-4 | 250250250250 | June'23July'23 Aug'23 Dec'23 | Dec’23Dec’232024-25 2024-25 |
| 3 | Tehri PSS4x250= 1000 MW | Uttarakhand/THDC | U-1U-2U-3U-4 | 250250250250 | Aug'23Sept'23Nov.'23Dec.'23 | Feb’24Mar’242024-25 2024-25 |
|  |
|  |  | **Sub- total (Central):** |  | **2860** | **2860** | **1060** |
|  | **State Sector** |  |  |  |  |  |
| 5 | Pallivasal | Kerala/ KSEB Ltd. | U-1 | 30 | June'23 | Dec'23 |
| 2x30= 60 MW | U-2 | 30 | June'23 | Mar'24 |
| 6 | Thottiyar | Kerala/ KSEB Ltd. | U-1 | 30 |  Jul'23 | Dec'23 |
| 1x30 + 1x10= 40 MW | U-2 | 10 |  Nov'23 | Mar'24 |
|  |  | **Sub- total (State):** |  | **100** | **100** | **100** |
|  | **Private Sector** |  |  |  |  |  |
| 7 | Tidong-I3x50= 150 MW | Himachal Pradesh/M/s StatkraftIndia Pvt. Ltd. |  U-1 U-2 U-3 | 505050 | June'24 June'24June'24 | Not likely during 2023-24 |
|   8 | Pinnapuram 4X240+2X120=1200 MW |  M/s Greenko Energies Pvt. Ltd. | U-1U-2U-3U-4U-5U-6 | 240240240240120120 | Jan’24Jan’24Feb’24Feb’24Mar’24Mar’24 | Feb’24Mar’242024-252024-252024-252024-25 |
|  |  | **Sub- total (Private):** |  |  **1350** |  **1350** |  **480** |
| **Total (CS+SS+PS)** | **4310** | **4310** | **1640** |