**Hydro Capacity Addition Programme for 2024-25**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Sl.**  **No.** | **Name of Project** | **State/ Implem. Agency** | **Unit No.** | **Capacity (MW)** | | **Capacity Addition** |
|  |  |  |  | **Target** | **Actual** | **As Programmed/ Anticipated** |
|  | **Central Sector** |  |  |  |  |  |
| 1 | Parbati-II /NHPC  (4\*200=800 MW) | Himachal Pradesh/NHPC | U-1  U-2  U-3  U-4 | 200  200  200  200 | 0 | Dec'24  Dec'24  Dec'24  Dec'24 |
| 2 | Tehri PSS/THDC  (4\*250=1000 MW) | Uttarakhand/THDC | U-1  U-2  U-3  U-4 | 250  250  250  250 | 0 | Sept’24  Oct'24  Nov'24  Dec’24 |
| 3 | Subansiri Lower / NHPC  (8x250=2000 MW | Arunachal Pradesh/Assam/ NHPC | U-1  U-2  U-3 | 250  250  250 | 0 | Mar’25  Mar’25  Mar’25 |
|  |  | **Sub- total (Central):** |  | **2550** | **0** |  |
|  | **State Sector** |  |  |  |  |  |
| 4 | Pallivasal  (2x30= 60 MW) | Kerala/ KSEB Ltd. | U-1  U-2 | 30  30 | 0 | Sept’24  Sept’24 |
| 5 | Thottiyar  (1x30 + 1x10  = 40 MW) | Kerala/ KSEB Ltd. | U-1 U-2 | 10  30 | 0 | Sept’24  Sept’24 |
| 6 | Uhl-III  (3\*33.3=100 MW) | Himachal Pradesh/BVPCL | U-1  U-2  U-3 | 33.3  33.3  33.3 | 0 | Oct’24  Nov’24  Dec’24 |
|  |  | **Sub- total (State):** |  | **200** | **0** |  |
|  | **Private Sector** |  |  |  |  |  |
| 7 | Pinnapuram 4X240+2X120  =1200 MW | Andhrapradesh/M/s Greenko Energies Pvt. Ltd. | U-1  U-2  U-3  U-4  U-5  U-6 | 240  240  240  240  120  120 | 0 | Dec’24  Dec’24  Jan’25  Feb’25  Feb’25  Mar’25 |
|  |  | **Sub-total (Private):** |  | **1200** | **0** |  |
| **Total (CS+SS+PS)** | | | | **3950** | **0** |  |