**Hydro Capacity Addition Programme for 2025-26**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Sl.**  **No.** | **Name of Project** | **State/ Implem. Agency** | **Unit No.** | **Capacity (MW)** | | **Capacity Addition** |
|  |  |  |  | **Target** | **Actual** | **As Programmed/ Anticipated** |
|  | **Central Sector** |  |  |  |  |  |
| 1 | Parbati-II /NHPC  (4\*200=800 MW) | Himachal Pradesh/NHPC | U-4 | 200 | 200 | Commissioned on 13.04.2025 |
| 2 | Tehri PSS/THDC  (4\*250=1000 MW) | Uttarakhand/THDC | U-1  U-2  U-3  U-4 | 250  250  250  250 | 0 | May'25  Jun’25  Aug’25  Oct’25 |
| 3 | Rangit-IV/NHPC | Sikkim | U-1  U-2  U-3 | 40  40  40 | 0 | Dec'25  Dec'25  Dec'25 |
| 4 | SUBANSIRI LOWER /NHPC  8X250=2000 MW | Arunachal Pradesh | U-1  U-2  U-3  U-4  U-5 | 250  250  250  250  250 | 0 | Dec’25  Jan’26  Jan’26  Feb’26  Feb’26 |
|  |  |  |  |  |  |  |
|  |  | **Sub-total (Central):** |  | **2570** | **200** |  |
|  | **State Sector** |  |  |  |  |  |
| 3 | Lower Sileru Extension /APGENCO) | Andhra Pradesh | U-1  U-2 | 115  115 | 0 | Mar'26  Mar'26 |
| 4 | Lower Kopili /APGCL | Assam | U-1  U-2 | 55  55 | 0 | Sep'25  Sep'25 |
| 5 | Kundah Pumped Storage (Phase-I, Phase-II & Phase-III) /TANGEDCO | Tamil Nadu | U-1  U-2  U-3 | 125  125  125 | 0 | Feb'26  Feb'26  Mar'26 |
|  |  | **Sub-total (State):** |  | **715** | **0** |  |
|  | **Private Sector** |  |  |  |  |  |
| 6 | Pinnapuram 4X240+2X120  =1200 MW | Andhra Pradesh/M/s Greenko Energies Pvt. Ltd. | U-1  U-2  U-3  U-4  U-5  U-6  U-7  U-8 | 240  240  240  240  120  120  240  240 | 0 | May’25  May’25  May’25  Jun’25  Jun’25  Jul’25  Aug’25  Sept’25 |
| 7 | Kutehr/JSW  3x80=240MW | Himachal Pradesh | U-1  U-2  U-3 | 80  80  80 |  | May’25  May’25  May’25 |
|  |  | **Sub-total (Private):** |  | **1920** | **0** |  |
| **Total (CS+SS+PS)** | | | | **5205** | **200** |  |