**Hydro Capacity Addition Programme for 2025-26**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Sl.****No.** | **Name of Project** | **State/ Implem. Agency** | **Unit No.** | **Capacity (MW)** | **Capacity Addition** |
|  |  |  |  | **Target** | **Actual** | **As Programmed/ Anticipated** |
|  | **Central Sector** |  |  |  |  |  |
| 1 | Parbati-II /NHPC(4\*200=800 MW) | Himachal Pradesh/NHPC | U-4 | 200 | 200 | Commissioned on 13.04.2025 |
| 2 | Tehri PSS/THDC(4\*250=1000 MW) | Uttarakhand/THDC | U-1U-2U-3U-4 | 250250250250 |  0 | May'25Jun’25Aug’25Oct’25 |
| 3 | Rangit-IV/NHPC | Sikkim | U-1U-2U-3 | 404040 | 0 | Dec'25Dec'25Dec'25 |
| 4 | SUBANSIRI LOWER /NHPC8X250=2000 MW | Arunachal Pradesh | U-1U-2U-3U-4U-5 | 250250250250250 |  0 | Dec’25Jan’26Jan’26Feb’26Feb’26 |
|  |  |  |  |  |  |  |
|  |  | **Sub-total (Central):** |  | **2570** | **200** |  |
|  | **State Sector** |  |  |  |  |  |
| 3 | Lower Sileru Extension /APGENCO) | Andhra Pradesh | U-1U-2 | 115115 | 0 | Mar'26Mar'26 |
| 4 | Lower Kopili /APGCL | Assam | U-1U-2 | 5555 | 0 | Sep'25Sep'25 |
| 5 | Kundah Pumped Storage(Phase-I, Phase-II & Phase-III) /TANGEDCO | Tamil Nadu | U-1U-2U-3 | 125125125 | 0 | Feb'26Feb'26Mar'26 |
|  |  | **Sub-total (State):** |  | **715** | **0** |  |
|  | **Private Sector** |  |  |  |  |  |
| 6 | Pinnapuram 4X240+2X120=1200 MW | Andhra Pradesh/M/s Greenko Energies Pvt. Ltd. | U-1U-2U-3U-4U-5U-6U-7U-8 | 240240240240120120240240 | 0 | May’25May’25May’25Jun’25Jun’25Jul’25Aug’25Sept’25 |
| 7 | Kutehr/JSW3x80=240MW | Himachal Pradesh | U-1U-2U-3 | 808080 |  | May’25May’25May’25 |
|  |  | **Sub-total (Private):** |  | **1920** | **0** |  |
| **Total (CS+SS+PS)** | **5205**  | **200** |  |