Hydro Capacity Addition Programme for 2026-27

| Sl. No. | Name of Project | State/ Implem. Agency | Unit No. | Capacity (MW) |  | Capacity Addition |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target | Actual | As Programmed/ Anticipated |
|  | Central Sector |  |  |  |  |  |
| 1 | SUBANSIRI LOWER HEP | Arunachal Pradesh/NHPC | U-4 to 8 | 1250 | 250 | Mar'2027 (U-4 Commissioned on 01 May’2026) |
| 2 | Rangit-IV HEP | Sikkim/NHPC | U-1 to 3 | 120 | 0 | Nov’2026 |
| 3 | Pakal Dul HEP | Jammu & Kashmir/CVPPL | U-1 to U-4 | 1000 | 0 | Mar'2027 |
| 4 | Kiru HEP | Jammu & Kashmir/CVPPL | U-1 to 4 | 624 | 0 | Mar'2027 |
| 5 | Dhaulasidh HEP | Himachal Pradesh/SJVN | U-1 to 2 | 66 | 0 | Mar'2027 |
| 6 | Tehri PSP | Uttarakhand/THDC | U-4 | 250 | 250 | Commissioned on 09 Apr’2026 |
|  |  | Sub- total (Central): |  | 3310 | 500 |  |
|  | State Sector |  |  |  |  |  |
| 1 | Lower Kopili HEP | Assam/APGCL | U-1 to 5 | 120 | 0 | Oct'2026 |
| 2 | Lower Sileru Extension HEP | Andhra Pradesh/ APGENCO | U-1 to 2 | 230 | 0 | Aug'2026 |
| 3 | Kundah PSP (Phase-I, Phase-II & Phase-III) | Tamil Nadu /TNGECL | U-1 to U-4 | 500 | 0 | Feb’2027 |
|  |  | Sub- Total (State): |  | 850 | 0 |  |
|  | Private Sector |  |  |  |  |  |
| 2 | Tidong-I HEP | Himachal Pradesh/JSW | U-1 to 3 | 150 | 50 | Sept'2026 (U-1 Commissioned on 08 May’2026) |
| 2 | MP30 Gandhi Sagar PSP (Greenko MP01 IREP Private Limited) | Madhya Pradesh/Greenko | U-1 to 9 | 1920 | 0 | Dec’2026 |
| 4 | Chitravathi PSP(M/s Adani Renewable Energy Forty-Two Limited) | Andhra Pradesh / Adani | U-1 to U-2 | 500 | 0 | Feb’2027 |
|  |  | Sub- Total (Private): |  | 2570 | 50 |  |
| Total (CS+SS+PS) |  |  |  | 6730 | 550 |  |