## Summary
Annexure-II
S. No. | States | Data sent to Bisag-N/Nodal Agency of states for mapping |  |  |  | If already sent, Data mapped on the portal | If data already mapped, whether verified | Remarks (if any)
|  | Existing | Under Construction | Under Planning | Target date
|  | (Yes/No/ Partial) | (Yes/No/ Partial) | (Yes/No/ Partial) | to send the complete data to BISAG-N | (Yes/No/Partial) | (Yes/No/Partial)
1 | AEGCL(Assam) | Yes | Partial | Partial | 2025-06-15 | Partial (80% is mapped) | No | Partial transmission data planned upto 2030 have been sent to Bisag-N through mail but the same have not been mapped in PMGS portal yet. Also, some correction/modifications to already mapped data have been sent to BISAG-N through mail but the same have not been reflected in the portal yet. Login credential required.
2 | APTRANSCO (Andhra Pradesh) | Yes | Partial | Partial | 2025-06-15 | Partial | Yes | Data is visible in the PM Gati Shakti Portal, but the following issues are observed in portal 1. Pop up not enabled to see the attribute data 2. Colour codes not as per the SOP communicated by the CEA to differentiate voltage wise data 3. Symbology is not as per the SOP communicated by the CEA to differentiate existing/under construction/under planning. These remarks were already communicated to Bisag-N.
3 | Arunachal Pradesh | Partial | Partial | Partial | 2025-06-15 | Partial | Partial | Partial transmission data has been sent to nodal agency APSAC (Arunachal Pradesh State Application Centre). Same is mapped but Login credential has been deactivated hence unsble to verify that data has been mapped correctly or not.
4 | CSPTCL (Chhattisgarh) | Yes | Partial | No | 2025-06-15 | Not available | No | Complete existing transmission network data and partial under construction data has been sent to BISAG-N. Remaining under construction data will be sent by 15th June 2025. Further approval of Capital investment plan (CIP) for FY 2025-26 (with vision plan for 2032) is under process from Chhattisgarh State Electricity Regulatory Commission (CSERC) and data for the same will be shared after the approval from regulator for further mapping on the Portal. Login ID & Password is required for verification of mapped data.
5 | GED (Goa) | Yes (existing assets data as on 31st Januray 2025 are sent) | Yes | Yes | 2025-05-31 | Yes (Complete existing, under construction and under planning upto 2032 transmission data are mapped on state portal "One Map Goa GIS ". The GEL (Goa Electronics Limited ) has integrated the One Map Goa GIS portal with PM gatishakti portal via the WFS link.) | Yes | The existing assets as on 31st Januray 2025) has been mapped on One Map Goa GIS portal . The data of existing network till April 2025 will be shared with GEL for updating on One Map Goa GIS portal on or before 31st may 2025. Login issue to access PM Gatishakti data, taken up with BISAG team to resolve the Login issue.
6 | GETCO (Gujarat) | Yes | No | No | 2025-06-15 | Yes | Yes | Data compilation for underconstruction and under planning is under process.
7 | HPPTCL (Himachal Pradesh) | Yes | No | No | 2025-06-15 | No | No | Only 20% of transmission data is with HPPTCL. Remaining 80% is with HPSEBL (Himachal Pradesh State Electricity Board Limited). Complete existing transmission data (of HPPTCL & HPSEBL) is sent to BISAG-N. Same is not mapped yet. Under construction and under planning data pertaining to HPPTCL will be sent by end of June 2025. For HPSEBL data, regular follow ups/meeting is being done and will be sent to BISAG-N after receiving the same from HPSEBL.
8 | HVPNL (Haryana) | Yes | Yes | Yes | Not applicable | HVPNL asset data of transmission line, tower and substation as on 31.12.2022 was updated on the PM Gati Shakti portal. | Yes | Complete data of existing, under construction and under planning network is sent to BISAG-N on 13th May 2025. HVPNL transmission asset data as on 31.12.2022 is mapped on portal. HVPNL is pursuing with BISAG-N for mapping of assets. Log-in credential not available.
9 | JUSNL (Jharkhand) | Partial | No | No | 2025-06-15 | No | No | Existing Substation data has been sent to BISAG-N. Existing Transmission line data is under compilation and will be sent within this week. Under construction and under planning data will be sent by 15th June 2025.
10 | KPTCL (Karnataka) | Partial | No | No | (i)Existing Line data: June 2025 (ii) U/C SS Data: June 2025 (iii) U/C Line data: September 2025 (iv) Under planning data: June 2025 | No | No | Existing Substation data of KPTCL has been sent on 13-05-2025 to BISAG-N. Existing Transmission Line data and under construction SS data will be sent by June 2025 as the Survey and Digitization is under progress. Request to furnish the Login credentials to KPTCL for validation. Note: As per KPTCL Cyber security policy, NDA shall be executed between KPTCL and receiving agency
11 | MPPTCL (Madhya Pradesh) | Yes | Yes | Yes | 100% Data already shared | Partial (Re-Structuring under process) | Partial (Re-Structuring under process) | Data is mapped on portal. Mapping of Restructuring/ modification of line is under process.
12 | MSETCL (Maharshtra) | Yes | Yes | Yes | 100% data shared | Yes | Yes | Data is visible in the PM Gati Shakti Portal. MSETCL have mapped the data and its symbology as per the NMP SOP. However, the following issues are observed in the portal : 1. Pop up not enabled to see the attribute data 2. Colour codes not as per the SOP communicated by the CEA to differentiate voltage wise data 3. Symbology is not as per the SOP communicated by the CEA to differentiate existing/under construction/bidding like wise 4. Creation of Log-in IDs for MSETCL users are requested time and again since almost six months; but no fruitful response to several reminders as well 5. Requirement of additional layer for STU data mapping is still not complied 6. Requirement of NOC mechanism is under process at BISAG even after passage of more than a year 7.MSETCL landing page requirement is still pending
13 | MePTCL (Meghalaya) | No | No | No | 30-06-2025 (Tentative) | - | - | Mapping and vetting of transmission infrastructure in process, and to be processed tentatively by 15/06/2025. Verification and final submission of 100% data to BISAG-N tentatively by 30/06/2025.
14 | Nagaland | Yes | Yes | Yes | NA | Log In Credentials not yet shared to check data availability. | - | Data of Generating Station, Transmission lines and Sub-Station with respect to Nagaland State shared with BISAG-N on 28.10.2024 and another reminder send on 20.22.2024 and 12.05.2025.
15 | OPTCL (Odisha) | Partial | No | No | 2025-06-15 | Yes | Yes | Partial existing transmission data is sent to BISAG-N. Same is mapped.
16 | PSTCL (Punjab) | Yes | No | No | 2025-06-15 | Partial | No, Login credential required for verification of data mapping | All existing data has been sent to Commerce & Industries Department who is the Nodal Department for Government of Punjab on Dt. 04.04.2025.
17 | RRVPNL (Rajasthan) | Partial (65%) | No | No | 2026-03-01 | Access to portal not provided |  | Partial existing transmission data is shared with BISAG-N. Tender is floated to hire an agency for collection and compilation of data. Complete data (existing, under construction and under planning) will be shared by March 2026.
18 | Sikkim | Partial (80%) | Partial | No |  | Credentials not yet shared to check data availability on portal |  | 80% of the Existing data has been shared to nodal agency. Further, partial under construction data is sent to nodal agency. Nodal agency of Sikkim informed that they are facing technical issue in uploading the data.
19 | TANTRANSCO (Tamil Nadu) | Yes (04.02.25) | No | No | 2025-06-30 | Credentials not yet shared to check data availability |  | Complete existing transmission network as on Dec 2024 has been shared to BISAG-N on 04-02-2025. No remarks received from BISAG-N.
20 | TGTRANSCO (Telangana) | Yes | Yes | Data Collection under process. To be submitted within week. |  | Yes | Yes | Total data has been mapped but the Voltage wise Symbology needs to be updated for Commissioned data (Substations and Towers) and Under construction data (Transmission Lines and Substations) on PM Gati Shakti SMP portal. These changes have already been communicated to BISAG-N.
21 | Tripura(TPTL) | Yes | Yes | Yes |  | No | No | All data regarding Transmission Lines & Sub-station (Existing, Under Construction & Under Planning/Proposed) under Tripura Power Transmission Limited(TPTL) in the form of Shape File sent to Bisag-N and Nodal Agency (Department of Industries & Commerce, Government of Tripura,) on 20th March, 2025 for uploading but yet not uploaded in the Portal.
22 | UPPTCL | Yes | No | No | 2025-06-01 | No | No | Complete existing transmission data as per SOP is sent to state nodal agency on 24th March 2025. Data of Under construction and vision plan for 2032 is under preparation and will be sent by June-2025. Log-in credential not available to check mapping of data.
UT''s
1 | Chandigarh | No | No | No | 2025-06-01 | No | No | Chandigarh Power Distribution Limited (CPDL) has taken over the Operations recently and therefore is starting to do the needful at the earliest please.
2 | DTL | Yes | No | No | 2025-06-01 | No | No | As per the information received from nodal agency GSDL (Geospatial Delhi Limited), exsisting network data has been shared with BISAG-N. Under construction and under planning data will be sent by June 2025. Log-in credential not available to check mapping of data.
3 | JKPTCL(Jammu) | Yes | No | Yes | 2025-06-01 | Partial | Partial | 85% data already mapped
4 | Pudducherry | No | No | No | 2025-06-01 | No | No | Data compilation under process.