## Conventional (hidden)
List of Conventional HE Candidate Projects till 2031-32
S.No. | Name of Project | State | River | River Basin | IC (MW) | Sector | Stage |  | Commisioning Year
Year - 2023-24 | [6 empty] | 1
1 | Pallivasal 2x30= 60 MW | Kerala/ KSEB Ltd. |  |  | 60 | State | Under Construction | Active | Mar'24
2 | Thottiyar 1x30+1x10= 40 MW | Kerala/ KSEB Ltd. |  |  | 40 | State | Under Construction | Active | Mar'24
| Total |  |  |  | 100 |  | 1
S.No. | Name of Project | State | River | River Basin | IC (MW) | Sector | Stage
Year - 2024-25 | [6 empty] | 1 | Active
1 | Parbati-II 4x200=800 MW | Himachal Pradesh/ NHPC |  |  | 800 | Central | Under Construction | Active | Sept'24
2 | Polavaram 12x80= 960 MW | Andhra Pradesh/ Polavaram Project Authority |  |  | 320 | State | Under Construction (U-1 to U-4) | Active | Mar'25
3 | Lower Kopili 2x55+2x2.5+1x5=120 MW | Assam/APGCL |  |  | 120 | State | Under Construction | Active | Mar'25
4 | Uhl-III 3x33.33=100 MW | Himachal Pradesh/ BVPCL |  |  | 100 | State | Under Construction | Active | Dec'24
5 | Tidong-I 3x50= 150 MW | Himachal Pradesh/M/s Statkraft India Pvt. Ltd. |  |  | 150 | Private | Under Construction | Active | Jun'24
| Total |  |  |  | 1490 |  | 1 | Active
S.No. | Name of Project | State | River | River Basin | IC (MW) | Sector | Stage | Active
Year - 2025-26 | [6 empty] | 1 | Active
1 | Rangit-IV 3x40= 120 MW | Sikkim/NHPC Ltd. |  |  | 120 | Central | Under Construction |  | May'25
2 | Parnai 3x12.5= 37.5 MW | Jammu & Kashmir/JKSPDC |  |  | 37.5 | State | Under Construction |  | Dec'25
3 | Kiru 4x156=624 MW | Jammu & Kashmir/CVPPL |  |  | 624 | Central | Under Construction | Active | Mar'26
4 | Subansiri Lower 8x250= 2000 MW | Arunachal Pradesh/NHPC |  |  | 2000 | Central | Under Construction | Active | Oct'25
5 | Luhri-I 2x80+2x25= 210MW | Himachal Pradesh/SJVN |  |  | 210 | Central | Under Construction | Active | Jan'26
6 | Dhaulasidh 2x33=66 MW | Himachal Pradesh/SJVN |  |  | 66 | Central | Under Construction | Active | Nov'25
7 | Polavaram 12x80= 960 MW | Andhra Pradesh/ Polavaram Project Authority |  |  | 640 | State | Under Construction (U-5 to U-12) |  | Mar'26
8 | Shahpurkandi 3x33+3x33+1x8= 206 MW | Punjab/Irr. Deptt. & PSPCL |  |  | 206 | State | Under Construction | Stalled | Oct'25
9 | Lower Sileru Extension (APGENCO) | Andhra Pradesh/ APGENCO |  |  | 230 | State | Under Construction |  | Mar'26
10 | Kutehr 3x80=240 MW | Himachal Pradesh/JSW Energy |  |  | 240 | Private | Under Construction |  | Nov'25
11 | Phata Byung 2X38=76 MW | Uttarakhand/ LANCO |  |  | 76 | Private | Under Construction (Stalled)
| Total |  |  |  | 4449.5 |  | 1 | Active
[7 empty] | 1 | Active
S.No. | Name of Project | State | River | River Basin | IC (MW) | Sector | Stage | Active
Year - 2026-27 | [6 empty] | 1 | Active
1 | Kwar 4x135=540 MW | Jammu & Kashmir/CVPPL |  |  | 540 | Central | Under Construction | Active | Nov'26
2 | Ratle 4x205+1x30= 850 MW | Jammu & Kashmir/ NHPC |  |  | 850 | Central | Under Construction | Active | May'26
3 | Rammam - III 3x40=120 MW | West Bengal/ NTPC Ltd. |  |  | 120 | Central | Under Construction |  | Sept'26
4 | Teesta- VI 4x125= 500 MW | Sikkim/NHPC |  |  | 500 | Central | Under Construction |  | Aug'26
5 | Pakal Dul 4x250= 1000 MW | Jammu & Kashmir/CVPPL |  |  | 1000 | Central | Under Construction |  | Sept'26
6 | Vishnugad Pipalkoti 4x111= 444 MW | Uttarakhand/THDC |  |  | 444 | Central | Under Construction | Stalled | Jun'26
7 | Shongtong Karcham 3x150= 450 MW | Himachal Pradesh/HPPCL |  |  | 450 | State | Under Construction |  | Nov'26
8 | Mankulam 2x20= 40 MW | Kerala/ KSEB Ltd. |  |  | 40 | State | Under Construction |  | May'26
9 | Lower Kalnai 2X24=48 MW | Jammu & Kashmir/JKSPDC |  |  | 48 | State | Under Construction (Stalled)
| Total |  |  |  | 3992 |  | 1
Year - 2027-28 | [6 empty] | 1
1 | Uri-I Stage-II | J & K | Jhelum | Jhelum | 240 | Central | Concurred |  | October'27
2 | New Ganderwal | J & K | Jhelum | Jhelum | 93 | State | Concurred |  | December'27
3 | Nafra | Arunachal Pradesh | Bichom (Kameng) | Kameng | 120 | Central | Concurred |  | March'28
4 | Deothal Chanju | Himachal Pradesh | Chanju nallah | Ravi | 30 | State | Concurred |  | January'28
5 | Sunni Dam 4x73+1x73+1x17=382 MW | Himachal Pradesh/SJVNL |  |  | 382 | Central | Under Construction |  | Mar'28
6 | Chanju-III 3x16= 48 MW | Himachal Pradesh/HPPCL |  |  | 48 | State | Under Construction |  | Jul'27
7 | Tangnu Romai 2X22=44 MW | Himachal Pradesh/TRPG |  |  | 44 | Private | Under Construction (Stalled)
8 | Maheshwar 10X40=400 MW | Madhya Pradesh/SMHPCL |  |  | 400 | Private | Under Construction (Stalled)
9 | Bhasmey 2X25.5=51 MW | Sikkim/Gati Infrastructure |  |  | 51 | Private | Under Construction (Stalled)
10 | Rangit-II 2X33=66 MW | Sikkim/Sikkim Hydro |  |  | 66 | Private | Under Construction (Stalled)
| Total |  |  |  | 1474 |  | 1
Year - 2028-29 | [6 empty] | 1
1 | Tato-I | Arunachal Pradesh | Yarjep | Siang | 186 | Private | Concurred |  | March'29
2 | Heo | Arunachal Pradesh | Yarjep | Siang | 240 | Private | Concurred |  | January'28
3 | Lakhwar Multipurpose Project (3x100=300 MW) | Uttarakhand/UJVNL |  |  | 300 | State | Under Construction |  | Oct'28
4 | Lata Tapovan 3X57=171 MW | Uttarakhand/NTPC |  |  | 171 | Central | Under Construction (Stalled)
5 | Tapovan Vishnugad 4x130=520 MW | Uttarakhand /NTPC |  |  | 520 | Central | Under Construction |  | Dec'28
6 | Panan 4X75=300 MW | Sikkim/Himagiri |  |  | 300 | Private | Under Construction (Stalled)
| Total |  |  |  | 1717 |  | 1
Year - 2029-30 | [6 empty] | 1
1 | Wah Umiam Stage-III (Mawphu stage-II) | Meghalaya |  |  | 85 | Central | Concurred |  | March'30
2 | Kirthai-II | J & K | Chenab | Chenab | 930 | Central | Concurred |  | October'29
3 | Dugar | Himachal Pradesh | Chenab | Chenab | 500 | Central | Concurred |  | July'29
4 | Tato-II | Arunachal Pradesh |  |  | 700 | Central | Concurred |  | February'30
5 | Turga | West Bengal |  |  | 1000 | State | Concurred |  | January'30
6 | Dulhasti Stage-II | J & K | Chenab | Chenab | 260 | Central | S&I |  | November'29
7 | Teesta Intermediate | West Bengal | Teesta | Teesta | 90 | State | S&I |  | December'29
| Total |  |  |  | 3565 |  | 1
|  | Sub-Total (2023-30) |  |  | 16787.5 |  | 1
Year - 2030-31 | [6 empty] | 1
1 | Etalin | Arunachal Pradesh |  |  | 3097 |  | Concurred |  | December'30
2 | Attunli | Arunachal Pradesh |  |  | 680 |  | Concurred |  | April'30
3 | Dikhu | Nagaland |  |  | 186 |  | Concurred |  | July'30
4 | Naying | Arunachal Pradesh |  |  | 1000 |  | Concurred |  | January'31
5 | Thana Plaun | Himachal Pradesh |  |  | 191 |  | Concurred |  | March'31
| Total |  |  |  | 5154 |  | 1
Year - 2031-32 | [6 empty] | 1
1 | Talong Londa | Arunachal Pradesh | Kameng | Kameng | 225 | Private | Concurred |  | August'31
2 | Teesta St-IV | Sikkim | Teesta | Teesta | 520 | Central | Concurred |  | January'32
3 | Demwe Lower | Arunachal Pradesh | Lohit | Luhit | 1750 | Private | Concurred |  | March'32
4 | Sawalkote | J & K | Chenab | Chenab | 1856 | Central | Concurred |  | November'31
5 | Dibang Multipurpose Project (NHPC) | Arunachal Pradesh |  |  | 2880 | Central | Under Construction |  | Feb'32
| Total |  |  |  | 7231 |  | 1
|  | Grand-Total (2023-32) |  |  | 29172.5 |  | 1

## PSP (hidden)
List of PSPs Candidate till 2031-32
S.No. | Name of Project | State | River | River Basin | IC (MW) | Type | Stage
Year - 2024-25
1 | Tehri PSS | Uttarakhand | Bhagirathi | Ganga | 1000 | PSP | Under Construction
2 | Pinnapuram | Andhra Pradesh | Pennar | Pennar | 1200 | PSP | Under Construction
| Total |  |  |  | 2200
Year - 2025-26
3 | Kundah PSP PhI,II & III | Tamilnadu | Kundah/Bhavani | Cauvery | 500 | PSP | Under Construction
| Total |  |  |  | 500
Year - 2026-27
4 | Shahpur | Rajasthan | UR-Off-Stream LR-Off-Stream |  | 1800 | PSP | S&I
5 | MP 30 Gandhi Sagar | Madhya Pradesh | LR-Chambal |  | 1920 | PSP | S&I
6 | Saundatti PSP | Karnataka | LR-Malaprabha |  | 1600 | PSP | S&I
7 | Sukhpura Off-Stream | Rajasthan | UR-Off-Stream LR-Off-Stream |  | 2560 | PSP | S&I
8 | Chitravathi | Andhra Pradesh | LR-Chitravathi |  | 500 | PSP | S&I
| Total |  |  |  | 8380
Year - 2027-28
9 | Koyna Left Bank | Maharashtra | Koyna | Krishna | 80 | PSP | Under Construction (Stalled)
10 | Sirohi | Rajasthan | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1200 | PSP | S&I
11 | Gandikota | Andhra Pradesh | LR- Penna river |  | 1000 | PSP | S&I
12 | Singanamala | Andhra Pradesh | Off-River Closed Loop |  | 800 | PSP | S&I
| Total |  |  |  | 3080
Year - 2028-29
13 | Upper Sileru | Andhra Pradesh | Sileru | Godavari | 1350 | PSP | Concurred
| Total |  |  |  | 1350
Year - 2029-30
14 | Turga | West Bengal | Subarnarekha |  | 1000 | PSP | Concurred
15 | Somasila | Andhra Pradesh | UR-Off-Stream LR-Off-Stream |  | 900 | PSP | S&I
16 | OWK | Andhra Pradesh | UR-Off-Stream LR- Penna river |  | 800 | PSP | S&I
17 | Upper Indravati | Odisha | Indravati |  | 600 | PSP | S&I
| Total |  |  |  | 3300
|  | Sub-total (2023-30) |  |  | 18810
Year - 2030-31
18 | Upper Kolab | Odisha | Kolab |  | 320 | PSP | S&I
19 | Sharavathy PSP | Karnataka | Sharavathy |  | 2000 | PSP | S&I
20 | Lugu Pahar | Jharkhand | UR- Kairo Jharna Nala, LR across bokaro river |  | 1500 | PSP | S&I
21 | Shirwata | Maharashtra | LR-Shirvata |  | 1800 | PSP | S&I
22 | Indira Sagar Omkareshwar | Madhya Pradesh | UR-ISP Reservoirr, LR-Omkareshwar Power Station reservior |  | 525 | PSP | S&I
23 | Narihalla | Karnataka | UR-proposed on minor rivulet draining into Narihalla Reservoir , LR- as Narihalla Reservoir existing on Narihalla River |  | 300 | PSP | S&I
24 | Bhavali | Maharashtra | UR-downstream of Bhavali Dam LR-Ulhas |  | 1500 | PSP | S&I
25 | Raiwada | Andhra Pradesh | UR-on a tabletop hill across a minor rivulet draining into a nallah , LR- across Sarada river |  | 850 | PSP | S&I
26 | Paidipalem East | Andhra Pradesh | LR - new proposed draws water Paidipalem Balancing reservoir |  | 1200 | PSP | S&I
27 | Paidipalem North | Andhra Pradesh | LR - new proposed draws water Paidipalem Balancing reservoir |  | 1000 | PSP | S&I
28 | Patgaon | Maharashtra | UR-existing Patgaon reservoir LR-on a nallah/ tributary of River Karli |  | 2100 | PSP | S&I
29 | Tarali | Maharashtra | LR- Existing Tarali reservior |  | 1500 | PSP | S&I
30 | Malshej Ghat Bhorande | Maharashtra | UR-on Minor nallah draining into Kukadi river LR-on Minor nallah draining Into Kalu river |  | 1500 | PSP | S&I
| Total |  |  |  | 16095
Year - 2031-32
31 | Balimela PSP | Odisha | LR- Karika Jhora stream, UR - Existing Reviservior |  | 500 | PSP | S&I
32 | UP01 | Uttar Pradesh | Off-Stream LR-Off Stream |  | 3660 | PSP | S&I
33 | Vempalli | Andhra Pradesh | Off-Stream LR-Off Stream |  | 1500 | PSP | S&I
34 | Kandhaura | Uttar Pradesh | Off-Stream LR-Off Stream |  | 1680 | PSP | S&I
| Total |  |  |  | 7340
42245

## PSP (New) (2)
Capacity Addition Plan of PSPs till 2031-32
S.No. | Name of Project | State | River | IC (MW) | Developer | Commissioning Year as per developer | Commissioning Year as per developer | Stage
Year - 2024-25
1 | Tehri PSS | Uttarakhand | Bhagirathi | 1000 | THDC |  |  | Under Construction
2 | Pinnapuram | Andhra Pradesh | Pennar | 1200 | Greenko |  |  | Under Construction
| Total |  |  | 2200
Year - 2025-26
3 | Kundah PSP PhI,II & III | Tamilnadu | Kundah/Bhavani | 500 | TANGEDCO |  |  | Under Construction
| Total |  |  | 500
2026-27
4 | Chitravathi | Andhra Pradesh |  | 500 | Adani Green | 2026-27 | Jun'26 | S&I
5 | MP 30 Gandhi Sagar | Madhya Pradesh | LR-Chambal | 1920 | Greenko | 2026-27 | Aug'26 | S&I
| sub total |  |  | 2420
2027-28
6 | Gandikota | Andhra Pradesh | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 1000 | Adani Green | 2027-28 | Mar'28 | S&I
7 | Tarali | Maharastra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 1500 | Adani Green | 2027-28 | Mar'28 | S&I
8 | Saundatii | Karnataka |  | 1600 | Greenko | 2027-28 | Mar'28 | S&I
9 | Shahpur | Rajasthan |  | 1800 | Greenko | 2027-28 | Jan'28 | S&I
10 | Bhivpuri | Maharashtra |  | 1000 | Tata Power | 2027-28 | Mar'28 | S&I
11 | Kandhaura | Uttar Pradesh | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 1680 | JSW Energy | 2027-28 | Mar'28 | S&I
12 | Narihalla | Karnataka | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 300 | JSW Energy | 2027-28 | Dec'27 | S&I | 0
13 | Veeraballi | Andhra Pradesh |  | 1800 | Astha energy | 2027-28 | Nov'27 | S&I
| sub total |  |  | 10680
2028-29
14 | Upper Sileru | Andhra Pradesh | Sileru | 1350 | APGENCO |  |  | Concurred
15 | Koyna Nivakane | Maharashtra |  | 2700 | Adani Green | 2028-29 | Jul'28 | S&I
16 | UP01 | Uttar Pradesh |  | 3660 | Greenko | 2028-29 | Mar'29 | S&I
17 | Shirawta | Maharashtra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 1800 | Tata Power | 2028-29 | Sep'28 | S&I
18 | Sirohi | Rajasthan | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 1200 | JSW Energy | 2028-29 | Jul'28 | S&I
19 | Bhavali | Maharashtra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 1500 | JSW Energy | 2028-29 | Jun'28 | S&I
20 | Pane | Maharashtra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 1500 | JSW Energy | 2028-29 | Jan'29 | S&I
| sub total |  |  | 13710
2029-30
21 | Turga | West Bengal | Subarnarekha | 1000 | WBSEDCL |  |  | Concurred
22 | Malshejghat Bhorende | Maharastra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 1500 | Adani Green | 2029-30 | Jul'29 | S&I
23 | Sukhpura | Rajasthan |  | 2560 | Greenko | 2029-30 | Dec'29 | S&I
24 | Vempalli | Andhra Pradesh | Kolab | 1500 | JSW energy | 2029-30 | Jun'29 | S&I
25 | Kamalapadu | Andhra Pradesh |  | 950 | APGENCO | 2029-30 | Jul'29 | S&I
26 | Singanamala | Andhra Pradesh |  | 800 | Aurobindo Realty & Infrastructure | 2029-30 | Mar'30 | S&I
27 | Owk | Andhra Pradesh | Subarnarekha | 800 | Aurobindo Realty & Infrastructure | 2029-30 | Mar'30 | S&I
28 | Paidipalem North | Andhra Pradesh |  | 1000 | Indosol Solar Power | 2029-30 | Jun'29 | S&I
29 | Musakhand | Uttar Pradesh | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 600 | ACME | 2029-30 | Apr'29 | S&I
30 | Warasgaon Warangi | Maharastra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 1500 | Adani Green | 2029-30 | Jul'29 | S&I
31 | Paidipalem East | Andhra Pradesh |  | 1200 | Indosol Solar Power | 2029-30 | Jun'29 | S&I
| sub total |  |  | 13410
2030-31
32 | Raiwada | Andhra Pradesh | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 900 | Adani Green | 2030-31 | Jun'30 | S&I
33 | Somasila | Andhra Pradesh | Subarnarekha | 900 | Shirdi Sai Electrical | 2030-31 | May'30 | S&I
34 | Sharavathy | Karnataka | Subarnarekha | 2000 | KPCL | 2030-31 | April'30 | S&I
35 | Indira Sagar | Madhya Pradesh |  | 640 | NHDC/NHPC | 2030-31 | Mar'31 | S&I
36 | Savitri | Maharashtra |  | 1800 | NHPC | 2030-31 | Mar'31 | S&I
37 | Upper Indravati | Odisha | Subarnarekha | 600 | OHPC | 2030-31 | Mar'31 | S&I
| sub total |  |  | 6840
2031-32
38 | Yaganti | Andhra Pradesh | Subarnarekha | 1000 | APGENCO | 2031-32 | Nov'31 | S&I
| sub total |  |  | 1000
| Total (till 2031-32) |  |  | 50760

## year wise Summary
Year | Previous Year Wise Capacity Addition |  | Revised Year Wise Capacity Addition
| No. Projects | Capacity Addition (MW) | No. Projects | Capacity Addition (MW)
2024-25 | 2 | 2200 | 2 | 2200
2025-26 | 1 | 500 | 1 | 500
2026-27 | 5 | 8380 | 2 | 2420
2027-28 | 4 | 3080 | 9 | 10680
2028-29 | 1 | 1350 | 7 | 13710
2029-30 | 4 | 3300 | 11 | 13410
2030-31 | 13 | 16095 | 6 | 6840
2031-32 | 4 | 7340 | 1 | 1000
Total | 34 | 42245 | 39 | 50760

## Quarter wise DPR submission
Quarter wise DPR preparation
| Year | Quarter | No. of projects | IC (MW)
| 2023-24 | Q4 | 2 | 2420
| 2024-25 | Q1 | 4 | 7280
|  | Q2 | 10 | 10000
|  | Q3 | 7 | 8640
|  | Q4 | 6 | 12520
| 2025-26 | Q1 | 1 | 900
|  | Q2 | 4 | 5270
|  | Q3 | 7 | 6820

## PSP (New) (hidden)
List of PSPs Candidate till 2031-32
S.No. | Name of Project | State | River | River Basin | IC (MW) | Type | Developer | Stage | Commissioning Year as per CEA | Commissioning Year as per developer | Layout Finalization | Site Investigations
Year - 2024-25
1 | Tehri PSS | Uttarakhand | Bhagirathi | Ganga | 1000 | PSP |  | Under Construction | Oct'24
2 | Pinnapuram | Andhra Pradesh | Pennar | Pennar | 1200 | PSP |  | Under Construction | Dec'24
| Total |  |  |  | 2200
Year - 2025-26
3 | Kundah PSP PhI,II & III | Tamilnadu | Kundah/Bhavani | Cauvery | 500 | PSP |  | Under Construction | Jul'25
| Total |  |  |  | 500
1 | MP 30 Gandhi Sagar | Madhya Pradesh | LR-Chambal |  | 1920 | PSP | Geenko | S&I | 2028-12-01 | 2026-27 | Finalised | completed
4 | Koyna Left Bank | Maharashtra | Koyna | Krishna | 80 | PSP |  | Under Construction (Stalled)
2 | Chitravathi | Andhra Pradesh | LR-Chitravathi |  | 500 | PSP | Adani Green | S&I | March'28 | 2026-27 | Finalised | completed
3 | Kandhaura | Uttar Pradesh | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1680 | PSP | JSW Energy | S&I | June'28 | 2027-2028 |  | In process
4 | Narihalla | Karnataka | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 300 | PSP | JSW Energy | S&I | September'28 | 2027-2028
5 | Gandikota | Andhra Pradesh | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1000 | PSP | Adani Green | S&I | February'29 | 2027-2028 | Finalised | completed
6 | Tarali | Maharastra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1500 | PSP | Adani Green | S&I | October'28 | 2027-2028 | Finalised | completed
7 | Raiwada | Andhra Pradesh | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 900 | PSP | Adani Green | S&I | March'29 | 2027-2028 | Finalised | In process
8 | Bhivpuri | Maharashtra |  |  | 1000 |  | Tata Power | S&I | July'28 | 2027-2028 | Finalised | In process
9 | Saundatii | Karnataka |  |  | 1600 |  | Tata Power | S&I | April'28 | 2027-2028 |  | In process
10 | Shahpur | Rajasthan |  |  | 1800 |  | Greenko | S&I | May'28 | 2027-2028 | Finalised | completed
11 | Veeraballi | Andhra Pradesh |  |  | 1800 |  | WBSEDL | S&I | May'28 | 2027-2028 | Finalised | In process
14 | Malshejghat Bhorende | Maharastra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1500 | PSP | Adani Green | S&I | June'29 | 2027-2028
15 | Warasgaon Warangi | Maharastra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1500 | PSP | Adani Green | S&I | February'30 | 2027-2028
12 | Musakhand | Uttar Pradesh | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 600 | PSP | ACME | S&I | February'30 | 2028-2029
13 | Upper Sileru | Andhra Pradesh | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1350 | PSP | APGENCO | Concurred | June'28 | 2028-2029
13 | Sirohi | Rajasthan | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1200 | PSP | JSW Energy | S&I | April'29 | 2028-2029
14 | Bhavali | Maharashtra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1500 | PSP | JSW Energy | S&I | July'29 | 2028-2029 | Finalised | 90% completed
15 | Pane | Maharashtra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1500 | PSP | JSW Energy | S&I | January'30 | 2028-2029 | Finalised | In process
16 | Shirawta | Maharashtra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1800 | PSP | Tata Power | S&I | August'29 | 2028-2029 | Finalised | In process
17 | UP01 | Uttar Pradesh |  |  | 3660 |  | Greenko | S&I | February'30 | 2028-2029 |  | In process
18 | Sukhpura | Rajasthan |  |  | 2560 |  | Greenko | S&I | May'29 | 2028-2029 | Finalised | completed
19 | Singanamala | Andhra Pradesh |  |  | 800 |  | Aurobindo Realty & Infrastructure Pvt. Ltd. | S&I | March'30 | 2028-2029 | Finalised | In process
20 | Paidipalem East | Andhra Pradesh |  |  | 1200 |  | Indosol Solar Power Pvt. Ltd. | S&I | February'31 | 2028-2029
21 | Paidipalem North | Andhra Pradesh |  |  | 1000 |  | Indosol Solar Power Pvt. Ltd. | S&I | January'31 | 2028-2029
22 | Kamalapadu | Andhra Pradesh |  |  | 950 |  | APGENCO | S&I | May'31 | 2028-2029 | Finalised | In process
22 | Sharavathy | Karnataka | Subarnarekha |  | 2000 | PSP | KPCL | S&I | April'30 | 2029-2030 | Finalised | completed
23 | Upper Indravati | Odisha | Subarnarekha |  | 600 | PSP | OHPC | S&I | March'31 | 2029-2030 | Finalised | 70% completed
24 | Turga | West Bengal | Subarnarekha |  | 1000 | PSP | APGENCO | Concurred | May'30 | 2029-2030
25 | Owk | Andhra Pradesh | Subarnarekha |  | 800 | PSP | Aurobindo Realty & Infrastructure Pvt. Ltd. | S&I | November'30 | 2029-2030
26 | Somasila | Andhra Pradesh | Subarnarekha |  | 900 | PSP | Shirdi Sai Electricals Ltd. | S&I | August'30 | 2029-2030 | Finalised | In process
27 | Yaganti | Andhra Pradesh | Subarnarekha |  | 1000 | PSP | APGENCO | S&I | November'31 | 2029-2030
28 | Vempalli | Andhra Pradesh | Kolab |  | 1500 | PSP | JSW energy | S&I | July'31 | 2030-2031 | Finalised | In process
29 | Gujjili | Andhra Pradesh | Kolab |  | 1400 | PSP | NREDCAP | S&I | October'31 | 2030-2031
30 | Chittamavalasa | Andhra Pradesh | Kolab |  | 800 | PSP | NREDCAP | S&I | January'32 | 2030-2031
35 | Indira Sagar | Madhya Pradesh |  |  | 640 |  | NHDC | S&I |  | 2030-2031
30 | Upper Kolab | Odisha | LR- Karika Jhora stream, UR - Existing Reviservior |  | 320 | PSP | OHPC | S&I | June'32 | 2031-2032
31 | Balimela | Odisha | LR- Karika Jhora stream, UR - Existing Reviservior |  | 500 | PSP | OHPC | S&I | February'32 | 2031-2032
Year - 2027-28
| Total |  |  |  | 820
Year - 2028-29
| Total |  |  |  | 6980
Year - 2029-30
| Total |  |  |  | 12960
Year - 2030-31
| Total |  |  |  | 20760
|  | Sub-total (2023-30) |  |  | 24960
Year - 2031-32
| Total |  |  |  | 24960
Year - 2032-33
| Total |  |  |  | 70680
Beyond Year - 2032-33
36 | Savitri | Maharashtra |  |  | 1800 |  | NHPC | S&I
37 | Koyna Nivakane | Maharashtra |  |  | 2700 |  | Adani Green | S&I
38 | Aravetipalli | Andhra Pradesh |  |  | 1320 |  | APSPCL | S&I
39 | Rayavaram | Andhra Pradesh |  |  | 1500 |  | NREDCAP | S&I
40 | Gadikota | Andhra Pradesh |  |  | 1200 |  | NREDCAP | S&I
41 | Sillahalla St-I | Tamil Nadu |  |  | 1000 |  | TANGEDCO | S&I
| Total |  |  |  | 9520
| Grand Total |  |  |  | 53800

## Rough (hidden)
List of PSPs Candidate till 2031-32
[11 empty] | Rough copy | Capacity
S.No. | Name of Project | State | River | IC (MW) | Developer | Expected DPR Submission Date | Commissioning Year as per developer | Commissioning Year as per developer | Layout Finalization | Site Investigations | 2026-27 | 2420
2026-27 | [10 empty] | 2027-28 | 10680
1 | Chitravathi | Andhra Pradesh |  | 500 | Adani Green | Jul'24 | 2026-27 | Jun'26 |  |  | 2028-29 | 13560
2 | MP 30 Gandhi Sagar | Madhya Pradesh | LR-Chambal | 1920 | Greenko | Mar'24 | 2026-27 | Aug'26 | Finalised | completed | Project name | Installed capacity
2027-28 | [10 empty] | Chitravathi | 500
3 | Gandikota | Andhra Pradesh | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 1000 | Adani Green | Aug'24 | 2027-28 | Mar'28 | Finalised | completed | MP 30 Gandhi Sagar | 1920
4 | Tarali | Maharastra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 1500 | Adani Green | Nov'24 | 2027-28 | Mar'28 | Finalised | completed | sub total | 2420
5 | Saundatii | Karnataka |  | 1600 | Greenko | Nov'24 | 2027-28 | Mar'28 |  | In process | Gandikota | 1000
6 | Shahpur | Rajasthan |  | 1800 | Greenko | Sep'24 | 2027-28 | Jan'28 | Finalised | completed | Tarali | 1500
7 | Bhivpuri | Maharashtra |  | 1000 | Tata Power | Apr'24 | 2027-28 | Mar'28 | Finalised | In process | Saundatii | 1600
8 | Kandhaura | Uttar Pradesh | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 1680 | JSW Energy | May'24 | 2027-28 | Mar'28 |  | In process | Shahpur | 1800
9 | Narihalla | Karnataka | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 300 | JSW Energy | Sep'24 | 2027-28 | Dec'27 |  |  | Bhivpuri | 1000
10 | Veeraballi | Andhra Pradesh |  | 1800 | Astha energy | May'24 | 2027-28 | Nov'27 | Finalised | In process | Kandhaura | 1680
2028-29 | [10 empty] | Narihalla | 300
11 | Koyna Nivakane | Maharashtra |  | 2700 | Adani Green | Dec'24 | 2028-29 | Jul'28 |  |  | Veeraballi | 1800
12 | UP01 | Uttar Pradesh |  | 3660 | Greenko | Mar'25 | 2028-29 | Mar'29 |  | In process |  | 10680
13 | Shirawta | Maharashtra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 1800 | Tata Power | May'24 | 2028-29 | Sep'28 | Finalised | In process | Koyna Nivakane | 2700
14 | Sirohi | Rajasthan | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 1200 | JSW Energy | Aug'24 | 2028-29 | Jul'28 |  |  | UP01 | 3660
15 | Bhavali | Maharashtra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 1500 | JSW Energy | Apr'24 | 2028-29 | Jun'28 | Finalised | 90% completed | Shirawta | 1800
16 | Pane | Maharashtra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 1500 | JSW Energy | Jul'24 | 2028-29 | Jan'29 | Finalised | In process | Sirohi | 1200
17 | Paidipalem East | Andhra Pradesh |  | 1200 | Indosol Solar Power Pvt. Ltd. | Sep'24 | 2028-29 | Jun'29 |  |  | Bhavali | 1500
2029-30 | [10 empty] | Pane | 1500
18 | Malshejghat Bhorende | Maharastra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 1500 | Adani Green | Mar'25 | 2029-30 | Jul'29 |  |  | Paidipalem East | 1200
19 | Sukhpura | Rajasthan |  | 2560 | Greenko | Mar'25 | 2029-30 | Dec'29 | Finalised | completed |  | 13560
20 | Vempalli | Andhra Pradesh | Kolab | 1500 | JSW energy | Mar'25 | 2029-30 | Jun'29 | Finalised | In process | Malshejghat Bhorende | 1500
21 | Kamalapadu | Andhra Pradesh |  | 950 | APGENCO | Jul'25 | 2029-30 | Jul'29 | Finalised | In process | Sukhpura | 2560
22 | Singanamala | Andhra Pradesh |  | 800 | Aurobindo Realty & Infrastructure Pvt. Ltd. | Nov'24 | 2029-30 | Mar'30 | Finalised | In process | Vempalli | 1500
23 | Owk | Andhra Pradesh | Subarnarekha | 800 | Aurobindo Realty & Infrastructure Pvt. Ltd. | Oct'24 | 2029-30 | Mar'30 |  |  | Kamalapadu | 950
24 | Paidipalem North | Andhra Pradesh |  | 1000 | Indosol Solar Power Pvt. Ltd. | Sep'24 | 2029-30 | Jun'29 |  |  | Singanamala | 800
25 | Musakhand | Uttar Pradesh | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 600 | ACME | Oct'24 | 2029-30 | Apr'29 |  |  | Owk | 800
26 | Warasgaon Warangi | Maharastra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 1500 | Adani Green | Mar'25 | 2029-30 | Jul'29 |  |  | Paidipalem North | 1000
2030-31 | [10 empty] | Musakhand | 600
27 | Raiwada | Andhra Pradesh | LR-Silli Nallah, tributary of Sipu river in West Banas Basin | 900 | Adani Green | Jun'25 | 2030-31 | Jun'30 | Finalised | In process | Warasgaon Warangi | 1500
28 | Somasila | Andhra Pradesh | Subarnarekha | 900 | Shirdi Sai Electricals Ltd. | Jul'24 | 2030-31 | May'30 | Finalised | In process |  | 11210
29 | Sharavathy | Karnataka | Subarnarekha | 2000 | KPCL | Jul'25 | 2030-31 | April'30 | Finalised | completed | Raiwada | 900
30 | Indira Sagar | Madhya Pradesh |  | 640 | NHDC/NHPC | Nov'24 | 2030-31 | Mar'31 |  |  | Somasila | 900
31 | Savitri | Maharashtra |  | 1800 | NHPC | Mar'25 | 2030-31 | Mar'31 |  |  | Sharavathy | 2000
32 | Upper Indravati | Odisha | Subarnarekha | 600 | OHPC | Jul'24 | 2030-31 | Mar'31 | Finalised | 70% completed | Indira Sagar | 640
2031-32 | [10 empty] | Savitri | 1800
33 | Yaganti | Andhra Pradesh | Subarnarekha | 1000 | APGENCO | Jul'25 | 2031-32 | Nov'31 |  |  | Upper Indravati | 600
2032-33 | [11 empty] | 6840
34 | Aravetipalli | Andhra Pradesh |  | 1320 | APSPCL | Jul'25 | 2032-33 | Nov'32 |  |  | Yaganti | 1000
35 | Upper Kolab | Odisha | LR- Karika Jhora stream, UR - Existing Reviservior | 320 | OHPC | Dec'25 | 2032-33 | Jun'32 |  |  |  | 1000
36 | Balimela | Odisha | LR- Karika Jhora stream, UR - Existing Reviservior | 500 | OHPC | Dec'25 | 2032-33 | Jun'32 |  |  | Aravetipalli | 1320
37 | Sillahalla St-I | Tamil Nadu |  | 1000 | TANGEDCO | Dec'25 | 2032-33 | Jul'32 |  |  | Upper Kolab | 320
38 | Gujjili | Andhra Pradesh | Kolab | 1400 | NREDCAP | Dec'25 | 2032-33 | Jul'32 |  |  | Balimela | 500
39 | Chittamavalasa | Andhra Pradesh | Kolab | 800 | NREDCAP | Dec'25 | 2032-33 | Jul'32 |  |  | Sillahalla St-I | 1000
40 | Rayavaram | Andhra Pradesh |  | 1500 | NREDCAP | Dec'25 | 2032-33 | Jul'32 |  |  | Gujjili | 1400
41 | Gadikota | Andhra Pradesh |  | 1200 | APGENCO | Dec'25 | 2032-33 | Jul'32 |  |  | Chittamavalasa | 800
[11 empty] | Rayavaram | 1500
| Total | [9 empty] | Gadikota | 1200
8040
[11 empty] | Grand total | 53750

## Combined (hidden)
List of Conventional HE Candidate Projects till 2031-32
S.No. | Name of Project | State | River | River Basin | IC (MW) | Type | Stage |  | Commisioning date
Year - 2023-24 | [6 empty] | 1
1 | Pallivasal 2x30= 60 MW | Kerala/ KSEB Ltd. |  |  | 60 |  | U-1 to U-2 | Active | Mar'24
2 | Thottiyar 1x30+1x10= 40 MW | Kerala/ KSEB Ltd. |  |  | 40 |  | U-1 to U-2 | Active | Mar'24
| Total |  |  |  | 100 |  | 1
S.No. | Name of Project | State | River | River Basin | IC (MW) | Type | Stage
Year - 2024-25 | [6 empty] | 1 | Active
1 | Parbati-II 4x200=800 MW | Himachal Pradesh/ NHPC |  |  | 800 |  | U-1 to U-4 | Active | 22.05.2014
2 | Polavaram 12x80= 960 MW | Andhra Pradesh/ Polavaram Project Authority |  |  | 320 |  | U-1 to U-4 | Active | Mar'26
3 | Lower Kopili 2x55+2x2.5+1x5=120 MW | Assam/APGCL |  |  | 120 |  | U-1 to U-5 | Active | Mar'25
4 | Uhl-III 3x33.33=100 MW | Himachal Pradesh/ BVPCL |  |  | 100 |  | U-1 to U-3 | Active | Dec'24
5 | Tidong-I 3x50= 150 MW | Himachal Pradesh/M/s Statkraft India Pvt. Ltd. |  |  | 150 |  | U-1 to U-3 | Active | Jun'24
6 | Tehri PSS | Uttarakhand | Bhagirathi | Ganga | 1000 | PSP | Under Construction |  | Oct'24
7 | Pinnapuram | Andhra Pradesh | Pennar | Pennar | 1200 | PSP | Under Construction |  | Dec'24
| Total |  |  |  | 3690 |  | 1 | Active
S.No. | Name of Project | State | River | River Basin | IC (MW) | Type | Stage | Active
Year - 2025-26 | [6 empty] | 1 | Active
1 | Rangit-IV 3x40= 120 MW | Sikkim/NHPC Ltd. |  |  | 120 |  | U-1 to U-3 |  | May'25
2 | Parnai 3x12.5= 37.5 MW | Jammu & Kashmir/JKSPDC |  |  | 37.5 |  | U-1 to U-3 |  | Dec'25
3 | Kiru 4x156=624 MW | Jammu & Kashmir/CVPPL |  |  | 624 |  | U-1 to U-4 | Active | Mar'26
4 | Subansiri Lower 8x250= 2000 MW | Arunachal Pradesh/NHPC |  |  | 2000 |  | U-1 to U-8 | Active | Oct'25
5 | Luhri-I 2x80+2x25= 210MW | Himachal Pradesh/SJVN |  |  | 210 |  | U-1 to U-4 | Active | Jan'26
6 | Dhaulasidh 2x33=66 MW | Himachal Pradesh/SJVN |  |  | 66 |  | U-1 to U-2 | Active | Nov'25
7 | Polavaram 12x80= 960 MW | Andhra Pradesh/ Polavaram Project Authority |  |  | 640 |  | U-5 to U-12 |  | Mar'26
8 | Shahpurkandi 3x33+3x33+1x8= 206 MW | Punjab/Irr. Deptt. & PSPCL |  |  | 206 |  | U-1 to U-7 | Stalled | Oct'25
9 | Lower Sileru Extension (APGENCO) | Andhra Pradesh/ APGENCO |  |  | 230 |  | U-1 to U-2 |  | Mar'26
10 | Kutehr 3x80=240 MW | Himachal Pradesh/JSW Energy |  |  | 240 |  | U-1 to U-3 |  | Nov'25
11 | Phata Byung 2X38=76 MW | Uttarakhand/ LANCO |  |  | 76 |  | U-1 to U-2 (Stalled)
12 | Kundah PSP PhI,II & III | Tamilnadu | Kundah/Bhavani | Cauvery | 500 | PSP | Under Construction |  | Jul'25
| Total |  |  |  | 4949.5 |  | 1 | Active
[7 empty] | 1 | Active
S.No. | Name of Project | State | River | River Basin | IC (MW) | Type | Stage | Active
Year - 2026-27 | [6 empty] | 1 | Active
1 | Kwar 4x135=540 MW | Jammu & Kashmir/CVPPL |  |  | 540 |  | U-1 to U-4 | Active | Nov'26
2 | Ratle 4x205+1x30= 850 MW | Jammu & Kashmir/ NHPC |  |  | 850 |  | U-1 to U-5 | Active | May'26
3 | Rammam - III 3x40=120 MW | West Bengal/ NTPC Ltd. |  |  | 120 |  | U-1 to U-3 |  | Sept'26
4 | Teesta- VI 4x125= 500 MW | Sikkim/NHPC |  |  | 500 |  | U-1 to U-4 |  | Aug'26
5 | Pakal Dul 4x250= 1000 MW | Jammu & Kashmir/CVPPL |  |  | 1000 |  | U-1 to U-4 |  | Sept'26)
6 | Vishnugad Pipalkoti 4x111= 444 MW | Uttarakhand/THDC |  |  | 444 |  | U-1 to U-4 | Stalled | Jun'26
7 | Shongtong Karcham 3x150= 450 MW | Himachal Pradesh/HPPCL |  |  | 450 |  | U-1 to U-3 |  | Nov'26
8 | Mankulam 2x20= 40 MW | Kerala/ KSEB Ltd. |  |  | 40 |  | U-1 to U-2 |  | May'26
9 | Lower Kalnai 2X24=48 MW | Jammu & Kashmir/JKSPDC |  |  | 48 |  | U-1 to U-2 (Stalled)
| Total |  |  |  | 3992 |  | 1
Year - 2027-28 | [6 empty] | 1
1 | Uri-I Stage-II | J & K | Jhelum | Jhelum | 240 | RoR | Concurred |  | October'27
2 | New Ganderwal | J & K | Jhelum | Jhelum | 93 | RoR | Concurred |  | December'27
3 | Nafra | Arunachal Pradesh | Bichom (Kameng) | Kameng | 120 | ROR | Concurred |  | March'28
4 | Deothal Chanju | Himachal Pradesh | Chanju nallah | Ravi | 30 | RoR | Concurred |  | January'28
5 | Sunni Dam 4x73+1x73+1x17=382 MW | Himachal Pradesh/SJVNL |  |  | 382 |  | U-1 to U-6 |  | Mar'28
6 | Chanju-III 3x16= 48 MW | Himachal Pradesh/HPPCL |  |  | 48 |  | U-1 to U-3 |  | Jul'27
7 | Tangnu Romai 2X22=44 MW | Himachal Pradesh/TRPG |  |  | 44 |  | U-1 to U-2 (Stalled)
8 | Maheshwar 10X40=400 MW | Madhya Pradesh/SMHPCL |  |  | 400 |  | U-1 to U-10 (Stalled)
9 | Bhasmey 2X25.5=51 MW | Sikkim/Gati Infrastructure |  |  | 51 |  | U-1 to U-2 (Stalled)
10 | Rangit-II 2X33=66 MW | Sikkim/Sikkim Hydro |  |  | 66 |  | U-1 to U-2 (Stalled) |  | May'25
11 | MP 30 Gandhi Sagar | Madhya Pradesh | LR-Chambal |  | 1920 | PSP | S&I |  | 2029-12-01
12 | Chitravathi | Andhra Pradesh | LR-Chitravathi |  | 500 | PSP | S&I |  | 2028-10-01
13 | Koyna Left Bank | Maharashtra | Koyna | Krishna | 80 | PSP | Under Construction (Stalled)
| Total |  |  |  | 3974 |  | 1
Year - 2028-29 | [6 empty] | 1
1 | Tato-I | Arunachal Pradesh | Yarjep | Siang | 186 | ROR | Concurred |  | March
2 | Heo | Arunachal Pradesh | Yarjep | Siang | 240 | ROR | Concurred |  | Jan
3 | Lakhwar Multipurpose Project (3x100=300 MW) | Uttarakhand/UJVNL |  |  | 300 |  | U-1 to U-3 |  | Oct'28
4 | Lata Tapovan 3X57=171 MW | Uttarakhand/NTPC |  |  | 171 |  | U-1 to U-3 (Stalled)
5 | Tapovan Vishnugad 4x130=520 MW | Uttarakhand /NTPC |  |  | 520 |  | U-1 to U-4 |  | Dec'28
6 | Panan 4X75=300 MW | Sikkim/Himagiri |  |  | 300 |  | U-1 to U-4 (Stalled)
7 | Kandhaura PSP | Uttar Pradesh | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1680 | PSP | S&I | S&I | June'28
8 | Narihalla PSP | Karnataka | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 300 | PSP | S&I | S&I | September'28
9 | Gandikota | Andra Pradesh | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1000 | PSP | S&I | S&I | February'29
10 | Tarali | Maharastra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1500 | PSP | S&I | S&I | October'28
11 | Raiwada | Andra Pradesh | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 900 | PSP | S&I | S&I | March'29
12 | Bhivpuri | Maharashtra |  |  | 1000 |  | S&I | S&I | July'28
13 | Saundatii Off Stream PSP Project | Karnataka |  |  | 1600 |  | S&I | S&I | April'28
14 | Shahpur Off Stream PSP Project | Rajasthan |  |  | 1800 |  | S&I | S&I | May'28
15 | Veerabali | Andhra Pradesh |  |  | 1800 |  | S&I | S&I | May'28
16 | Upper Sileru | Andra Pradesh | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1350 | PSP | Concurred | Concurred | June'28
| Total |  |  |  | 14647 |  | 1
Year - 2029-30 | [6 empty] | 1
1 | Wah Umiam Stage-III (Mawphu stage-II) | Meghalaya |  |  | 85 | ROR (P) | Concurred |  | March
2 | Kirthai-II | J & K | Chenab | Chenab | 930 | RoR | Concurred |  | October
3 | Dugar | Himachal Pradesh | Chenab | Chenab | 500 | RoR | Concurred |  | July
4 | Dulhasti Stage-II | J & K | Chenab | Chenab | 260 | RoR | S&I |  | November
5 | Teesta Intermediate | West Bengal | Teesta | Teesta | 90 | ROR | S&I |  | December
6 | Tato-II | Arunachal Pradesh |  |  | 700 | Central | Concurred |  | Febbruary'30
7 | Turga | West Bengal |  |  | 1000 | State | Concurred |  | January'30
8 | Musakhand Pumped Storage | Uttar Pradesh | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 600 | PSP | S&I | S&I | February'30
9 | Sirohi PSP | Rajasthan | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1200 | PSP | S&I | S&I | April'29
10 | Malshejghat Bhorende | Maharastra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1500 | PSP | S&I | S&I | June'29
11 | Warasgaon Warangi | Maharastra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1500 | PSP | S&I | S&I | February'30
12 | Bhavali PSP | Maharashtra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1500 | PSP | S&I | S&I | July'29
13 | Pane PSP | Maharashtra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1500 | PSP | S&I | S&I | January'30
14 | Shirawta | Maharashtra | LR-Silli Nallah, tributary of Sipu river in West Banas Basin |  | 1800 | PSP | S&I | S&I | August'29
15 | UP01 Off Stream PSP Project | Uttar Pradesh |  |  | 3660 |  | S&I | S&I | February'30
16 | Sukhpura off Stream PSP Project | Rajasthan |  |  | 2560 |  | S&I | S&I | May'29
17 | Singanamala | Andhra Pradesh |  |  | 800 |  | S&I | S&I | March'30
| Total |  |  |  | 20185 |  | 1
|  | Sub-Total (2023-30) |  |  | 51537.5 |  | 1
Year - 2030-31 | [6 empty] | 1
1 | Etalin | Arunachal Pradesh |  |  | 3097 |  | Concurred |  | December'30
2 | Attunli | Arunachal Pradesh |  |  | 680 |  | Concurred |  | April'30
3 | Dikhu | Nagaland |  |  | 186 |  | Concurred |  | July'30
| Naying | Arunachal Pradesh |  |  | 1000 |  | Concurred |  | January'31
4 | Thana Plaun | Himachal Pradesh |  |  | 191 |  | Concurred |  | March'31
5 | Upper Indravati Pumped Storage Project | Odisha | Subarnarekha |  | 600 | PSP | S&I | S&I | March'31
6 | Owk | Andhra Pradesh | Subarnarekha |  | 800 | PSP | S&I | S&I | November'30
7 | Paidipalem East | Andhra Pradesh |  |  | 1200 |  | S&I | S&I | February'31
8 | Paidipalem North | Andhra Pradesh |  |  | 1000 |  | S&I | S&I | January'31
9 | Somasila | Andhra Pradesh | Subarnarekha |  | 900 | PSP | S&I | S&I | August'30
10 | Turga | West Bengal | Subarnarekha |  | 1000 | PSP | S&I | Concurred | May'30
11 | Total |  |  |  | 10654 |  | 1
Year - 2031-32 | [6 empty] | 1
1 | Talong Londa | Arunachal Pradesh | Kameng | Kameng | 225 | Private | Concurred |  | August'31
2 | Teesta St-IV | Sikkim | Teesta | Teesta | 520 | Central | Concurred |  | January'32
3 | Demwe Lower | Arunachal Pradesh | Lohit | Luhit | 1750 | Private | Concurred |  | March'32
4 | Sawalkote | J & K | Chenab | Chenab | 1856 | Central | Concurred |  | November'31
9 | Vempalli PSP | Andhra Pradesh | Kolab |  | 1500 | PSP | S&I | S&I | July'31
10 | Gujjili | Andhra Pradesh | Kolab |  | 1400 | PSP | S&I | S&I | October'31
| Total |  |  |  | 7251 |  | 1
|  | Grand-Total (2023-32) |  |  | 69442.5 |  | 1

## Year-wise_UC (hidden)
FY: 2023-24
Sl. No. | Name of Project | State/ Implem. Agency | Capacity (MW) |  | Unit No. | Remarks | S.No. | Name of Project | State | River | River Basin | IC (MW) | Type | Sector | Stage
1 | Subansiri Lower 8x250= 2000 MW | Arunachal Pradesh/NHPC | 500 | Center | U-1 to U-2
2 | Naitwar Mori 2x30=60 MW | Uttarakhand/SJVNL | 60 | Center | U-1 to U-2
3 | Pallivasal 2x30= 60 MW | Kerala/ KSEB Ltd. | 60 | State | U-1 to U-2
4 | Thottiyar 1x30+1x10= 40 MW | Kerala/ KSEB Ltd. | 40 | State | U-1 to U-2
Total (CS+SS+PS) |  |  | #REF!
FY: 2024-25
Sl. No. | Name of Project | State/ Implem. Agency | Capacity (MW) |  | Unit No. | Remarks
1 | Rangit-IV 3x40= 120 MW | Sikkim/NHPC Ltd. | 120 | Center | U-1 to U-3
2 | Subansiri Lower 8x250= 2000 MW | Arunachal Pradesh/NHPC | 1000 | Center | U-3 to U-6
3 | Parbati-II 4x200=800 MW | Himachal Pradesh/ NHPC | 800 | Center | U-1 to U-4
4 | Tehri PSS 4x250= 1000 MW | Uttarakhand/THDC | 1000 | Center | U-1 to U-4
5 | Kundah Pumped Storage (Phase-I, Phase-II & Phase-III) 4x125=500 MW | Tamil Nadu/TANGEDCO | 500 | State | U-1 to U-4
6 | Polavaram 12x80= 960 MW | Andhra Pradesh/ Polavaram Project Authority | 320 | State | U-1 to U-4
7 | Lower Kopili 2x55+2x2.5+1x5=120 MW | Assam/APGCL | 120 | State | U-1 to U-5
8 | Parnai 3x12.5= 37.5 MW | Jammu & Kashmir/JKSPDC | 37.5 | State | U-1 to U-3
9 | Uhl-III 3x33.33=100 MW | Himachal Pradesh/ BVPCL | 100 | State | U-1 to U-3
10 | Tidong-I 3x50= 150 MW | Himachal Pradesh/M/s Statkraft India Pvt. Ltd. | 150 | Private | U-1 to U-3
11 | Pinapuram 4x240+2x120 | Andhra Pradesh/Greenko | 1200 | Private | U-1 to U-6
Total (CS+SS+PS) |  |  | #REF!
FY: 2025-26
Sl. No. | Name of Project | State/ Implem. Agency | Capacity (MW) |  | Unit No. | Remarks
1 | Kiru 4x156=624 MW | Jammu & Kashmir/CVPPL | 624 | Central | U-1 to U-4
2 | Subansiri Lower 8x250= 2000 MW | Arunachal Pradesh/NHPC | 500 | Central | U-7 to U-8
3 | Luhri-I 2x80+2x25= 210MW | Himachal Pradesh/SJVN | 210 | Central | U-1 to U-4
4 | Dhaulasidh 2x33=66 MW | Himachal Pradesh/SJVN | 66 | Central | U-1 to U-2
5 | Tapovan Vishnugad 4x130=520 MW | Uttarakhand /NTPC | 520 | Central | U-1 to U-4
6 | Polavaram 12x80= 960 MW | Andhra Pradesh/ Polavaram Project Authority | 640 | State | U-5 to U-12
7 | Shahpurkandi 3x33+3x33+1x8= 206 MW | Punjab/Irr. Deptt. & PSPCL | 206 | State | U-1 to U-7
8 | Lower Sileru Extension (APGENCO) | Andhra Pradesh/ APGENCO | 230 | State | U-1 to U-2
9 | Kutehr 3x80=240 MW | Himachal Pradesh/JSW Energy | 240 | Private | U-1 to U-3
Total (CS+SS+PS) |  |  | #REF!
FY: 2026-27
Sl. No. | Name of Project | State/ Implem. Agency | Capacity (MW) |  | Unit No. | Remarks
1 | Kwar 4x135=540 MW | Jammu & Kashmir/CVPPL | 540 | Central | U-1 to U-4
2 | Ratle 4x205+1x30= 850 MW | Jammu & Kashmir/ NHPC | 850 | Central | U-1 to U-5
3 | Rammam - III 3x40=120 MW | West Bengal/ NTPC Ltd. | 120 | Central | U-1 to U-3
4 | Teesta- VI 4x125= 500 MW | Sikkim/NHPC | 500 | Central | U-1 to U-4
5 | Pakal Dul 4x250= 1000 MW | Jammu & Kashmir/CVPPL | 1000 | Central | U-1 to U-4
6 | Vishnugad Pipalkoti 4x111= 444 MW | Uttarakhand/THDC | 444 | Central | U-1 to U-4
7 | Shongtong Karcham 3x150= 450 MW | Himachal Pradesh/HPPCL | 450 | State | U-1 to U-3
8 | Mankulam 2x20= 40 MW | Kerala/ KSEB Ltd. | 40 | State | U-1 to U-2
Total (CS+SS) |  |  | #REF!
FY: 2027-28
Sl. No. | Name of Project | State/ Implem. Agency | Capacity (MW) |  | Unit No. | Remarks
1 | Sunni Dam 4x73+1x73+1x17=382 MW | Himachal Pradesh/SJVNL | 382 | Central | U-1 to U-6
2 | Chanju-III 3x16= 48 MW | Himachal Pradesh/HPPCL | 48 | State | U-1 to U-3
Total (CS+SS) |  |  | #REF!
FY: 2028-29
Sl. No. | Name of Project | State/ Implem. Agency | Capacity (MW) |  | Unit No. | Remarks
1 | Lakhwar Multipurpose Project (3x100=300 MW) | Uttarakhand/UJVNL | 300 | State | U-1 to U-3
Total |  |  | 300
FY: 2031-32
Sl. No. | Name of Project | State/ Implem. Agency | Capacity (MW) |  | Unit No. | Remarks
1 | Dibang Multipurpose Project 240x12=2880 | Arunachal Pradesh/NHPC | 2880 | Central | U-1 to U-12
|  | Total | 2880
|  | Grand Total (Active) | #REF!
Stalled HEPs
Sl. No. | Name of Project | State/ Implem. Agency | Capacity (MW) |  | Unit No.
1* | Lata Tapovan 3X57=171 MW | Uttarakhand/NTPC | 171 | Central | U-1 to U-3
2* | Koyna Left Bank 2X40=80 MW | Maharashtra/WRD | 80 | State | U-1 to U-2
3* | Lower Kalnai 2X24=48 MW | Jammu & Kashmir/JKSPDC | 48 | State | U-1 to U-2
4* | Tangnu Romai 2X22=44 MW | Himachal Pradesh/TRPG | 44 | Private | U-1 to U-2
5* | Maheshwar 10X40=400 MW | Madhya Pradesh/SMHPCL | 400 | Private | U-1 to U-10
6* | Bhasmey 2X25.5=51 MW | Sikkim/Gati Infrastructure | 51 | Private | U-1 to U-2
7* | Rangit-II 2X33=66 MW | Sikkim/Sikkim Hydro | 66 | Private | U-1 to U-2
8* | Phata Byung 2X38=76 MW | Uttarakhand/ LANCO | 76 | Private | U-1 to U-2
9* | Panan 4X75=300 MW | Sikkim/Himagiri | 300 | Private | U-1 to U-4
|  | Total (CS+SS+PS) | #REF!
* Construction is presently held up
|  | Grand Total (Active+Stalled) | #REF!

## Summary (hidden)
SUMMARY
Tentative Year-wise Hydro Capacity Addition for the period 2023-24 till 2031-32
[15 empty] | Stalled |  | Total
Sector | 2023-24 |  | 2024-25 |  | 2025-26 |  | 2026-27 |  | 2027-28 |  | 2028-29 |  | 2031-32
| MW | Nos. | MW | Nos. | MW | Nos. | MW | Nos. | MW | Nos. | MW | Nos. | MW | Nos. | MW | Nos. | MW | Nos.
Central Sector | #REF! | 2# | #REF! | 4# | #REF! | 5# | #REF! | 6 | #REF! | 1 | 0 | 0 | 2880 | 1 | 171 | 1 | #REF! | 18
State Sector | #REF! | 2 | #REF! | 5# | #REF! | 3# | 490 | 2 | #REF! | 1 | 300 | 1 | 0 | 0 | 128 | 2 | #REF! | 15
Private Sector | 0 | 0 | #REF! | 2# | #REF! | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 937 | 6 | #REF! | 9
Total | #REF! | 4# | #REF! | 11# | #REF! | 9# | #REF! | 8 | #REF! | 2 | 300 | 1 | 2880 | 1 | 1236 | 9 | #REF! | 42
Note:-Presently 42 no. of hydro electric project (above 25 MW) totaling to 18033.5 MW are under implementation (CS-18 nos.(12287 MW),SS-15 nos.(3219.5 MW),PS-9 nos. (2527 MW)). Out of these,32 no. HEPs totaling to 16797.5 MW are under active construction (CS – 17 nos. (12116 MW), SS – 13 nos. (3091.5 MW), PS – 3 nos. (1590 MW) and 9 no. HEPs totaling to 1236 MW are presently stalled.
#Polavaram,Subansiri Lower HEP are bifurcated for benefits during more than one year.

## Cummulative (hidden)
As on 31.10.23
HYDRO CAPACITY ADDITION FROM THE YEAR 2023-32
| Conventional |  |  |  |  | Pumped Storage Plant |  |  |  |  | Total( Conventional + PSP)
| Under Construction |  | Concurred & yet to be taken up for construction (Candidate) | Candidate (Under S&I Canditate) | Sub-Total (Conv.) | Under Construction |  | Concurred & yet to be taken up for construction (Candidate) | Candidate (Under S&I Canditate) | Sub-Total (PSP) | Under Construction |  | Concurred & yet to be taken up for construction (Candidate) | Candidate (Under S&I Canditate) | Grand Total
| Under Active Construction | Presently Stalled |  |  |  | Under Active Construction | Presently Stalled |  |  |  | Under Active Construction | Presently Stalled
2023-24 | 600 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 600
2024-25 | 2647.5 | 0 | 0 | 0 | 2647.5 | 2200 | 0 | 0 | 0 | 2200 | 4847.5 | 0 | 0 | 0 | 4847.5
2025-26 | 3236 | 76 | 0 | 0 | 3312 | 500 | 0 | 0 | 0 | 500 | 3736 | 76 | 0 | 0 | 3812
2026-27 | 3944 | 48 | 0 | 0 | 3992 | 0 | 0 | 0 | 8380 | 8380 | 3944 | 48 | 0 | 8380 | 12372
2027-28 | 430 | 561 | 483 | 0 | 1474 | 0 | 80 | 0 | 3000 | 3080 | 430 | 641 | 483 | 3000 | 4554
2028-29 | 300 | 471 | 426 | 0 | 1197 | 0 | 0 | 1350 | 0 | 1350 | 300 | 471 | 1776 | 0 | 2547
2029-30 | 0 | 0 | 1515 | 350 | 1865 | 0 | 0 | 1000 | 2300 | 3300 | 0 | 0 | 2515 | 2650 | 5165
Sub total :2023-24 to 2029-30 | 11157.5 | 1156 | 2424 | 350 | 15087.5 | 2700 | 80 | 2350 | 13680 | 18810 | 13857.5 | 1236 | 4774 | 14030 | 33897.5
2030-31 | 0 | 0 | 421 | 0 | 421 | 0 | 0 | 0 | 16095 | 16095 | 0 | 0 | 421 | 16095 | 16516
2031-32 | 2880 | 0 | 7448 | 480 | 10808 | 0 | 0 | 0 | 7340 | 7340 | 2880 | 0 | 7448 | 7820 | 18148
Sub total :2030-31 to 2031-32 | 2880 | 0 | 7869 | 480 | 11229 | 0 | 0 | 0 | 23435 | 23435 | 2880 | 0 | 7869 | 23915 | 34664
Total :2023-24 to 2031-32 | 14037.5 | 1156 | 10293 | 830 | 26316.5 | 2700 | 80 | 2350 | 37115 | 42245 | 16737.5 | 1236 | 12643 | 37945 | 68561.5

## Pending due to EC FC Convention (hidden)
Concurred by CEA and yet to be taken up for Construction(Conventional HEPs)
S. No | Name of Scheme | State/UT | Sector | Developer | Installed Capacity (MW) | Date of CEA concurrence/ appraisal
CATEGORY-I: Pending due to Environment and Forest Clearance issues
(a) Environment Clearance received and Forest Clearance yet to be obtained
1 | Teesta St-IV | Sikkim | Central | NHPC | 520 | 13.05.10
2 | Tawang St-I | Arunachal Pradesh | Central | NHPC | 600 | 10.10.11
3 | Tawang St-II | Arunachal Pradesh | Central | NHPC | 800 | 22.09.11
4 | Wah-Umiam Stage-III | Meghalaya | Central | NEEPCO | 85 | 26.07.21
5 | Thana Plaun | Himachal Pradesh | State | HPPCL | 191 | 07.09.21
6 | Kirthai-II | J&K | JV | CVPPL | 930 | 14.06.19
7 | Sawalkot | J&K | Central | NHPC | 1856 | 18.04.18
8 | Dugar | Himachal Pradesh | Central | NHPC | 500 | 26.04.22
9 | Heo | Arunachal Pradesh | Central | NEEPCO | 240 | 28.07.15
10 | Tato-I | Arunachal Pradesh | Central | NEEPCO | 186 | 28.10.15
11 | Tato-II | Arunachal Pradesh | Central | NEEPCO | 700 | 22.05.12
12 | Etalin | Arunachal Pradesh | Central | SJVNL | 3097 | 12.07.13
| Sub Total |  |  |  | 9705
(b) Both Environment and Forest Clearance yet to be obtained
13 | Hirong | Arunachal Pradesh | Central | NEEPCO | 500 | 10.04.13
14 | Naying | Arunachal Pradesh | Central | NEEPCO | 1000 | 11.09.13
15 | Uri-I Stage-II | J&K | Central | NHPC | 240 | 07.03.23
16 | Attunli | Arunachal Pradesh | Central | SJVN | 680 | 02.07.18
17 | Dikhu | Nagaland | Private | NMPPL | 186 | 31.03.14
| Sub Total |  |  |  | 3956
(c) Environment and Forest Clearance Subjudice
18 | Kotlibhel Stage-IA | Uttarakhand | Central | NHPC | 195 | 03.10.06
19 | Kotlibhel Stage-IB | Uttarakhand | Central | NHPC | 320 | 31.10.06
Stage-IB
20 | Alaknanda | Uttarakhand | Private | GMRL | 300 | 08.08.08
| Sub total |  |  |  | 815
| Total (pending for E&F clearance) |  |  |  | 14476
CATEGORY-II: Environment and Forest Clearance accorded and pending due to other reasons
21 | New Ganderwal | J&K | State | JKSPDC | 93 | 10.06.14
22 | Nafra | Arunachal Pradesh | Central | NEEPCO | 120 | 11.02.11
| Total (pending for other reasons) |  |  |  | 1213
CATEGORY-III: MoU/ MoA/ Implementation agreement cancelled/ terminated
23 | Chhatru | Himachal Pradesh | Private | DSIL | 126 | 15.01.15
24 | Miyar | Himachal Pradesh | Central | NTPC | 120 | 07.02.13
| Subtotal (MoU cancelled) |  |  |  | 246
CATEGORY- IV: Validity of concurrence expired
25 | Lower Siang | Arunachal Pradesh | Private | JAVL | 2700 | 16.02.10
26 | Demwe Lower | Arunachal Pradesh | Private | ADPL | 1750 | 20.11.09
27 | Kalai-II | Arunachal Pradesh | Private | Kalai PPL | 1200 | 27.03.15
28 | Talong Londa | Arunachal Pradesh | Private | GMR | 225 | 16.08.13
| Subtotal (Concurrence expired) |  |  |  | 5875
| Grand Total |  |  |  | 21810

## Pending (PSP) (hidden)
Concurred by CEA and yet to be taken up for Construction(PSPs)
S. No | Name of Scheme | State/UT | Sector | Developer | Installed Capacity (MW) | Date of CEA concurrence/ appraisal
CATEGORY-I: Pending due to Environment and Forest Clearance issues
(b) Both Environment and Forest Clearance yet to be obtained
1 | Upper Sileru | Andhra Pradesh | State | APGENCO | 1350 | 13.06.23
| Sub Total |  |  |  | 1350
CATEGORY-II: Environment and Forest Clearance accorded and pending due to other reasons
2 | Turga Pumped Storage Project | West Bengal | State | WBSPCL | 1000 | 05.10.16
| Total (pending for other reasons) |  |  |  | 1000
| Grand Total |  |  |  | 2350

## State-wise PSPs (hidden)
State-Wise PSPs
State | Count of PSP | Sum of IC (MW)
Andhra Pradesh | 11 | 11100
Jharkhand | 1 | 1500
Karnataka | 3 | 3900
Madhya Pradesh | 2 | 2445
Maharashtra | 6 | 8480
Odisha | 3 | 1420
Rajasthan | 3 | 5560
Tamilnadu | 1 | 500
Uttar Pradesh | 2 | 5340
Uttarakhand | 1 | 1000
West Bengal | 1 | 1000
Grand Total | 34 | 42245

## Held up (2) (hidden)
Annex-II
Hydroelectric Projects allotted for development on which Survey & Investigation is held up
Sl. No. | Scheme | Basin/River | State | District | Installed Capacity (MW) | Agency | Date of Allotment/ MoA | Status
Jammu & Kashmir
1 | Shamnot | Chenab | J&K | Doda | 370 | JKSPDCL | - | S&I held up as the project will submerge National Highway.
| Total (J&K) |  |  |  | 370
Himachal Pradesh
2 | Khab | Sutluj | Himachal Pradesh | Kinnaur | 636 | HPPCL | 22.09.2009 | Govt. of HP has confirmed the TWL of Upstream project i.e. Yangthang Khab and FRL of Downstream project Jhangi Thopan vide letter dated 15.06.2017. Accordingly a revised PFR for Khab HEP is being prepared considering the scheme to be single stage RoR and considering the virgin stretch of river as per MoEF&CC guidelines.
3 | Gyspa Dam | Bhaga | Himachal Pradesh | Lahaul & Spiti | 300 | HPPCL | 22.09.2009 | S&I held up due to sustained opposition from local people.
4 | Nakhtan (Parbati-I) | Parbati | Himachal Pradesh | Kullu | 460 | HPPCL | 22.09.2011 | Request of HPPCL for monitoring of Nakthan HEP to be put on hold received on 31.12.18 on account of CEIA study of Beas Basin & Hearing of court case on regular basis.
5 | Jangi Thopan Powari HEP | Satluj | Himachal Pradesh | Kinnaur | 804 | SJVN Ltd. | 25.09.2019 | Pre-DPR Chapters returned after there is no progress in the S&I activities by the developer
6 | Tidong-II | Tidong | Himachal Pradesh | Kinnaur | 60 | Tidong Hydro Power Ltd. | 20.01.2012 | S&I is held up due to local public agitation & there is no progress in the S&I activities of the project for a long time.
7 | Tandi Rashil HEP | Chenab | Himachal Pradesh | Lahaul & Spiti | 268 | SJVN Ltd. | 30.09.2022 | Developer vide letter dt. 01.09.23 has informed that no significant progress has been made in S&I work as locals have been resisting entry into project area since March,2022
8 | Luhri Stage-II | Satluj | Himachal Pradesh | Mandi & Kullu | 172 | SJVN Ltd. | 25.09.2019 | SJVN vide letter dt. 01.09.23 informed that domain allotment is pending with GoHP and layout of the project could not be finalized.
| Total (Himachal Pradesh) |  |  |  | 2700
Uttarakhand
9 | Chunger - Chal | Dhauliganga | Uttarakhand | Pithoragarh | 120 | NHPC | 21.11.2005 | S&I was held up due to MoEF Clearance. Project in Askot wild life Sanctuary. PCCF (Wildlife) and Chief Warden Wildlife, Dehradun has since granted permission for S&I on 17.05.2016. NHPC vide letter dated 09.04.2018 intimated GoUK that it is not presently prudent to proceed further with implementation of Chungar Chal HE Project. State Govt. has requested NHPC to inform about their final decision on the project.
10 | Sela Urthing | Dhauliganga | Uttarakhand | Pithoragarh | 114 | UJVNL | 09.12.2004 | S&I held up due to MOJS is not in favour of consutruction of any other HEP in Ganga Basin
11 | Bokang Bailing | Dhauliganga | Uttarakhand | Pithoragarh | 200 | THDC | 21.11.2005 | S&I held up due to MOJS is not in favour of consutruction of any other HEP in Ganga Basin
12 | Devsari HEP | Pinder | Uttarakhand | Chamoli | 194 | SJVN Ltd. | Nov., 2005 | Pre-DPR Chapters returned after there is no progress in the S&I activities by the developer
| Total (Uttarakhand) |  |  |  | 628
Arunachal Pradesh
13 | Naba HEP (ROR) | Subansiri | Ar. Pradesh | Upper Subansiri | 1105 | Naba Power Private Ltd. | 21.06.2010 | Project taken out of S&I list till developer submit letter from GoAP regarding continuation of the project with the developer in view of MoP letter dt. 11.05.23
14 | Anjaw HEP (ROR) | Lohit | Ar. Pradesh | Anjaw | 270 | Lohit Urja Pvt. Ltd. | 09.07.2007 | Project taken out of S&I list till developer submit letter from GoAP regarding continuation of the project with the developer in view of MoP letter dt. 11.05.23
15 | Pauk | Siang | Ar. Pradesh | West Siang | 145 | Velcan Energy Pvt Ltd | 30.06.2007 (rev MOA-31.07.09) | S&I held up due to land disputes between clans and law & order problem.
| Total (Ar. Pradesh) |  |  |  | 1520
Meghalaya
16 | Selim | Myntdu | Meghayala | East & West Jaintia Hills | 170 | MePGCL |  | S&I held up due to irregular allocation/release of funds, the hostile terrain, non and non-availability of geologists from GSI, India. MePGCL vide their letter dated 01.11.2019 informed that installed capacity is likely to be 60 MW. Report on Site Specific Design Earthquake Parameters submitted to CWC on 30.11.21 by developer.
| Total (Meghalaya) |  |  |  | 170
| Total (All India) |  |  |  | 5388
Note : following have been shifted to Balance Category from S&I held up
1 | Sumte Kothang | Spiti | Himachal Pradesh | Lahaul & Spiti | 130 | Reliance Power Ltd. (M/s Sumte Kothang HPPL) | 31.12.2012 | S&I held up due to opposition from locals and NGOs. Project stands terminated on 28.07.2017. | - | - | - | - | - | - | - | - | - | 43 | 51 | Opposition from locals/ NGOs. Project is likely to cost less than Rs. 1000 Crores - DPR to be submitted to State Govt. for approval
2 | Lara Sumta | Spiti | Himachal Pradesh | Kinnaur | 104 | Reliance Power Ltd. (M/s Lara Sumte HPPL) | 31.12.2012 | S&I held up due to opposition from locals and NGOs. Project stands terminated on 28.07.2017. | - | - | - | - | - | - | - | - | - | 43 | 51 | Opposition from locals/ NGOs. Project is likely to cost less than Rs. 1000 Crores - DPR to be submitted to State Govt. for approval
3 | Garba Tawaghat | MahaKali | Uttarakhand | Pithoragarh | 630 | NHPC | 21.11.2005 | MoEF&CC haas issued draft notification on 29.01.2019 regarding proposed ESZ of Askot Wildlife Sancutary. Publication of final notification of boundaries is still awaited. Being located on Mahakali River, the project would need to be developed jointly with Nepal under the provision of Mahakali Treaty.
4 | Tamak Lata | Dhauliganga | Uttarakhand | Chamoli | 280 | UJVNL | 09.12.2004 | Project included in the list of 24 HE peroject named in PIL under consideration by Hon'ble Supreme Court.
5 | Subansiri Upper | Singit | Ar. Pradesh | Upper Subansiri | 1800 | KSK Energy Ventures Ltd | 18.03.2010 | Earlier the project was alloted to KSK Energy Ventures Ltd. The Project has been allotted to NHPC in July 2023
6 | Kynshi-II | Kynshi | Meghayala | West Khasi Hills | 450 | GoMe & Jaiprakash Power Venture Ltd. (JV) | 11.12.2007 | S&I held up on account of non-finalisation of dam location/height due to deposit of Uranium. I.C. revised to 325 MW. GoMe informed vide their letter dated 28.11.2019 that project has been kept in abeyance since 2012 due to presence of Uranium deposits within the Dam & Reservoir areas of the project.
7 | Kalez khola | Kalez Khola | Sikkim | West Sikkim | 52 | CWC | 12.2.2007 | Due to objection raised by local people against Topographical Survey.
8 | Suntaleytar | Rangpo Chu | Sikkim | East Sikkim | 40 | Hindustan Electric Power Ltd. | LOI date 23.02.12 | S&I to be taken up after finalization of MOA.
9 | Teesta Low Dam I&II | Badi Rangit | West Bengal | Darjiling | 71 | NHPC Ltd. | 03.07.2015 | The project was alloted to NHPC. However, withdrawal of consent for the project by Govt. of Sikkim on 30.01.2017.
10 | Salki | Salki | Odisha | Boudh | 65 | OHPCL |  | Project shifted to S&I held up as no progress in the S&I activities of project reported by developer.
11 | Kharag | Kharag | Odisha | Kandhmal | 63 | OHPCL |  | Project shifted to S&I held up as no progress in the S&I activities of project reported by developer.
Pumped Storage Projects allotted for development on which Survey & Investigation is held up
Sl. No. | Scheme | Basin/River | State | District | Installed Capacity (MW) | Agency | Date of Allotment/ MoA | Status
Tamil Nadu
1 | Kodayar PSP | Kodayar | Tamil Nadu | Kanyakumari | 1500 | TANGEDCO |  | Pre-DPR Chapters returned after there is no progress in the S&I activities by the developer
| Total (Tamil Nadu) |  |  |  | 1500
Andhra Pradesh
2 | Kurukutti | UR-Minor nallah draining into Boduru Gedda river, LR-Boduru Gedda river | Andhra Pradesh | Vizianagaram | 1200 | Adani Green Energy Ltd. | 29.06.2022 | Project site (partly) falls within the disputed boundary between Govt. of Andhra Pradesh and Govt. of Odisha. Drilling Held up.
3 | Karrivalasa | UR-Minor nallah draining into Boduru Gedda river, LR-Boduru Gedda river | Andhra Pradesh | Vizianagaram | 1000 | Adani Green Energy Ltd. | 29.06.2022
| Total (Andhra Pradesh) |  |  |  | 2200
| Total (All India) |  |  |  | 3700

## Year-wise_UC (2) (hidden)
List of active under construction Hydro projects (above 25 MW)- Year Wise
FY: 2023-24
Sl. No. | Name of Project | Unit No. | State/ Implem. Agency | Capacity (MW) | Remarks
Central Sector
1 | Subansiri Lower 8x250= 2000 MW | U-1 to U-2 | Arunachal Pradesh/NHPC | 500
2 | Naitwar Mori 2x30=60 MW | U-1 to U-2 | Uttarakhand/SJVNL | 60
|  |  | Sub- total (Central): | 560
State Sector
3 | Pallivasal 2x30= 60 MW | U-1 to U-2 | Kerala/ KSEB Ltd. | 60
4 | Thottiyar 1x30+1x10= 40 MW | U-1 to U-2 | Kerala/ KSEB Ltd. | 40
|  |  | Sub- total (State): | 100
Total (CS+SS+PS) |  |  |  | 660
FY: 2024-25
Sl. No. | Name of Project | Unit No. | State/ Implem. Agency | Capacity (MW) | Remarks
Central Sector
1 | Rangit-IV 3x40= 120 MW | U-1 to U-3 | Sikkim/NHPC Ltd. | 120
2 | Subansiri Lower 8x250= 2000 MW | U-3 to U-6 | Arunachal Pradesh/NHPC | 1000
3 | Parbati-II 4x200=800 MW | U-1 to U-4 | Himachal Pradesh/ NHPC | 800
4 | Tehri PSS 4x250= 1000 MW | U-1 to U-4 | Uttarakhand/THDC | 1000
|  |  | Sub- total (Central): | 2920
State Sector
5 | Kundah Pumped Storage (Phase-I, Phase-II & Phase-III) 4x125=500 MW | U-1 to U-4 | Tamil Nadu/TANGEDCO | 500
6 | Polavaram 12x80= 960 MW | U-1 to U-4 | Andhra Pradesh/ Polavaram Project Authority | 320
7 | Lower Kopili 2x55+2x2.5+1x5=120 MW | U-1 to U-5 | Assam/APGCL | 120
8 | Parnai 3x12.5= 37.5 MW | U-1 to U-3 | Jammu & Kashmir/JKSPDC | 37.5
9 | Uhl-III 3x33.33=100 MW | U-1 to U-3 | Himachal Pradesh/ BVPCL | 100
|  |  | Sub- total (State): | 1077.5
Private Sector
10 | Tidong-I 3x50= 150 MW | U-1 to U-3 | Himachal Pradesh/M/s Statkraft India Pvt. Ltd. | 150
11 | Pinapuram 4x240+2x120 | U-1 to U-6 | Andhra Pradesh/Greenko | 1200
|  |  | Sub- total (Private): | 1350
Total (CS+SS+PS) |  |  |  | 5347.5
FY: 2025-26
Sl. No. | Name of Project | Unit No. | State/ Implem. Agency | Capacity (MW) | Remarks
Central Sector
1 | Kiru 4x156=624 MW | U-1 to U-4 | Jammu & Kashmir/CVPPL | 624
2 | Subansiri Lower 8x250= 2000 MW | U-7 to U-8 | Arunachal Pradesh/NHPC | 500
3 | Luhri-I 2x80+2x25= 210MW | U-1 to U-4 | Himachal Pradesh/SJVN | 210
4 | Dhaulasidh 2x33=66 MW | U-1 to U-2 | Himachal Pradesh/SJVN | 66
5 | Tapovan Vishnugad 4x130=520 MW | U-1 to U-4 | Uttarakhand /NTPC | 520
|  |  | Sub- total (Central): | 1920
State Sector
6 | Polavaram 12x80= 960 MW | U-5 to U-12 | Andhra Pradesh/ Polavaram Project Authority | 640
7 | Shahpurkandi 3x33+3x33+1x8= 206 MW | U-1 to U-7 | Punjab/Irr. Deptt. & PSPCL | 206
8 | Lower Sileru Extension (APGENCO) | U-1 to U-2 | Andhra Pradesh/ APGENCO | 230
|  |  | Sub- total (State): | 1076
Private Sector
9 | Kutehr 3x80=240 MW | U-1 to U-3 | Himachal Pradesh/JSW Energy | 240
|  |  | Sub- total (Private): | 240
Total (CS+SS+PS) |  |  |  | 3236
FY: 2026-27
Sl. No. | Name of Project | Unit No. | State/ Implem. Agency | Capacity (MW) | Remarks
Central Sector
1 | Kwar 4x135=540 MW | U-1 to U-4 | Jammu & Kashmir/CVPPL | 540
2 | Ratle 4x205+1x30= 850 MW | U-1 to U-5 | Jammu & Kashmir/ NHPC | 850
3 | Rammam - III 3x40=120 MW | U-1 to U-3 | West Bengal/ NTPC Ltd. | 120
4 | Teesta- VI 4x125= 500 MW | U-1 to U-4 | Sikkim/NHPC | 500
5 | Pakal Dul 4x250= 1000 MW | U-1 to U-4 | Jammu & Kashmir/CVPPL | 1000
6 | Vishnugad Pipalkoti 4x111= 444 MW | U-1 to U-4 | Uttarakhand/THDC | 444
|  |  | Sub- total (Central): | 3454
State Sector
7 | Shongtong Karcham 3x150= 450 MW | U-1 to U-3 | Himachal Pradesh/HPPCL | 450
8 | Mankulam 2x20= 40 MW | U-1 to U-2 | Kerala/ KSEB Ltd. | 40
|  |  | Sub- total (State): | 490
Total (CS+SS) |  |  |  | 3944
FY: 2027-28
Sl. No. | Name of Project | Unit No. | State/ Implem. Agency | Capacity (MW) | Remarks
Central Sector
1 | Sunni Dam 4x73+1x73+1x17=382 MW | U-1 to U-6 | Himachal Pradesh/SJVNL | 382
|  |  | Sub- total (Central): | 382
State Sector
2 | Chanju-III 3x16= 48 MW | U-1 to U-3 | Himachal Pradesh/HPPCL | 48
|  |  | Sub- total (State): | 48
Total (CS+SS) |  |  |  | 430
FY: 2028-29
Sl. No. | Name of Project | Unit No. | State/ Implem. Agency | Capacity (MW) | Remarks
State Sector
1 | Lakhwar Multipurpose Project (3x100=300 MW) | U-1 to U-3 | Uttarakhand/UJVNL | 300
|  |  | Sub- total (State): | 300
Total |  |  |  | 300
FY: 2031-32
Sl. No. | Name of Project | Unit No. | State/ Implem. Agency | Capacity (MW) | Remarks
Central Sector
1 | Dibang Multipurpose Project 240x12=2880 | U-1 to U-12 | Arunachal Pradesh/NHPC | 2880
|  |  | Sub- total (Central): | 2880
|  |  | Total | 2880
|  |  | Grand Total (Active) | 16797.5
Stalled HEPs
Sl. No. | Name of Project | Unit No. | State/ Implem. Agency | Capacity (MW)
Central Sector
1* | Lata Tapovan 3X57=171 MW | U-1 to U-3 | Uttarakhand/NTPC | 171
|  |  | Sub- total (Central): | 171
State Sector
2* | Koyna Left Bank 2X40=80 MW | U-1 to U-2 | Maharashtra/WRD | 80
3* | Lower Kalnai 2X24=48 MW | U-1 to U-2 | Jammu & Kashmir/JKSPDC | 48
|  |  | Sub- total (State): | 128
Private Sector
4* | Tangnu Romai 2X22=44 MW | U-1 to U-2 | Himachal Pradesh/TRPG | 44
5* | Maheshwar 10X40=400 MW | U-1 to U-10 | Madhya Pradesh/SMHPCL | 400
6* | Bhasmey 2X25.5=51 MW | U-1 to U-2 | Sikkim/Gati Infrastructure | 51
7* | Rangit-II 2X33=66 MW | U-1 to U-2 | Sikkim/Sikkim Hydro | 66
8* | Phata Byung 2X38=76 MW | U-1 to U-2 | Uttarakhand/ LANCO | 76
9* | Panan 4X75=300 MW | U-1 to U-4 | Sikkim/Himagiri | 300
|  |  | Sub- total (Private): | 937
|  |  | Total (CS+SS+PS) | 1236
* Construction is presently held up
|  |  | Grand Total (Active+Stalled) | 18033.5