## Records (3)
|  | List of Pumped Storage Projects granted ToR by MoEF&CC | [5 empty] | As on 30.05.2024
S.No | Pumped Storage Project | District | Type of Scheme | Installed Capacity | Company | Date of Grant of TOR | Status of EC &FC |  | status
[7 empty] | Date of Grant/ status EC | Date of Grant/ status FC
Andhra Pradesh
1 | Upper Sileru | Visakhapatnam | On Stream | 1350 | Andhra Pradesh Power Generation Corporation Limited (APGENCO) | 2019-06-03 | EC proposal discussed in EAC in Feb 24 deferred to next meeting; | In process | DPR Concurred on 13.06.2023
2 | Yerravaram | Visakhapatnam | On Stream | 1200 | Shirdi Sai Electricals Ltd. | 2022-01-24 |  |  | Under S&I held up
3 | Veeraballi | Kadapa | Off stream closed loop | 1800 | Astha Green Energy Ventures India Pvt Ltd | 2020-07-13 |  | In process | Under S&I
4 | Gandikota | Kadapa | Off Stream open loop | 1000 | Adani Green Energy Limited | 2022-01-04 | EC: EC proposal discussed in EAC in Oct 23, deferred for ADS; | In process | Under S&I
5 | Somasila | Kadapa | Off Stream closed loop | 900 | Shirdi Sai Electricals Ltd. | 2022-06-29 |  | In process | Under S&I
6 | Chitravathi | Anantapur | Off stream open loop | 500 | Adani Green Energy Limited | 2021-10-18 | EC: 28/08/2023 ; transfer of EC application submitted. | FC: not required | Under S&I
7 | Singanamala | Anantapur | Off stream closed loop | 800 | Aurobindo Realty & Infrastructure | 2023-02-13 | EC proposal submitted in Feb 24, EDS raised | In process | Under S&I
8 | Kurukutti | Vizianagaram | Off stream open loop | 1200 | Adani Green Energy Limited | 2021-12-16 |  |  | Under S&I held up
9 | Karrivalasa | Vizianagaram | Off stream open loop | 1000 | Adani Green Energy Limited | 2021-12-16 |  |  | Under S&I held up
10 | Owk | Kurnool | Off stream open loop | 800 | Aurobindo Realty & Infrastructure | 2022-01-04 |  |  | Under S&I
11 | Pinnapuram | Kurnool | Off stream closed loop | 1200 | Greenko Solar Energy Pvt. Ltd |  | EC: 14.07.2020 | FC-I: 23.05.2020; FC-II: 24.05.2021 | DPR Concurred on 20.04.2022
12 | Paidipalem North | YSR | Off stream closed loop | 1000 | Indosol Solar Power Pvt. Ltd. | 2023-04-17 |  | delisted | Under S&I
13 | Paidipalem East | YSR | Off stream closed loop | 1200 | Indosol Solar Power Pvt. Ltd. | 2023-04-17 |  | delisted | Under S&I
14 | Vempalli | YSR | Off stream closed loop | 1500 | JSW Energy | 2023-08-07 |  | In process | Under S&I
15 | Kamalapadu | Ananthapuramu | Off stream closed loop | 950 | APGENCO | 2023-08-07 |  |  | Under S&I
16 | Gujjili | Alluri Sitharama Raju | Off stream closed loop | 1500 | New And Renewable Energy Development Corporation Of Andhra Pradesh Ltd (NREDCAP) | 2023-08-07 |  |  | Returned/ S&I held up
17 | Chittamvalasa | Alluri Sitharama Raju | Off stream closed loop | 800 | New And Renewable Energy Development Corporation Of Andhra Pradesh Ltd (NREDCAP) | 2023-09-10 |  |  | Returned/ S&I held up
18 | Yaganti | Nandyal | Off stream closed loop | 1000 | APGENCO | 2023-08-07 |  |  | Under S&I
19 | Raiwada | Anakapalli and Vizianagaram | Off stream open loop | 850 | Adani Green Energy Limited | 2023-10-25 |  | In process | Under S&I
20 | Rayavaram | Annamayya | Off stream closed loop | 1500 | New And Renewable Energy Development Corporation Of Andhra Pradesh Ltd (NREDCAP) | 2024-01-30 |  |  | Under S&I
21 | Gadikota | Annamayya | Off stream closed loop | 1200 | APGENCO | 2024-01-30 |  |  | Under S&I
Chattisgarh
22 | Chikni | Surajpur | on-stream open loop | 325 | Chikini Energy Private Limited | 2023-08-07 |  |  | Proposal not yet received at CEA
23 | Kharauli | Surajpur | on-stream open loop | 500 | Kharauli Energy Private Limited | 2023-09-10 |  |  | Proposal not yet received at CEA
24 | Hasdeo Bango | Korba | On stream | 1200 | Chhattisgarh State Power Generation Company Limited | 2024-01-10 |  |  | Retrurned for revised submission
25 | CHH-09 | Surguja | Off Stream Closed Loop | 1200 | Sterlite Grid 36 Limited | 2024-01-22 |  |  | Proposal not yet received at CEA
26 | Gandhwani | Surguja | Off Stream Closed Loop | 1200 | Gandhwani Energy Private Limited | 2024-02-05 |  |  | Proposal not yet received at CEA
Gujarat
27 | Ukai | Tapi | Off stream | 2400 | Greenko Energies Private Limited | 2020-04-13 |  |  | Proposal not yet received at CEA
28 | Pindval | Valsad | Off stream | 1000 | Torrent Power Limited | 2023-09-23 |  |  | Proposal not yet received at CEA
29 | Tokarpada | Valsad | Off stream | 1300 | Torrent Power Limited | 2023-09-23 |  |  | Proposal not yet received at CEA
Karnataka
30 | Shanti Sagar | Davanagere | Off stream | 270 | Cerulean Energy Solutions Private Limited | 2020-01-17 |  |  | Proposal not yet received at CEA
31 | Vijayanagar | Bellary | Off stream closed loop | 130 | JSW Renewable Energy (Vijayanagar) Limited | 2022-06-03 | EC: recommended in Nov. 23 ; ADS raised. |  | Proposal concurred by state govt.
32 | Narihalla | Ballari | Off stream open loop | 300 | JSW Energy PSP Three Limited | 2023-07-05 |  | In process | Under S&I
33 | Sankanoor | Kalaburagi | Off-Stream Closed Loop | 300 | Cerulean Energy Solutions Private Limited | 2023-08-07 |  |  | Proposal not yet received at CEA
34 | Sharavathy | Uttara Kannada | On Stream | 2000 | Karnataka Power Corporation Limited | 2023-12-14 |  | In process | Under S&I
35 | Saundatti | Belgavi | Off stream closed loop | 1200 | Greenko Solar Energy Pvt. Ltd transfer to Greenko KA01 IREP Pvt. Ltd/ | 18.5.2018 amended 25.09.2018; transfer of EC proosal submitted on 28.11.23; ADS raised by MS | EC: 19.09.22 amended 24.03.2023; | FC-I: 18.12.2018 , FC-II pending | Under S&I
Madhya Pradesh
36 | MP 30 Gandhi Sagar | Neemuch | Off stream open loop | 1440 | Greenko Energies Private Limited | 2020-02-28 | 01-12- 2021 and its amendment Transfer of EC with dated: 13-02-2023; | FC-II: 09.06.2023 | Under S&I
37 | Panari | Satna | Off stream open loop | 1800 | Sri Siddharth Infratech & Services (I) Private Limited | 2020-03-13 |  |  | Returned
38 | Astha MP | Khargone | Off stream | 1200 | Astha Green Energy Ventures India Private Limited | 2023-04-17 |  |  | Proposal not yet received at CEA
39 | MP Pumped Storage Project | Panna | Off stream | 600 | Rithwik Projects Private Limited | 2023-06-13 |  |  | Proposal not yet received at CEA
40 | Rewa | Rewa | Off stream | 600 | Sasa Stone Private Limited | 2023-06-13 |  |  | Proposal not yet received at CEA
Maharashtra
41 | Mhaismal | Aurangabad | Off stream | 800 | Greenko Energies Private Limited | 2020-02-28 |  |  | Proposal not yet received at CEA
42 | Nayagaon | Aurangabad | Off-stream closed loop | 2000 | Greenko Energies Private Limited | 2020-04-13 |  | In process | Under S&I
43 | Bhavali | Nashik | On Stream | 1500 | JSW Energy PSP Two Limited | 2022-06-27 |  |  | Under S&I
44 | Patgaon | Kolhapur | On Stream | 2100 | Adani Green Energy Limited | 2022-11-09 |  |  | Returned/ S&I held up
45 | KOLHAPUR | Kolhapur | Off stream | 1200 | Rithwik Projects Private Limited | 2023-06-13 |  |  | Proposal not yet received at CEA
47 | Tarali | Satara | Off stream open loop | 1500 | Adani Green Energy Limited | 2024-01-03 |  |  | Under S&I
48 | Koyna-Nivakane | Satara | Off-stream closed loop | 2450 | Adani Green Energy Limited | 2023-08-07 |  |  | Under S&I
49 | Warasgaon Warangi | Pune | Off stream open loop | 1200 | Adani Green Energy Limited | 2023-02-13 |  |  | Under S&I
50 | Malshej Ghat Bhorande | Pune | Off stream closed loop | 1440 | Adani Green Energy Limited | 3/24/2023; amendment in TOR applied |  |  | Under S&I
51 | Shirawta | Pune | Off Stream open Loop | 1800 | The Tata Power Co. Ltd. | 9/23/2023; amendment of TOR applied |  | In process | Under S&I
52 | Bhivpuri | Raigarh | Off Stream open Loop | 1000 | The Tata Power Co. Ltd. | 2023-09-23 |  | In process | Under S&I
53 | Saidongar-2 | Pune and Raigarh | Off stream | 1200 | Torrent Power Limited | 2023-09-23 |  |  | Proposal not yet received at CEA
54 | Saidongar-1 | Pune and Raigarh | Off stream | 3000 | Torrent Power Limited | 2023-09-23 |  |  | Proposal not yet received at CEA
55 | Pane | Pune and Raigarh | Off stream open loop | 1500 | JSW Energy PSP Seven Limited | 2024-01-30 |  | In process | Under S&I
Odisha
56 | Upper Indravati | Kalahandi | OFF Stream open loop | 600 | Odisha Hydro Power Corporation Limited | 2023-12-14 |  |  | Under S&I
57 | Greenko OD01 | Kalahandi | Off stream | 1200 | Greenko Energies Private Limited | 2023-04-17 |  |  | Proposal not yet received at CEA
58 | Ramial Left | Keonjhar | Off stream | 1500 | Renew Solar Power Private Limited | 2024-01-15 |  |  | Proposal not yet received at CEA
59 | Tainsar | Deogarh | Off Stream open Loop | 675 | Jindal Renewable Power Private Limited | 2024-01-22 |  |  | Proposal not yet received at CEA
60 | Upper Kolab | Koraput | Off Stream open loop | 320 | Odisha Hydro Power Corporation Limited | 2020-02-28 |  |  | Returned/ S&I held up
61 | Balimela | Malkangiri | On Stream | 500 | Odisha Hydro Power Corporation Limited | 2020-05-21 |  |  | Returned/ S&I held up
Rajasthan
62 | Sukhpura | chittorgarh | Off stream Closed loop | 2560 | Greenko Energies Private Limited | 2020-02-28 |  |  | Under S&I
63 | Rana Pratap Sagar | chittorgarh | Offstream Close loop | 1200 | Semaliya Energy Private Limited | 2022-01-24 |  |  | Proposal not yet received at CEA
64 | Semaliya-II | chittorgarh | Offstream Close loop | 1200 | Semaliya Energy Private Limited | 2023-06-07 |  |  | Proposal not yet received at CEA
65 | Brahmani | Chittorgarh | Off stream | 600 | Acme Cleantech Solutions Private Limited | 2023-12-11 |  |  | Proposal not yet received at CEA
66 | Shahpur | Baran | Off stream Closed loop | 1800 | Greenko Energies Private Limited | 2020-04-13 | EC: proposal submitted to MoEF&CC for EC and is under examination | FC-I: 15.03.2024 | Under S&I
67 | Sirohi | Kolhapur | Off stream Closed loop | 640 | Sasa Stone Private Limited | 2023-06-13 |  | In process | Proposal not yet received at CEA
68 | Sirohi | Sirohi | Off stream Closed loop | 1200 | JSW Energy PSP One Limited | 2023-07-05 |  |  | Under S&I
Tamil Nadu
69 | Kundah | The Nilgiris | Off stream | 500 | Tamil Nadu Generation And Distribution Corporation | 2020-06-05 | EC: 12.02.2021 |  | DPR Concurred
70 | Sillahalla-I | The Nilgiris | On stream | 1000 | Tamil Nadu Generation and Distribution Corporation | 2020-09-23 |  |  | Returned / S&I held up
71 | Manalar | Theni | Off stream | 1200 | Tamil Nadu Generation and Distribution Corporation | 2023-04-17 |  |  | Proposal not yet received at CEA
72 | Greenko TN01 | Tirupathur | Off stream Closed loop | 1200 | Greenko Energies Private Limited | 2023-06-07 |  |  | Proposal not yet received at CEA
73 | Arunachalam | Dharamapuri and Tiruvannamalai | Off stream Closed loop | 900 | Volthills Private Limited | 2023-08-07 |  |  | Proposal not yet received at CEA
Telangana
74 | Ippagudem | Mulugu | Off stream Closed loop | 3960 | Greenko Energies Private Limited | 2020-07-13 |  |  | Proposal not yet received at CEA
75 | Ranapur | Adilabad | Off stream Closed loop | 1200 | Sri Siddharth Infratech & Services (I) Private Limited | 2022-12-08 |  |  | Proposal not yet received at CEA
76 | Greenko TS01 | Adilabad | Off stream Closed loop | 750 | Greenko Energies Private Limited | 2023-04-17 |  |  | Proposal not yet received at CEA
77 | Astha Telangana | Nizamabad | Off stream Closed loop | 600 | Astha Green Energy Ventures India Private Limited | 2023-06-07 |  |  | Proposal not yet received at CEA
78 | Cerulean-II | Komarambheem | Off stream Closed loop | 640 | Cerulean Energy Solutions Private Limited | 2023-06-07 |  |  | Proposal not yet received at CEA
Uttar Pradesh
79 | Greenko UP01 | Sonbhadra | Off stream Closed loop | 3660 | Greenko Energies Private Limited | 2022-01-24 |  | In process | Under S&I
80 | SONBHADRA | Sonbhadra | Offstream Close loop | 1200 | Sri Siddharth Infratech & Services (I) Private Limited | 2023-06-07 |  |  | Proposal not yet received at CEA
81 | Shoma | Sonbhadra | Off stream Closed loop | 2400 | Torrent Power Limited | 2023-08-07 |  |  | Under S&I
82 | Sashnai | Sonbhadra | Offstream Close loop | 1760 | Torrent Power Limited | 2023-12-14 |  |  | Proposal not yet received at CEA
83 | Kandhaura | Sonbhadra | Off stream Closed loop | 1680 | JSW Energy PSP Six Limited | 16.04.2024 |  | In process | Under S&I
84 | Astha UP | Mirzapur and Prayagraj | Offstream Close loop | 640 | Astha Green Energy Ventures India Private Limited | 2023-06-13 |  |  | Proposal not yet received at CEA
85 | Musakhand | Chandauli | Off stream Closed loop | 600 | Acme Cleantech Solutions Private Limited | 9/23/2023 applied for amendment |  | In process | Under S&I
West Bengal
86 | Bandu | Purulia | On stream | 900 | WBSEDCL | 2019-03-20 |  |  | Proposal not yet received at CEA
87 | Turga | Purulia |  | 1000 | WBSEDCL |  | EC: 02.07.2018 | FC-I: 12.04.2018; FC-II: 13.10.2022 | DPR Concurred on 05.10.2016
|  | Total |  | 104690